3GPP RAN-WG4 Meeting #97-e		R4-2014918

Electronic meeting, November 2 – 13, 2020

Agenda item:	13.1

Source:	Apple Inc., vivo

Title:	Updated work plan for FS_FR2_enhTestMethods

Release:	Rel-17

Document for:	Approval

# 1	Introduction

The Study on enhanced test methods for FR2 [1], approved during RAN #85 in September of 2019, had been suspended from the RAN4 agenda for the duration of the RAN4 #94e, #94e-bis, and RAN4 #95e meetings due to the prioritization of Rel-16 completion in RAN4.  This information had been captured in the Rapporteur’s status report to RAN #88e in [2].  In addition, several agreements in RAN4 had recommended a revision of the study item’s work scope in [3], [4], and [5].  This background motivated extending the study item’s scope and timeline during the RAN #89 meeting [6], [7].

This contribution provides an updated work plan for the study item based on the revised scope of the SID.

# 2	Discussion

The revised SID captures the following scope [7]:

1. Define test methodology for high DL power and low UL power test cases - Considering path loss reduction, measurement antenna gain improvement, DUT positioning improvement, and MU improvement - Considering NFTF (defined in Clause 5.2 of TR38.810) and direct near field test methodologies as possible alternative methods - The list of candidate non-permitted test systems is limited to NF based solutions - Study preliminary assessment of measurement uncertainty of new alternative methods 2. Define solutions to minimize the impact of polarization basis mismatch between the TE and DUT on the RF testing - Considering polarization basis mismatch between the test equipment and UE and UE implementations which may be impacted by this mismatch - Study EIS test metric which can apply to different UE RF implementations considering downlink polarization sweep enhancement - Limit the study of this objective to the permitted UE RF methods defined in Clause 5.2 of TR38.810 - Possible enhancements may be described as - Downlink polarization sweeping by the test equipment (i.e. introducing an additional degree of freedom for polarization alignment of the measurement antenna) - The use of circular polarization to perform measurements - Coherent combining and demodulation of orthogonally polarized received signals in the test equipment - Uplink polarization sweeping by the test equipment to search for the optimal polarization angle to receive and demodulate the signal transmitted by the UE - Considering NFTF (defined in Clause 5.2 of TR38.810) test methodology for EIS measurement - TPMI side condition method, where TPMI side conditions are applicable to Rel-16 (and higher) UEs - Test mode to trigger TX diversity - Other approaches are not precluded 3. Study testability enhancements to support the verification of RF requirements for inter-band (FR2+FR2) CA - Work on inter-band DL CA is prioritized - Whether the test setup shall be restricted to emulating the signal from the same direction for the aggregated bands shall be aligned with the UE RF architecture assumption taken in the work item on NR RF Requirement Enhancements for FR2 [UID 830189] 4. Support extreme temperature conditions for all applicable FR2 UE RF test cases - Considering beam peak search, spherical coverage, and total radiated power procedures - Limit the study of this objective to the permitted UE RF methods defined in Clause 5.2 of TR38.810 - Study preliminary impacts on system measurement uncertainty under extreme temperature conditions 5. Study testability enhancements to support the verification of RF requirements for FR2 DL 256QAM 6. Study testability enhancements to reduce test time - Including RF test method enhancement with reduced test time, and possible test time saving approach for UE Demodulation test and RRM test 7. Study testability aspects for the introduction of the new band n262 - Considering the extension of frequency applicability of the permitted methods in TR38.810 from 43.5 GHz up to at least 48.2 GHz - Considering the extension of frequency applicability of the test methodology enhancements in Objectives 1 through 6 above

Observation 1:	We note that Objective 7 implies that the study on enhanced test methods includes scope for RF, RRM, and demodulation with the goal of extending the frequency applicability to include the new band n262.

The following work plan is proposed:

RAN4 #97e (November 2020)

-	Reach preliminary conclusions for Objectives 1 – 3 and capture in TR38.884

-	Objective 4: discuss, and if necessary, agree on assumptions based on which impact on measurement uncertainty due to ET can be derived; begin to collect aspects which enhance the permitted methods in TR38.810 to enable ET test cases

-	Objectives 5, 6, 7: initial discussions

-	Approve revised work plan

RAN4 #98e (January 2021)

-	Finalize conclusions for Objectives 1 – 3 and capture in the TR

-	Objective 4: agree updated test setup which enables ET test cases and capture in TR38.884; make progress on uncertainty assessment

-	Objective 5: reach conclusions and capture in the TR

-	Objective 6: identify list of test time reduction techniques and agree a framework based on which a decision on the feasibility of each can be reached

-	Objective 7 (for the extension of applicability of permitted methods in TR38.810 to band n262): identify aspects which can impact measurement uncertainty over the new frequency range

-	Objective 7 (for the extension of applicability of Obj 1-6 to band n262): identify aspects which can impact measurement uncertainty over the new frequency range

RAN #91e (March 2021): Submit TR38.884 for information to RAN Plenary

RAN4 #98bis-e (April 2021)

-	Finalize conclusions for Objective 4 and capture in the TR

-	Make progress on Objectives 6 and 7

RAN4 #99e (May 2021)

-	Finalize conclusions for Objectives 6 and 7 and capture in the TR

RAN #92e (June 2021): Conclude the study and submit TR38.884 for approval to RAN Plenary

Observation 2:	The scope of any uncertainty assessment is understood to include the identification of potential new uncertainty elements and the derivation of an initial estimated value of its contribution.

Proposal 1:	It is proposed to approve the updated work plan for the Study on enhanced test methods for FR2.

# 3	Conclusions

This contribution has provided our proposal to update the work plan for the Study on enhanced test methods for FR2.

# 4	References

RP-201110, “Revised SID: Study on enhanced test methods for FR2,” Apple Inc., CAICT, 3GPP RAN #88e, June 2020

RP-201205, “Status report for SI Study on enhanced test methods for FR2 NR UEs,” 3GPP RAN #88e, June 2020

R4-2012713, “WF on the high DL power and low UL power test cases objective,” 3GPP RAN4 #96e, August 2020

R4-2012714, “WF on the polarization mismatch objective,” 3GPP RAN4 #96e, August 2020

R4-2011816, “WF on UE testability above 43.5 GHz,” R&S, Apple, 3GPP RAN4 #96e, August 2020

RP-201861, “Status report for the Study on enhanced test methods for FR2,” 3GPP RAN #89e, September 2020

RP-201862, “Revised WID for the Study on enhanced test methods for FR2,” Apple Inc., 3GPP RAN #89e, September 2020