3GPP TSG-RAN WG4 Meeting # 98-e	R4-2101798

Electronic Meeting, 25 January – 5 February 2021

Agenda Item:	14.1.1

Source: 	Nokia, Nokia Shanghai Bell, T-Mobile USA, U.S. Cellular

Title: 	Revised Work Plan for Study on High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, and Band n71

Document for:	Approval

# 1.	Introduction

The study item on High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, and Band n71 was approved at RAN#88-e [1]. The purpose of this study item is to study RF requirements that are applicable for high power UE operation in LTE band 12 and band 5, and in NR band n71 for fixed wireless and vehicle-mounted use cases, in ITU Region 2.

The target completion date of this study item is March 2021 at RAN#91. There are four RAN4 meetings (#96, #96is, #97, #98) in the time budget request worksheet in [1]. However, the RAN4#96bis and RAN4#97 physical meetings have been cancelled and will be combined into one RAN4#97e e-meeting. Therefore, there will only be three RAN4 meetings to complete this study item, hence careful work plan should be in place to achieve the target completion date.

The work plan for this study item was approved at RAN4#96-e [2] and updated at RAN4#97-e [3]. This contribution provides a revised work plan according to the current progress. In view of the cancelled physical meetings and the current progress of this study item, it is proposed to request at RAN#91 to extend the study item for one quarter to complete the remaining tasks. This revised work plan should be approved and used as guidance for agenda and contributions for this study item in the upcoming RAN4 e-meetings, considering the contribution cap per agenda item in the RAN4 e-meetings.

# 2.	Work plan

Table 1 summarizes the work plan for the RAN4 meetings before June 2021. The timeline and the TU allocation are based on the time budget request worksheet in [1] and one quarter extension to be requested at RAN#91 assuming the same time allocation in each RAN4 e-meetings in the extension quarter. The changes compared to [3] are shown by Track Changes.

Table 1: Work plan for RAN4 meetings before target completion date

| TSG/WG | Meeting Number | Date | TU | Tasks |
| --- | --- | --- | --- | --- |
| RAN4RF | #96-e | Aug 17-28, 2020 | 0.25 | 1) General - Approve initial work plan - Approve skeleton TR 2) Coexistence study - Agree initial simulation assumptions - Agree initial simulation results priority |
| RAN | #89-e |  |  |  |
| RAN4RF | #97-e | Nov 2-13, 2020 | 0.25 | 1) General - Approve revised work plan, if any - Approve updated TR 2) Coexistence study - Discuss initial simulation results - Agree revised simulation assumptions, if any - Agree revised simulation results priority |
| RAN | #90-e |  |  |  |
| RAN4RF | #98-e | Jan 25 to Feb 5, 2021 | 0.25 | 1) General - Approve revised work plan - Approve updated TR 2) Coexistence study - Further discuss simulation results 3) UE RF - Discuss analyses on UE operation - Discuss analyses on new components |
| RAN | #91-e |  |  |  |
| RAN4RF | #99-e | Apr 12-20, 2021 | 0.25 | 1) General - Approve revised work plan, if any - Approve updated TR 2) Coexistence study - Further discuss simulation results 3) UE RF - Further discuss analyses on UE operation - Further discuss analyses on new components |
| RAN4RF | #99b-e | May 19-27, 2021 | 0.25 | 1) General - Approve updated TR - Agree on conclusion of the study item 2) Coexistence study - Further discuss simulation results - Agree on conclusion of considered UE requirements from results 3) UE RF - Further analyses on UE operation - Further analyses on new components - Agree on conclusion of considered UE requirements from analyses |
| RAN | #92-e |  |  |  |

# References

[1]	RP-201261, “New SID on high-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, and Band n71”, U.S. Cellular.

[2]	R4-2011199, “Work Plan for Study on High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, and Band n71”, Nokia, Nokia Shanghai Bell.

[3]	R4-2016933, “Updated Work Plan for Study on High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, and Band n71”, Nokia, Nokia Shanghai Bell.