## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2: Progress – TTCN development (Sep-->Nov’21)
Completed:
  5GS Rel-15:
    EN-DC single carrier
  POS:
    B1C signal in A-BDS
Started:
  5GS Rel-16:
    NR mobility enhancements
    NR private networks
    NR UE power saving
    Network slicing enhancements
    5G to 3G SRVCC
  POS:
    Rel-16 NR positioning
  MCPTT:
    On-network location
Progressed:
  5GS Rel-15:
    NR/5GC single carrier
    NR/5GC NR-DC
  5GS Rel-16:
    RACS
    SON/MDT
  IMS over NR/5GC:
    Call Control
    Supplementary Services
  MCPTT:
    Client configuration
    On-network group call
    On-network private call
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 3: Progress – TTCN verification (Status on 4th Nov’21)
Progress – 4G (LTE, NB-IoT):
Feature | Rel- | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE/C2K Inter-RAT | Rel-8 | WI-088 | 13 / 14 | = | Left: TC 8.4.5.4(LTE to HRPD HO)
LTE/UMTS Inter-RAT | Rel-9 | WI-167 | 11 / 12 | = | Left: TC 13.1.21(emergency call)
LTE/GERAN Inter-RAT | Rel-9 | WI-168 | 3 / 4 | = | Left: TC 13.1.21(emergency call)
LTE/C2K Inter-RAT | Rel-10 | WI-180 | 1 / 2 | = | Left: TC 8.6.5.3(MDT RLF logging)
LTE/GERAN Inter-RAT | Rel-10 | WI-182/184 | 1 / 2 | = | Left: TC 8.6.5.2(MDT RLF logging)
CA intraband cont | Rel-11 | WI-162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | WI-245 | 6 / 9 | = | 
eDRX | Rel-13 | WI-253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | WI-254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | WI-254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | WI-257 | 71 / 73 | = | Left: TCs 22.1.1.M2, 22.4.26
LAA | Rel-13 | WI-272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | WI-295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 4: Progress – TTCN verification (Status on 4th Nov’21)
Progress – 5G (EN-DC, NR/5GC):
Feature | Rel- | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC AS (NSA Option3) | Rel-15 | WI-503 | 86 / 102 | +1 | Prio1: 86/102 +1 under verification
NR/5GC AS (SA Option2) | Rel-15 | WI-503 | 148/171 | +9 | Prio1: 92/107 ; Prio2: 56/64 +2 under verification
NR/5GC NAS (SA Option2) | Rel-15 | WI-504 | 67 / 72 | +5 | Prio1: 32/32 ; Prio2: 35/40 +1 under verification
NR/5GC NR CA (SA Option2) | Rel-15 | WI-510 | 21 / 31 | +1 | Prio1: 12/15 ; Prio2: 9/16
EN-DC NR CA (NSA Option3) | Rel-15 | WI-512 | 7 / 17 | +2 | Prio1: 7/13 ; Prio2: 0/4
NR/5GC Inter-RAT (SA Option2) | Rel-15 | WI-513 | 36 / 38 | +1 | Prio1: 16/16 ; Prio2: 20/22
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 5: Progress – TTCN verification (Status on 4th Nov’21)
Progress – IMS, Positioning, MCPTT:
Feature | Rel- | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
VoLTE (GSMA IR.92) | Rel-8 | WI-103 | 45 / 51 | = | 
SMS over IMS | Rel-8 | WI-128 | 2 / 5 | = | 
IMS Emergency Calls | Rel-9 | WI-154 | 31 / 35 | = | 
LTE Positioning | Rel-9+ | WI-166 | 14 / 27 | = | 
VoWiFi (GSMA IR.51) | Rel-11 | WI-267 | 20 / 34 | = | Prio1: 5/9 ; Prio2: 15/25
VoLTE over CAT-M1 (GSMA NG.108) | Rel-13 | WI-283 | 10 / 11 | = | Left: TC J.15.5(TIR)
SMS over CAT-M1 (GSMA NG.108) | Rel-13 | WI-128M | 1 / 2 | = | Left: TC J.18.1(MO SMS)
MCPTT over LTE | Rel-14 | WI-288, RFT-153 | 27 / 49 | +25 | Prio1: 27/46 ; Prio2: 0/3 +1 under verification
IMS eCall over LTE | Rel-14 | WI-298 | 2 / 12 | = | +3 under verification
IMS over NR/5GC (SA Option2) | Rel-15 | WI-505 | 45 / 101 | +8 | Prio1: 21/21 ; Prio2: 24/80 +4 under verification
5G Positioning (SA Option2) | Rel-15 | WI-506 | 9 / 10 | = | Left: TC 9.3.3.1B
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 6: Progress – TTCN verification (Status on 4th Nov’21)
Started:
Starting:
Feature | Rel- | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
Intra-NR SON / MDT | Rel-16 | WI-517_A | 2 / 30 | +2 | Prio1: 2/24 ; Prio2: 0/6 +1 under verification
Feature | Rel- | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
EPS fallback - voice fallback indication | Rel-16 | None | 0 / 2 |  | +2 under verification
5G network slicing enhancements | Rel-16 | None | 0 / 6 |  | +1 under verification
NR RACS | Rel-16 | None | 0 / 8 |  | +2 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 7: Summary & open issues from TTCN Workshop #55 (18th Oct’21)
Test Models – 5G:
  Endorsed TTCN test sequence updates for NR RRC connection re-establishment procedure.
  Endorsed clarification of SS requirements for the NR (& LTE) RLC Ack test modes.
  Endorsed NR ASP update to support recommended bit rate reporting.
  Discussed IP aspects of supporting a 2nd P-CSCF (needed by IMSo5G TC 6.2).
  Endorsed new Upper Tester commands needed for SNPN.
  Endorsed initial test model for 5G V2X.
  Prose CRs to TS 38.523-3 proposed at RAN5#93-e for the above.
Test Models – POS:
  Endorsed test model for Rel-16 NR positioning.
  Prose CR to TS 37.571-4 proposed at RAN5#93-e for the above.
Test Models – MCX:
  Endorsed MCX ASP type definition updates for Floor Control.
  Endorsed initial test model aspects for MCData.
  Prose CR to TS 36.579-5 proposed at RAN5#93-e for the above.

## Slide 8: Status of TTCN tasks in 2021 – 2020 tasks completion
2020 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2021 WkLoad | TTCN Status (as of Nov’21) / Comments
MCX: PTT, Video, Data | Rel-14 | L | Q3’20 | 106 | Q3’17-Q2’22 | 10 | 46% (@iwd-21wk37)
LTE CA band combinations | R14to16 | L | Q1’22 | n/a | Q1’19-Q1’22 | 0.1 | 23% (@iwd-21wk37)
MTC (even) further enhanced | R14to15 | L | Q4’21 | 18 | Q1’18-Q1’22 | 1 | 11% (@iwd-21wk37)
NB-IoT further enhanced | Rel-15 | L | Q3’21 | 8 | Q2’20-Q1’22 | 1 | 50% (@iwd-21wk37)
MDT: Bluetooth/WLAN meas. | Rel-15 | L,W,B | Q4’19 | 8 | Q1’19-Q4’21 | 1 | 50% (@iwd-21wk37)
Short TTI & processing time | Rel-15 | L | Q1’21 | 12 | Q4’19-Q4’21 | 1 | Not started
LTE mobility even further enh. | Rel-16 | L | Q4’21 | 11 | Q4’20-Q1’22 | 1 | Not started
5GS: NSA option 3 (EN-DC) | Rel-15 | N,L | Q4’21 | 125 | Q3’17-Q4’21 | 1 | 100% (@iwd-21wk37)
5GS: SA option 2 (NR/5GC) | Rel-15 | N,L | Q4’21 | 443 | Q3’18-Q1’22 | 6 | 91% (@iwd-21wk37)
5GS: Non-3GPP access | Rel-15 | W | Q1’20 | 21 | Q4’19-Q4’21 | 2 | Not started
NR new/extended bands | Rel-16 | N | Q4’21 | n/a | Q1’20-Q1’22 | 0.2 | 68% (@iwd-21wk37)
5G CA/DC band combinations | Rel-16 | N,L | Q4’21 | n/a | Q1’19-Q1’22 | 0.2 | 7% (@iwd-21wk37)
UE RACS optimisations | Rel-16 | N,L | Q1’22 | 14 | Q4’20-Q1’22 | 1.5 | 43% (@iwd-21wk37)
NR UE power saving | Rel-16 | N | Q1’22 | 9 | Q4’20-Q1’22 | 1.5 | 11% (@iwd-21wk37)
NR industrial IoT | Rel-16 | N,L | Q4’21 | 6 | Q4’20-Q1’22 | 1.5 | Not started
5G V2X with NR sidelink | Rel-16 | N,L | Q2’22 | 74 | Q4’20-Q3’22 | 6 | 5% ; Test Model work
Private network support | Rel-16 | N | Q1’22 | 14 | Q4’20-Q1’22 | 2 | 28% (@iwd-21wk37)
NR mobility enhancements | Rel-16 | N | Q4’21 | 14 | Q4’20-Q1’22 | 1.5 | 57% (@iwd-21wk37)
NR MIMO enhancements | Rel-16 | N | Q2’22 | 1 | Q4’20-Q2’22 | 0.5 | Not started
Total: |  |  |  | 884 |  | 39 | man.months
Notes: Note: TTCN of some features initially started in 2020 will only be completed in 2021 due to availability of prose late in CY2020, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 9: Status of TTCN tasks in 2021 – 2021 tasks & maintenance
2021 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2021 WkLoad | TTCN Status (as of Nov’21) / Comments
MCX enhancements | Rel-15 | L | Q2’22 | 67 | Q3’21-Q4’22 | 2 | 18% (@iwd-21wk37)
LTE new/updated bands | Rel-16+ | L | Q4’21 | n/a | Q1’21-Q4’21 | 0.3 | 85% (@iwd-21wk37)
B1C signal in BDS | Rel-16 | N,L | Q4’21 | n/a | Q1’21-Q4’21 | 0.2 | 100% (@iwd-21wk37)
5G to 3G SRVCC | Rel-16 | N,U | Q4’21 | 4 | Q1’21-Q4’21 | 2 | 85% (@iwd-21wk37)
NR SON & MDT support | Rel-16 | NLWB | Q4’21 | 47 | Q1’21-Q1’22 | 3 | 70% (@iwd-21wk37)
NR URLLC phy layer enh. | Rel-16 | N | Q2’22 | 5 | Q2’21-Q2’22 | 1 | Not started
IMS eCall over NR | Rel-16 | N | Q1’22 | 17 | Q3’21-Q2’22 | 0.5 | Not started
NR positioning support | Rel-16 | N | Q1’22 | 14 | Q2’21-Q1’22 | 1 | 30% (@iwd-21wk37)
NW slicing enhancements | Rel-16 | N | Q4’21 | 6 | Q3’21-Q1’22 | 1 | 33% (@iwd-21wk37)
NR new/extended bands | Rel-17 | N | Q4’21 | n/a | Q1’21-Q1’22 | 0.5 | 24% (@iwd-21wk37)
5G CA/DC band combinations | Rel-17 | N,L | Q4’21 | n/a | Q1’21-Q1’22 | 0.5 | 7% (@iwd-21wk37)
TEIx_Test (new TC coverage) | Rel-8+ | All | n/a | 10 | Q1’21-Q4’21 | 1 | 2021 total after RAN5#93-e: 2 TCs
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | 170 |  | 64 | man.months
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 10: Status of TTCN funding in 2021
2021 workload is estimated at 103 man.months (mm), see previous slides.
PCG#45/OP#44 approved the 3GPP funding of 58 mm for 2021 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2021.
Current commitments for 2021 are as follows:
3GPP companies / 3GPP MRPs committed to provide 19 mm as voluntary contributions for 2021 TTCN development.
Total resources of 103 mm  no estimated funding gap.
Funding |  | 
Entity | Man.months | Comments
3GPP | 58 | PCG#45/OP#44 approved (decision OP44/06)
CTIA/PTCRB | 12 | 5GS, MCX
GCF | 12 | 5GS, MCPTT, MCX
Qualcomm | 2 | NR-DC, RACS, NPN,UE power saving, IMSoNR eCall
Total: | 84 | 
TTCN experts free-of-charge |  | 
Entity | Man.months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 5GS, NB-IoT, LCR TDD
Adare | 2 | TTCN deliveries, LTE-A-Pro, 5GS
Anritsu | 1 | 5GS
Keysight | 1 | 5GS
Rohde&Schwarz | 1 | 5GS
Total: | 19 | 

## Slide 11: Preparing for 2022 TTCN Work
Course of action to secure funding for TF160 work in 2022:
  Prior to RAN5#92-e meeting (August), a request to identify the potential TTCN development tasks in 2022 has been made to 3GPP members.
  At RAN5#92-e, a provisional ‘TTCN Tasks List’ has been endorsed by RAN5.
  The TTCN Tasks List has been presented at RAN#93-e (Sept) and endorsed by TSG RAN.
  The RAN Chair has presented the List to 3GPP PCG/OP (Oct) in order to support TF160 request for the TTCN funding in 2022. 3GPP PCG/OP has approved the 2022 TTCN funding request from TSG RAN of 58 man.months.
  The finalized TTCN Tasks List will be reviewed and endorsed at RAN5#93-e (Nov) for TSG RAN approval at RAN#94-e (Dec).
Based on inputs to RAN5#93-e, the updated list of TTCN tasks is presented in the next slides.

## Slide 12: Preparing for 2022 TTCN Work – Tasks List 2021 tasks completion
2021 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | 3GPP related Work Item
MCX: PTT, Video, Data | Rel-14 | L | Q3’20 | 106 | Q3’17-Q2’22 | 4 | MCPTT-ConTest, MCImp-UEConTest
LTE CA band combinations | R15to16 | L | Q1’22 | n/a | Q1’19-Q1’22 | 0.1 | LTE_CA_R1x-UEConTest
MTC (even) further enhanced | R14to15 | L | Q4’21 | 18 | Q1’18-Q1’22 | 1 | LTE_(f)eMTC(4)-UEConTest
NB-IoT further enhanced | Rel-15 | L | Q3’21 | 8 | Q2’20-Q1’22 | 0.5 | NB_IOTenh2-UEConTest
MCX enhancements | Rel-15 | L | Q2’22 | 67 | Q3’21-Q4’22 | 6 | MCenh-UEConTest
LTE mobility even further enh. | Rel-16 | L | Q4’21 | 11 | Q4’20-Q1’22 | 1 | LTE_feMob-UEConTest
5GS: SA option 2 (NR/5GC) | Rel-15 | N,L | Q4’21 | 443 | Q3’18-Q1’22 | 1 | 5GS_NR_LTE-UEConTest
UE RACS optimisations | Rel-16 | N,L | Q1’22 | 14 | Q4’20-Q1’22 | 1 | RACS-UEConTest
NR UE power saving | Rel-16 | N | Q1’22 | 9 | Q4’20-Q1’22 | 0.5 | NR_UE_pow_sav-UEConTest
NR industrial IoT | Rel-16 | N,L | Q4’21 | 6 | Q4’20-Q1’22 | 0.5 | NR_IIoT-UEConTest
5G V2X with NR sidelink | Rel-16 | N,L | Q2’22 | 74 | Q4’20-Q3’22 | 6 | 5G_V2X_NRSL_eV2XARC-UEConTest
Private network support | Rel-16 | N | Q1’22 | 14 | Q4’20-Q1’22 | 0.5 | NG_RAN_PRN_Vertical_LAN-UEConTest
NR mobility enhancements | Rel-16 | N | Q4’21 | 14 | Q4’20-Q1’22 | 1 | NR_Mob_enh-UEConTest
NR MIMO enhancements | Rel-16 | N | Q2’22 | 1 | Q4’20-Q2’22 | 0.5 | NR_eMIMO-UEConTest
NR SON & MDT support | Rel-16 | NLWB | Q4’21 | 47 | Q1’21-Q1’22 | 1 | NR_SON_MDT-UEConTest
NR URLLC phy layer enh. | Rel-16 | N | Q2’22 | 5 | Q2’21-Q2’22 | 1 | NR_L1enh_URLLC-UEConTest
IMS eCall over NR | Rel-16 | N | Q1’22 | 17 | Q3’21-Q2’22 | 2 | NR_EIEI-UEConTest
NR positioning support | Rel-16 | N | Q1’22 | 14 | Q2’21-Q1’22 | 0.5 | NR_pos-UEConTest
NW slicing enhancements | Rel-16 | N | Q4’21 | 6 | Q3’21-Q1’22 | 0.5 | eNS-UEConTest
NR new/extended bands | R16to17 | N | Q4’21 | n/a | Q1’21-Q1’22 | 0.2 | NR_lic_bands_BW_R1x-UEConTest
5G CA/DC band combinations | R16to17 | N,L | Q4’21 | n/a | Q1’21-Q1’22 | 0.2 | NR_CADC_NR_LTE_DC_R1x-UEConTest
Total: |  |  |  | 859 |  | 29 | man.months
Notes: Note: TTCN of some features initially started in 2021 will only be completed in 2022 due to availability of prose late in CY2021, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 13: Preparing for 2022 TTCN Work – Tasks List New 2022 tasks and maintenance
2022 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | 3GPP related Work Item
5GS: NSA option 4 (NE-DC) | Rel-15 | N,L | Q1’22 | 35 | Q1’22-Q4’22 | 6 | 5GS_NR_LTE-UEConTest
NR FR1 RF requirements | Rel-16 | N | Q4’21 | 6 | Q1’22-Q2’22 | 1 | NR_RF_FR1-UEConTest
NR 2-step RACH | Rel-16 | N | Q1’22 | 4 | Q1’22-Q2’22 | 1 | NR_2step_RACH-UEConTest
EN-DC, NR-DC, NR CA enh. | Rel-16 | N,L | Q1’22 | 25 | Q1’22-Q4’22 | 3 | LTE_NR_DC_CA_enh-UEConTest
NR in unlicensed spectrum | Rel-16 | N | Q4’22 | 13 | Q1’22-Q4’22 | 3 | NR_unlic-UEConTest
LTE/NR multi-SIM UEs | Rel-17 | N,L | 2023 | FFS | Q4’22-Q4’23 | 0.5 | LTE_NR_MUSIM
NR & EN-DC SON/MDT enh. | Rel-17 | N,L | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_ENDC_SON_MDT_enh
NR UE power saving enh. | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_UE_pow_sav_enh
NR RAN slicing enh. | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_slice
NR positioning enh. | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_pos_enh
NR sidelink enh. | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_SL_enh
NR sidelink relay | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_SL_relay
Reduced capability NR UEs | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_redcap
NR multi/broadcast services | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_MBS
NR operation up to 71GHz | Rel-17 | N | 2023 | FFS | Q4’22-Q4’23 | 0.5 | NR_ext_to_71GHz
TEIx_Test (new TC coverage) | Rel-8+ | All | n/a | 20 | Q1’22-Q4’22 | 2 | TEIx_Test
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | >103 |  | 72 | man.months
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 14: Preparing for 2022 TTCN Work – Funding
2022 workload is estimated at 101 man.months (mm), see previous slides.
PCG#47/OP#46 approved the 3GPP funding of 58 mm for 2022 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2022.
Current commitments for 2022 are as follows:
3GPP companies / 3GPP MRPs committed to provide 17 mm as voluntary contributions for 2022 TTCN development.
Total resources of 101 mm  no estimated funding gap.
Funding |  | 
Entity | Man.months | Comments
3GPP | 58 | PCG#47/OP#46 approved (decision OP46/08)
CTIA/PTCRB | 12 | 5GS, MCX
GCF | 12 | 5GS, MCX
Qualcomm | 2 | RACS, NPN, IMSoNR eCall
Total: | 84 | 
TTCN experts free-of-charge |  | 
Entity | Man.months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 5GS, V2X, NB-IoT, LCR TDD
Anritsu | 1 | 5GS
Keysight | 1 | 5GS
Rohde&Schwarz | 1 | 5GS
Total: | 17 | 

## Slide 15: Annexes

## Slide 16: TTCN baseline and deliveries – 2021 schedule
Four TTCN-3 full deliveries / year.
Type definitions baseline upgrade planned in 2021:
  Rel-16 Phase2: partial upgrade to Rel-16 Mar'21 baseline for NR ASN.1 + 5GC NAS due to several non-backwards compatible (NBC) changes.
  Rel-16 Phase3: partial upgrade to Rel-16 Sep'21 baseline for NR ASN.1 due to new NR ASN.1 IEs required by Rel-16 NR/5GC test cases.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk03 |  |  | 22-Jan |  | GCF CAG#65 (26-29 Jan)
wk12 | 26-Mar | 22-Mar | 26-Mar | TTCN-3 | 
wk15 |  |  | 16-Apr |  | GCF CAG#66 (20-23 Apr)
wk24 | 18-Jun | 14-Jun | 18-Jun | TTCN-3 Rel-16 phase2 baseline upgrade | Partial upgrade to Rel-16 Mar'21 baseline for NR+5GC
wk28 |  |  | 16-Jul |  | GCF CAG#67 (20-23 Jul)
wk37 | 17-Sep | 13-Sep | 17-Sep | TTCN-3 | 
wk40 |  |  | 08-Oct |  | GCF CAG#68 (12-15 Oct)
wk49 | 10-Dec | 06-Dec | 10-Dec | New! TTCN-3 Rel-16 phase3 baseline upgrade | Partial upgrade to Rel-16 Sep'21 baseline for NR

## Slide 17: TTCN baseline and deliveries – 2022 schedule
One TTCN-2 full deliveries (FDD & LCR TDD) and five TTCN-3 full deliveries / year.
  Q3/Q4 dates tentative: dependent on RAN5 meetings being physical or electronic (TBC).
Type definitions baseline upgrade to 3GPP Release 17 required in 2022:
  Rel-17 Stage3 freeze scheduled by 3GPP in March 2022.
  Rel-17 ASN.1 freeze scheduled by 3GPP in June 2022.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk04 |  |  | 21-Jan |  | GCF CAG#69 (25-28 Jan)
wk12 | 25-Mar | 21-Mar | 25-Mar | TTCN-3 | 
wk18 |  |  | 29-Apr |  | GCF CAG#70 (3-6 May)
wk24 | 17-Jun | 13-Jun | 17-Jun | TTCN-3 | 
wk30 |  |  | 22-Jul |  | GCF CAG#71 (26-27 Jul)
wk37 | 16-Sep | 12-Sep | 16-Sep | TTCN-3 | 
wk42 |  |  | 14-Oct |  | GCF CAG#72 (18-19 Oct)
wk43 | 28-Oct | 19-Oct | 28-Oct | TTCN3 Rel-17 Baseline upgrade | Move to Rel-17 Sep'22 baseline
wk48 | 01-Dec | 28-Nov |  | TTCN2 (FDD) | 
wk48 | 02-Dec | 28-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 09-Dec | 05-Dec | 09-Dec | TTCN-3 | 

## Slide 18: 5GS Rel-15 – Protocol test case numbers Before RAN5#93-e
5GS Rel-15 | TCs # | Details
NR/5GC (5G option 2) | Total: 443 | IdleMode: 60, NR L2: 82, NR RRC: 105, 5GC: 57, Multilayer: 28, IMS: 101, POS: 10.
EN-DC (5G option 3) | Total: 125 | NR L2: 71, RRC: 51, EPC: 3, IMS, POS: none.
NE-DC (5G option 4) | Total: 35 | NR L2: 2, NR RRC: 33
TOTAL: | 603 | 
Notes: Legend:
Blue: changes from last MCC TF160 report.

## Slide 19: Minutes of TTCN Sidebar
Friday 12th November @10AM CEST.
Agenda and minutes:
  See RAN5#93-e_TTCN_Sidebar-v2.zip