## Cover sheet
RAN5 meeting #96e | [10 empty] | R5-224280
Electronic Meeting, 15th – 26th Aug 2022
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP UE Conformance – Rel-17 Enhancement of Private Network Support for NG-RAN including CT aspects
Work item code: | NG_RAN_PRN_enh_plus_CT-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 10 (+10)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 10 (+10)
FR1 |  | 5% (+5%) | 0 | 10 (+10)
FR2 |  | 5% (+5%) | 0 | 10 (+10)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 10 (+10) | 0% | 0 | 10 (+10) | 0% | 0 | 10 (+10)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-221300 | New WID on UE Conformance – Enhancement of Private Network Support for NG-RAN including CT aspects, China Telecom, RAN#96, June 2022
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Enhancement of Private Network Support for NG-RAN including CT aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NG_RAN_PRN_enh_plus_CT-UEConTest
WP Scope: |  | <WP Scope description> | [12 empty] | vs Area
WP Resp: |  | Lei GAO |  |  | gaol8@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 5% (+5%) | 5% (+5%)
[14 empty] | 18 (+18) | 18 (+18)
[14 empty] | 26.4 (+26.4) | 26.4 (+26.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4 | Introduction of General and Signaling Test Environment for Rel-17 eNPN Tests | GIN definition, ASN.1 updates (SIB1, SIB18, other messages) | TBD | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.3.7 | Introduction of common implementation conformance statements for Rel-17 eNPN Tests | GIN PICS | TBD | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Idle Mode
|  | 38.523-1 | 6.5.1 | SNPN Only Selection | Existing sub-clause header |  | TBD |  |  | 0
3 | Y | 38.523-1 | 6.5.1.4 | SNPN Selection in Manual Mode / switch to Automatic Mode | TS 23.122, cl 4.9.3.1.2 (1) with { UE in Manual network/SNPN selection mode and user initiates an emergency call } ensure that { when { UE determines that the selected SNPN does not support emergency calls or registration request for emergency services is rejected by the network } then { UE exits manual selection mode and automatically registers on a different SNPN } } | TBD | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
4 | Y | 38.523-1 | 6.5.1.5 | SNPN Selection in Automatic Mode / SNPN selection using credentials from a credentials holder | TS 23.122, cl 4.9.3.1.1 (1) with { UE in Automatic network selection mode and supports access to an SNPN using credentials from a credentials holder, using the SNPN selection parameters in the selected entry of the "list of subscriber data" or associated with the selected PLMN subscription } ensure that { when { SNPNs are available which broadcast the indication that access using credentials from a credentials holder is supported or allow registration attempts from MSs that are not explicitly configured to select the SNPN} then { UE selects a cell of the highest priority SNPN and UE attempts a registration on the selected cell } } | TBD | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
5 | Y | 38.523-1 | 6.5.1.6 | SNPN Selection in Manual Mode / SNPN selection using credentials from a credentials holder | TS 23.122, cl 4.9.3.1.2 (1) with { UE in Manual network/SNPN selection mode and supports access to an SNPN using credentials from a credentials holder } ensure that { when { SNPN cells are available which broadcast the indication that access using credentials from a credentials holder is supported: } then { UE indicates to the user available SNPNs along with a human-readable network name } } | TBD | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
6 | Y | 38.523-1 | 6.5.1.7 | SNPN Selection in Automatic Mode / SNPN selection for onboarding services in SNPN | TS 23.122, cl 4.9.3.1.3 (1) with { UE in Automatic network selection mode and supports onboarding services in SNPN } ensure that { when { UE needs to access an SNPN for onboarding services and an SNPN indicating that onboarding is allowed is available } then { UE selects an SNPN and attempts initial registration for onboarding services in SNPN on the selected SNPN } } (2) with { UE in Automatic network selection mode and supports onboarding services in SNPN } ensure that { when { UE needs to access an SNPN for onboarding services and no SNPN indicating that onboarding is allowed is available } then { UE indicates no onboarding services to upper layers and performs SNPN selection not for onboarding services in SNPN } } | TBD | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
7 | Y | 38.523-1 | 6.5.1.8 | SNPN Selection in Manual Mode / SNPN selection for onboarding services in SNPN | TS 23.122, cl 4.9.3.1.4 (1) with { UE in Manual network selection mode and supports onboarding services in SNPN } ensure that { when { SNPNs indicating that onboarding is allowed are available and the SNPNs are allowable SNPNs, in the list of "permanently forbidden SNPNs" and in the list of "temporarily forbidden SNPNs" } then { UE indicates to upper layers SNPNs for onboarding services } } | TBD | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
8 | Y | 38.523-1 | 6.5.1.9 | SNPN / User Reselection in Automatic Mode / Support using credentials from a credentials holder | TS 23.122, cl 4.9.3.2.1 (1) with { UE in Automatic SNPN selection mode and registered on an SNPN cell and supports access to an SNPN using credentials from a credentials holder, using the SNPN selection parameters in the selected entry of the "list of subscriber data" or associated with the selected PLMN subscription } ensure that { when { another SNPN is available which broadcast the indication that access using credentials from a credentials holder is supported or allow registration attempts from MSs that are not explicitly configured to select the SNPN and UE is requested to initiate reselection and registration onto an available SNPN } then { UE reselects the SNPN cell } } | TBD | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
9 | Y | 38.523-1 | 6.5.1.10 | SNPN / cell reselection for IMS emergency services | TS 38.304, cl 5.2.8 (1) with { UE in SNPN access mode is in NR RRC_IDLE state and supports voice services } ensure that { when { UE receives SIB1 message indicating that the current cell does not support IMS voice calls for any SNPN(s) } then { UE perform cell selection/reselection to an acceptable cell of any available SNPN supporting emergency calls } } | TBD | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
13 |  | 38.523-1 | 6.5.3 | Network selection between PLMN and SNPN | New sub-clause header |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
10 | Y | 38.523-1 | 6.5.3.1 | Network selection for UE in SNPN limited service state | TS 23.122, cl 3.5 (1) with { UE in SNPN access mode is in limited service state and supports accessing a PLMN } ensure that { when { UE needs to make an emergency call and there is no available SNPN supporting emergency services } then { UE stops operating in SNPN access mode and attempts to camp on a cell of a PLMN } } (2) with { UE orignally enabled SNPN access mode has camped on a cell of a PLMN and started an emergency call } ensure that { when { UE determines the emergency call is released } then { UE re-satrts operating in SNPN access mode and performs SNPN selection } } (3) with { UE in SNPN access mode and no SIM in the UE or the "list of subscriber data" with no valid entry} ensure that { when { an SNPN cell is available and UE needs to make a emergency call or select a cell for onboarding services in SNPN } then { UE selects the SNPN cell and attempts to camp on it } } | TBD | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
11 | Y | 38.523-1 | 6.5.3.2 | Network selection for UE in PLMN limited service state | TS 23.122, cl 3.5 (1) with { UE not in SNPN access mode and in limited service state } ensure that { when { UE needs to make an emergency call, there is no available PLMN supporting emergency services and UE determines that there is an available SNPN supporting emergency services } then { UE starts operating in SNPN access mode and attempts to camp on a cell of the SNPN supporting emergency services. } } (2) with { UE orignally disabled SNPN access mode has camped on a cell of a SNPN and started an emergency call } ensure that { when { UE determines the emergency call is released } then { UE stops operating in SNPN access mode and performs PLMN selection } } | TBD | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  | TBD |  |  | 3 | 0% | 0% |  | 0% | 0%
RRC
|  | 38.523-1 | 8.1.7 | Non-public networks | Existing sub-clause header |  | RAN5#97 (Nov-22) |  |  | 0
14 |  | 38.523-1 | 8.1.7.2 | Enhancements to Support SNPN | New sub-clause header |  | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
12 | Y | 38.523-1 | 8.1.7.2.1 | Support SNPN UE Onboarding and remote provisioning | TS 38.331, cl 5.3.3.4 (1) with { UE is in SNPN access mode and receives system information } ensure that { when { UE receives SIB1 message including an IE snpn-AccessInfoList-r17 } then { UE includes the onboardingRequest in RRCSetupComplete message upon reception of the RRCSetup message } } | China Telecom | RAN5#97 (Nov-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
NAS
TBD |  | 38.523-1 | <Clause> | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | TBD |  |  |  | 5 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
|  | 38.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | TBD |  |  |  | 5 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | TBD |  |  |  | 3 | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.