## Cover sheet
3GPP TSG-RAN WG5 Meeting #96-e | [8 empty] | R5-224996
Electronic meeting, 15th Aug - 26th Aug, 2022
Agenda Item: | 7.4.2
Source: | Puloli
Title: | WP - UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103)
Work item code: | LTE_upper_700MHz_A-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
At the RAN#96 meeting in June 2022 a RAN5 work item for conformance test aspects of Introduction of upper 700MHz A block E-UTRA band for the US (band 103) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item for intruducing Band 103 (LTE_upper_700MHz_A-UEConTest). The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 72% (+72%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (FDD) |  | 71.5% (+71.5%)
FDD |  | 71.5% (+71.5%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 100% (+100%) |  |  | 100% (+100%)
LTE RF/RRM
RF common parts | 36.521-1 | 100% (+100%) |  |  | 100% (+100%)
RF Tx test cases | 36.521-1 Tx | 100% (+100%) |  |  | 100% (+100%)
Applicability RF, Demod/QSI and RRM test cases | 36.521-2 | 100% (+100%) |  |  | 100% (+100%)
RRM test cases | 36.521-3 | 100% (+100%) |  |  | 100% (+100%)
LTE RAN and CN protocols
Applicability Protocol test cases | 36.523-2 | 0% |  |  | 0%
Test suites (TTCN) | 36.523-3 | 0% |  |  | 0%
5 References
[1] RP-221417 | New WID on: UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103) New WID on: UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_upper_700MHz_A-UEConTest
WP Scope: |  | The objective of this work item is to introduce the UE conformance requirements corresponding to ‘WI LTE_upper_700MHz_A’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications.
WP Resp: |  | Heng Pan |  |  | heng.pan@puloli.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | NA |  |  | NA
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD
71.5% (+71.5%)
8 (+8)
1 (+1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 8 | Introduction of test frequencies for LTE Band 103 | Added band 103 to NB-IoT standalone operations | Puloli | RAN5#96 (Aug-22) | R5-224141 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
2 |  | 36.521-1 | 5 | Introduction of test frequencies for LTE Band 103 for NB-IoT operations in clause 5 | Added LTE band 103 details for frequency range, Rx-Tx separation, channel bandwidths and carrier frequency EARFCN parameters Added band 103 to the list of supported bands for UE category NB1 and NB2 | Puloli | RAN5#96 (Aug-22) | R5-224142 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-1: RF test cases - Tx
3 |  | 36.521-1 Tx | 6.2 | Introduction of Band 103 for UE category NB1 and NB2 in transmit power test cases in clause 6.2 | Added minimum requirements and test requirements for the following tramitter test cases: 6.2.2F and 6.2.2FA | Puloli | RAN5#96 (Aug-22) | R5-224143 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
4 |  | 36.521-1 Tx | 6.6 | Introduction of LTE Band 103 in spurious emission test cases in clause 6.6 | Added LTE band 103 to minimum requirements for spurious emission and UE co-existence in clasue 6.6.3.2, 6.6.3.2A0, 6.6.3EA.2, 6.6.3EC.2, 6.6.3F and 6.6.3G.2_1.5. | Puloli | RAN5#96 (Aug-22) | R5-224430 |  | 0.2 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-2: Applicability for RF, Demod/QSI reporting and RRM test cases
5 |  | 36.521-2 | A4.3 | Introduction of Baseline Implementation Capability for LTE Band 103 | Add new ICS statements. | Puloli | RAN5#96 (Aug-22) | R5-224826 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-3: RRM test cases
6 |  | 36.521-3 | 3.5.1 | Introduction of LTE Band 103 in Group of band definitions | Added band 103 to Table 3.5.1-1 for E-UTRA band groups and to Table 3.5.1-2 for band groups for NB-IoT. | Puloli | RAN5#96 (Aug-22) | R5-224828 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
LTE RAN and CN protocols
TS 36.523-2: Applicability for Protocol test cases
7 |  | 36.523-2 | A.4.3.1 | Baseline Implementation Capabilities for Band 103 | Add new ICS statements. | Puloli | RAN5#97 (Nov-22) |  |  | 0.1 | 0% | 0% |  | 0%
TS 36.523-3: Protocol test suites (TTCN)
8 |  | 36.523-3 | 11 | Guidelines on test execution for Band 103 | Update of the test case execution guidelines for LTE Band 103 |  | RAN5#97 (Nov-22) |  |  | 0.2 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.