## Cover sheet
3GPP TSG-RAN5 Meeting #98 | [8 empty] | R5-230390
Athens, Greece, Feb 27th - Mar 3rd, 2023
Agenda Item: | 7.4.2
Source: | CMCC
Title: | WP UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 (FR1)
Work item code: | NR_HST_FR1_enh-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
At RAN#96e meeting in June 2022, a Release 17 work item for UE Conformance Test Aspects for Enhanced NR support for high speed train scenario for frequency range 1 (FR1) (NR_HST_FR1_enh-UEConTest) was approved [1]. The objective of this work item is to define the UE conformance requirements corresponding to WID on Enhanced NR HST (FR1) with Unique identifier 960077. This work item will cover Demod and RRM conformance test specifications with Enhanced NR HST (FR1). The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 71% (+8%) | 4 (+4) | 9.5 (+7)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 72.7% (+9.1%) | 4 (+4) | 7.5 (+7)
FR1 |  | 72.7% (+9.1%) | 4 (+1) | 7.5
NSA Option 3 (EN-DC) |  | 68.6% (+7.6%) | 4 (+4) | 6.5 (+4)
FR1 |  | 68.6% (+7.6%) | 4 (+1) | 6.5
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100%
NR RF/RRM
RF Demod/QSI test cases | 38.521-4 | 81.8% (+1.8%) | 4 (+4) | 4.5 (+4) | 81.8% (+1.8%) | 4 (+1) | 4.5 |  |  | 81.8% (+1.8%) | 4 (+1) | 4.5
RRM test cases | 38.533 | 85% (+35%) | 0 | 5 (+3) | 85% (+35%) | 0 | 3 |  |  | 85% (+35%) | 0 | 2
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% |  |  | 100% |  |  |  |  | 100%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0% |  |  |  |  | 0%
5 References
[1] RP-221359 | New WID on UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 (FR1)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for NR support for high speed train scenario | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_HST_FR1_enh-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Enhanced NR support for high speed train scenario for frequency range 1 (FR1) comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 72.7% (+9.1%) | 68.6% (+7.6%)
[15 empty] | 19 | 16
[15 empty] | 12 | 10
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.6.3 | General and RRM Test Environment | Introduction of General and RRM Test Environment for Rel-17 enhanced NR HST | CMCC | RAN5#97 (Nov-22) | R5-227703, R5-227704, R5-227705 | CMCC Dan Song <songdan@chinamobile.com> R17 HST enh IE has been added into HighSpeedConfig, ServingCellConfigCommon and ServingCellConfigCommonSIB parts in clause 4.6.3 Radio resource control information elements. | 0.5 | 100% | 100% |  |  | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | A.4.3.11 | High Speed Capabilities | Introduction of common implementation conformance statements for Rel-17 enhanced NR HST | CMCC | RAN5#97 (Nov-22) | R5-227710 | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 100% | 100% |  |  | 100%
NR RF/RRM
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
3 | Y | 38.521-4 | 5.1.1.5.4 | Applicability of different requirements for HST | To add the applicability of CA requirements for HST. (R4-2207196, R4-2211328) | CMCC | RAN5#98 (Feb-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% | 0% |  | 0% | 0%
| Y | 38.521-4 | 5.2A.2.4 | Requirements for 2RX HST-SFN CA PDSCH | Header |  |  |  |  | 0
4 | Y | 38.521-4 | 5.2A.2.4.0 | Minimum conformance requirements for 2RX HST-SFN CA PDSCH | To specify the Minimum conformance requirements for 2RX HST-SFN CA PDSCH (R4-2207196, R4-2215203) | Ericsson | RAN5#97 (Nov-22) | R5-225024, R5-227953 | Niclas Weiler<niclas.weiler@ericsson.com> Further updates to the minimum conformance requirements are needed according to R4-2215203. | 0.5 | 100% | 100% | 100% |  | 100% | 100%
5 | Y | 38.521-4 | 5.2A.2.4.1 | 2RX PDSCH Demodulation Performance for HST-SFN CA | To verify the PDSCH Demodulation Performance for 2RX HST-SFN CA (R4-2207196) | Ericsson | RAN5#97 (Nov-22) | R5-225024, R5-227953 | Niclas Weiler<niclas.weiler@ericsson.com> | 0.5 | 100% | 100% | 100% |  | 100% | 100%
| Y | 38.521-4 | 5.2A.2.5 | Requirements for 2RX HST-DPS CA PDSCH | Header |  |  |  |  | 0
6 | Y | 38.521-4 | 5.2A.2.5.0 | Minimum conformance requirements for 2RX HST-DPS CA PDSCH | To specify the Minimum conformance requirements for 2RX HST-DPS CA PDSCH (R4-2207196, R4-2211328, R4-2215203) | Ericsson | RAN5#97 (Nov-22) | R5-225769, R5-227956 | Petter Karlsson<petter.karlsson@ericsson.com> Further updates to the minimum conformance requirements are needed according to R4-2215203. | 0.5 | 100% | 100% | 100% |  | 100% | 100%
7 | Y | 38.521-4 | 5.2A.2.5.1 | 2RX PDSCH Demodulation Performance for HST-DPS CA | To verify the PDSCH Demodulation Performance for 2RX HST-DPS CA (R4-2207196, R4-2211328) | Ericsson | RAN5#97 (Nov-22) | R5-225769, R5-227956 | Petter Karlsson<petter.karlsson@ericsson.com> | 0.5 | 100% | 100% | 100% |  | 100% | 100%
| Y | 38.521-4 | 5.2A.3.4 | Requirements for 4RX HST-SFN CA PDSCH | Header |  |  |  |  | 0
8 | Y | 38.521-4 | 5.2A.3.4.0 | Minimum conformance requirements for 4RX HST-SFN CA PDSCH | To specify the Minimum conformance requirements for 4RX HST-SFN CA PDSCH (R4-2207196, R4-2211328, R4-2210905, R4-2215203) | CMCC | RAN5#97 (Nov-22) | R5-227954, R5-226356 | CMCC Luyang Zhao<zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% | 100% |  | 100% | 100%
9 | Y | 38.521-4 | 5.2A.3.4.1 | 4RX PDSCH Demodulation Performance for HST-SFN CA | To verify the PDSCH Demodulation Performance for 4RX HST-SFN CA (R4-2207196, R4-2211328, R4-2210905) | CMCC | RAN5#98 (Feb-23) | R5-227954, R5-226356, R5-231841 | CMCC Luyang Zhao<zhaoluyang@chinamobile.com> Further update to Message contents | 0.5 | 100% (+10%) | 100% (+10%) | 100% (+10%) |  | 100% | 100%
| Y | 38.521-4 | 5.2A.3.5 | Requirements for 4RX HST-DPS CA PDSCH | Header |  |  |  |  | 0
10 | Y | 38.521-4 | 5.2A.3.5.0 | Minimum conformance requirements for 4RX HST-DPS CA PDSCH | To specify the Minimum conformance requirements for 4RX HST-DPS CA PDSCH (R4-2207196, R4-2211328, R4-2215203) | CMCC | RAN5#97 (Nov-22) | R5-227955, R5-226356 | CMCC Luyang Zhao<zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% | 100% |  | 100% | 100%
11 | Y | 38.521-4 | 5.2A.3.5.1 | 4RX PDSCH Demodulation Performance for HST-DPS CA | To verify the PDSCH Demodulation Performance for 4RX HST-DPS CA (R4-2207196, R4-2211328) | CMCC | RAN5#98 (Feb-23) | R5-227955, R5-226356, R5-231842 | CMCC Luyang Zhao<zhaoluyang@chinamobile.com> Further update to Message contents | 0.5 | 100% (+10%) | 100% (+10%) | 100% (+10%) |  | 100% | 100%
12 |  | 38.521-4 | A.3.2.1.1 | Reference measurement channels for SCS 15 kHz FR1 | To introducte "Table A.3.2.1.1-13: PDSCH Reference Channel for FDD HST-SFN with CA scenario" (R4-2207196) | CMCC | RAN5#98 (Feb-23) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 0% | 0% | 0% |  | 0% | 0%
13 |  | 38.521-4 | G.1.5 | Minimum Test time | To update "Table G.1.5-1: Minimum Test time for PDSCH demodulation", "Table G.1.5-1a: Minimum Test time for PDSCH demodulation with 1% BLER" and "Table G.1.5-2: Minimum Test time for PDCCH demodulation" for different HST doppler speed | Ericsson | RAN5#97 (Nov-22) | R5-225770 | Petter Karlsson<petter.karlsson@ericsson.com> 4Rx to be added. | 0.5 | 100% | 100% | 100% |  | 100% | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | TBD
19 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4 and 38.533. | CMCC, Ericsson | RAN5#97 (Nov-22) | R5-228030 | Test case applicability statements for 38.521-4 and 38.533 have been captured in Column "TDOC(s)" for 38.521-4 and 38.533 test cases. | 0.5 | 100% | 100% | 100% |  | 100% | 100%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
14 | Y | 38.533 | 4.6.1.8 | EN-DC FR1 event triggered reporting cell without SSB time index detection in DRX for UE configured with highSpeedMeasCA-Scell-r17 | To verify that the UE makes correct reporting of an event for UE configured with highSpeedMeasCA-Scell-r17 (R4-2215217) | Ericsson | RAN5#99 (May-23) | R5-227861, R5-227862, R5-231150 | Jakub Kolodziej<jakub.kolodziej@ericsson.com> Pending on RAN4 to complete the RRM test cases Further update to TT analysis | 1 | 85% (+35%) |  | 85% (+35%) |  |  | 85%
15 | Y | 38.533 | 4.6.2.9 | EN-DC FR1 event triggered reporting without SSB time index detection in DRX for UE configured with highSpeedMeasInterFreq-r17 | To verify that the UE makes correct reporting of an event for UE configured with highSpeedMeasInterFreq-r17 (R4-2215217) | Ericsson | RAN5#99 (May-23) | R5-227863, R5-227864, R5-231709 | Jakub Kolodziej<jakub.kolodziej@ericsson.com> Pending on RAN4 to complete the RRM test cases Further update to TT analysis | 1 | 85% (+35%) |  | 85% (+35%) |  |  | 85%
16 | Y | 38.533 | 6.1.1.8 | NR SA FR1-FR1 Cell reselection for UE configured with highSpeedMeasInterFreq-r17 | To verify the requirement for the inter frequency NR cell reselection requirements for UE configured with highSpeedMeasInterFreq-r17 (R4-2215217) | Ericsson | RAN5#99 (May-23) | R5-227865, R5-227866, R5-231950 | Jakub Kolodziej<jakub.kolodziej@ericsson.com> Pending on RAN4 to complete the RRM test cases Further update to TT analysis | 1 | 85% (+35%) | 85% (+35%) |  |  | 85%
17 | Y | 38.533 | 6.6.1.8 | NR SA FR1 event triggered reporting without gap in DRX for UE configured with highSpeedMeasCA-Scell-r17 | To verify that the UE makes correct reporting of an event for UE configured with highSpeedMeasCA-Scell-r17 (R4-2215217) | Ericsson | RAN5#99 (May-23) | R5-227207, R5-227867,R5-231951 | Jakub Kolodziej<jakub.kolodziej@ericsson.com> Pending on RAN4 to complete the RRM test cases Further update to TT analysis | 1 | 85% (+35%) | 85% (+35%) |  |  | 85%
18 | Y | 38.533 | 6.6.2.12 | NR SA FR1 event triggered reporting tests without SSB time index detection INin DRX for UE configured with highSpeedMeasInterFreq-r17 | To verify that the UE makes correct reporting of an event when UE is configured with highSpeedMeasInterFreq-r17 (R4-2215217) | Ericsson | RAN5#99 (May-23) | R5-227868, R5-231710 | Jakub Kolodziej<jakub.kolodziej@ericsson.com> Pending on RAN4 to complete the RRM test cases Further update to TT analysis | 1 | 85% (+35%) | 85% (+35%) |  |  | 85%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
20 |  | 38.903 | <Clause> | <Title> | Add TT analyses for the new test cases introduced for 38.533 |  | RAN5#98 (Feb-23) |  | TT analyses for 38.533 have been captured in Column "TDOC(s)" for 38.521-4 test cases. | 1 |  |  |  |  | 0% | 0%
21 |  | 38.903 | <Clause> | <Title> | Add TT analyses for the new test cases introduced for 38.521-4. |  | RAN5#98 (Feb-23) |  | TT analyses for 38.521-4 have been captured in Column "TDOC(s)" for 38.521-4 test cases. | 1 | 0% | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.