## WP scope
Work plan for introduction of EN-DC PC3 FR1 configurations into 3GPP UE conformance test specifications
| WP template: | PRD21, WP EN-DC PC3 FR1 v1.4.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | WP EN-DC PC3 FR1 for DC_71A_n2A | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) |  | Qualcomm (Kevin Wang) | [6 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | RAN5 #99 | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
| Overall completion |  | 100%
Target configurations
Note: A work plan can include multiple target configurations but it is recommended to create separate work plans for Intra-band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Comments | Introduced in PRD version
| Rel-17 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_71A_n2A | DC_71A_n2A | Ongoing | PC3 |  |  | Rogers | Qualcomm (Kevin Wang) | RAN5#94-e, RAN5#97 | NR_CADC_NR_LTE_DC_R17-UEConTest |  | v.1.0.0

## WP EN-DC PC3 FR1
Work plan for introduction of EN-DC PC3 FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [12 empty] | WP template: PRD21, WP EN-DC PC3 FR1 v1.4.0
1. EN-DC configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | EN-DC confifurations [DL/UL]
|  | New EN-DC configuration(s) without UL DC |  |  |  | DL/- BCS0
|  | New EN-DC configurations with UL DC |  |  |  | DL/UL BCS0 | DC_71A_n2A/DC_71A_n2A
|  | New EN-DC configuration(s) without UL DC |  |  |  | DL/- new BCS
|  | New EN-DC configurations with UL DC |  |  |  | DL/UL new BCS
|  | All configurations |  |  |  | All | DC_71A_n2A/DC_71A_n2A
|  | All BCS0 configurations (No BCS included in config.name) |  |  |  | All BCS0 | DC_71A_n2A/DC_71A_n2A
|  | All new BCS configurations with BCS>0 |  |  |  | All new BCS
2. Overall status vs WP steps
[7 empty] | Status |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
|  | Overall completeness |  |  |  |  | 100%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 100%
|  | Step 2: Complete Test Point (TP) analysis for impacted EN-DC configurations |  |  |  |  | 100%
|  | Step 3.1: CR(s) to common test environment (TS 38.508-1) |  |  |  |  | 100%
|  | Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-3) |  |  |  |  | 100%
|  | Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6) |  |  |  |  | 100%
|  | Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7) |  |  |  |  | 100%
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
|  | Step 4: CR(s) for new ICS/capabilities (TS 38.508-2) |  |  |  |  | 100%
3. Details
[8 empty] | WP item columns to be filled in |  |  |  | Do not edit |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Bands completed | CA completed | TCs available | BSC0 completed | Impacted CBWs identified | Bands new CBWs completed
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1
All BCS0 | 1-1 | Pre-requisite | PRD21 | NR bands worksheet | All NR bands completed | DC_71A_n2A/DC_71A_n2A | Set status in column "Bands completed" to 100% when all impacted NR bands have been confirmed completed in PRD21 worksheet "NR bands". |  | RAN5 #99 |  |  | 1 | 100% | 100%
All BCS0 | 1-1.1 | Pre-requisite | PRD21 | 5G NR CADC Configurations | All NR CA configurations included in the EN-DC configurations within the WP scope are completed | DC_71A_n2A/DC_71A_n2A | Set status in column "CA completed" to 100% when all NR CA sub-configurations included in the WP scope's EN-DC configurations are listed as completed in RAN5 PRD21 worksheet "5G NR CADC Configurations". |  | RAN5 #99 |  |  | 1 | 100% |  | 100%
All BCS0 | 1-2 | Pre-requisite | 38.521-3 | Annex A | All E-UTRA bands completed | DC_71A_n2A/DC_71A_n2A | Set status in column "Bands completed" to 100% when all impacted E-UTRA bands have been confirmed completed in RAN5 TSs and TRs. |  | RAN5 #99 |  |  | 1 | 100% | 100%
All BCS0 | 1-3 | Pre-requisite | PRD20 | E-UTRA CA list work sheet | All E-UTRA CA configurations included in the EN-DC configurations within the WP scope are completed | DC_71A_n2A/DC_71A_n2A | Set status in column "E-UTRA CA completed" to 100% when all E-UTRA CA sub-configurations included in the WP scope's EN-DC configurations are listed as completed in RAN5 PRD20. |  | RAN5 #99 |  |  | 1 | 100% | 100%
All BCS0 | 1-4 | Pre-requisite | 38.521-3 | 6, 7 | All applicable Transmitter (clause 6), Receiver (clause 7) for the type of EN-DC configuraiton completed | DC_71A_n2A/DC_71A_n2A | Set status in column "TCs available" to 100% when all relevant test cases in 36.521-3 for the WP scope of EN-DC configuration types are completed. If the relevant test cases are not completed then contact the responsible for the test case as indicated in the relevant WI WP and consider to support to get the test case(s) completed. |  | RAN5 #99 | R5-231797 R5-230897 R5-231682 R5-230906 R5-231680 R5-231681 |  | 1 | 100% |  |  | 100%
All new BCS | 1-5 | Pre-requisite | 38.101-1 | 5.5A.1 | BCS0 completed for the EN-DC configuration |  | Set status in column "BCS0 completed" to 100% when the BCS0 of all the new BSC configurations have been confirmed completed in RAN5 PRD21 worksheet "5G NR CADC configurations". BSC0 configuration is listed in PRD21 as EN-DC configuration without "BSC" suffix in the name. |  | RAN5 #99 |  |  | 1 |  |  |  |  | 0%
All new BCS | 1-6 | Pre-requisite | 38.101-1 | 5.5A.1 | Bandwidth included in the new BCS |  | Set status in column "Impacted CBWs identified" when all new CBWs added by the new BCS of the configuration(s) have been identified and listed in the "Comments" column. |  | RAN5 #99 |  |  | 1 | [5 empty] | 0%
All new BCS | 1-7 | Pre-requisite | 38.101-1 PRD21 | NR bands worksheet | All NR bands completed for new BCS |  | Set status in column "Bands new CBWs completed" to 100% when all channel bandwidths of the involved NR bands for the new BCS of the configuration have been confirmed completed in RAN5 PRD21 worksheet "NR bands". |  | RAN5 #99 |  |  | 1 | [6 empty] | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted EN-DC configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
TP analysis
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
DL/UL BCS0 | 2-1 | TP Analysis | 38.905 | 4.3 | Test point (TP) analysis for MOP | DC_71A_n2A/DC_71A_n2A | For each Intra-band contiguous, intra-band non-contiguous and inter-band EN-DC band combination add TP Analysis for Maximum Output Power (MOP) in TR 38.905. The status column "TP analysis" is set to 100% when all required MOP TP analysis have been included in TR 38.905. |  | RAN5 #99 |  |  | 1
DL/UL BCS0 | 2-2 | TP Analysis | 38.905 | 4.3 | Test point (TP) analysis for A-MPR for Intra-band contiguous and non-contiguous EN-DC band combinations | DC_71A_n2A/DC_71A_n2A | For each Intra-band contiguous and intra-band non-contiguous EN-DC band combination add TP Analysis for A-MPR as described in TR 38.905. The status column "TP analysis" is set to 100% when all required MOP TP analysis have been included in TR 38.905. |  | RAN5 #99 |  |  | 1
All BCS0 | 2-3a | TP Analysis | 38.905 | 4.3 | Test point (TP) analysis for reference sensitivity for BCS0 | DC_71A_n2A/DC_71A_n2A | For each inter-band EN-DC configuration perform reference sensitivity TP analysis as described in TR 38.905. Document the TP analysis by a CR to TR 38.905. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | RAN5 #99 | R5-231613 |  | 1 | 100% | 100%
All new BCS | 2-3b | TP Analysis | 38.905 | 4.1.3.1 | Test point (TP) analysis for reference sensitivity for new BCS > 0 |  | For each new BCS for of the inter-band EN-DC configurations perform reference sensitivity TP analysis as described in TR 38.905. for the new BCSs. Document the TP analysis by a CR to TR 38.905. The status column "TP analysis" is set to 100% when all required TP analysis for the new BCSs have been included in TR 38.905. |  | RAN5 #99 |  |  | 1 |  | 0%
DL/UL BCS0 | 2-4 | TP Analysis | 38.905 | 4.3 | Test point (TP) analysis for general and UE co-existence spurious emission test cases for EN_DC | DC_71A_n2A/DC_71A_n2A | For each two band EN_DC inter-band configuration perform general spurious emission and UE-coexistence spurious emission TP analysis as described in TR 38.905. Document the TP analysis by a CR to TR 38.905 including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | RAN5 #99 | R5-231614 |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Test Freq.
1
All BCS0 | 3.1-1a | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.4.x | NR Test frequencies | DC_71A_n2A/DC_71A_n2A | - Add the EN-DC configuration to the relevant test frequency table in clause 4.3.1.3 - Check that the involved NR bands have single carrier test frequencies specified in 4.3.1.x - For EN-DC configurations including any intra-band EN-DC contiguous CCs or any intra-band EN-DC non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified in in clause clause 4.3.1.4.x. |  | RAN5 #99 |  |  | 1 | 100% | 100%
All new BCS | 3.1-1b | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.4.x | NR test frequencies BSC>0 |  | For EN-DC configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified for the new BCS CBW combinations in clause 4.3.1.4.x. |  | RAN5 #99 |  |  | 1 |  | 0%
All BCS0 | 3.1-2a | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.4.x | EN-DC band combination test frequencies BCS0 | DC_71A_n2A/DC_71A_n2A | For EN-DC Inter-band configurations add the CA configuration to the relevant table in one of the clause 4.3.1.4.x. |  | RAN5 #99 |  |  | 1 | 100% | 100%
All new BCS | 3.1-2b | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.4.x | EN-DC band combination test frequencies BSC>0 |  | For EN-DC configurations including any EN-DC or NR CA intra-band contiguous CCs or any EN_DC or NR CA intra-band non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified for the new BCS CBW combinations in clause 4.3.1.4.x. |  | RAN5 #99 |  |  | 1 |  | 0%
All BCS0 | 3.1-3 | 38.508-1 - (6) Common SIG | 38.508-1 | 6.2.3.2 | Test frequencies for EN_DC signalling test | DC_71A_n2A/DC_71A_n2A | For Intra-band contiguous or intra-band non-contiguous configurations with 2CC add test frequencies in clause 6.2.3.2. |  | RAN5 #99 |  |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-3)
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Clause 5 | Discussion paper
[14 empty] | 1 | 1
All BCS0 | 3.2-0 | 38.521-3 - General | PRD21 | 4.1 | Discussion paper on adding configuration to chapter 5 without changes to RF transmitter and receiver test cases. | DC_71A_n2A/DC_71A_n2A | If it is thought there are no configuration specific changes needed for Chapter 6/7 or only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7, a paper shall be submitted to justify why no such changes are needed to Chapter 6/7 or why only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7. If deemed that no discussion paper is needed then set status to 100% and add comment in the comments column why no discussion paper is needed. |  | 100 |  |  | 1
All BCS0 | 3.2-1 | 38.521-3 - General | 38.521-3 | 5.5B.2 | Intra-band contiguous EN-DC | DC_71A_n2A/DC_71A_n2A | Add band combinations for intra-band contiguous EN-DC to the relevant table in clause 5.5B.3. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5 #99 |  |  | 1
All BCS0 | 3.2-2 | 38.521-3 - General | 38.521-3 | 5.5B.3 | Intra-band non-contiguous EN-DC | DC_71A_n2A/DC_71A_n2A | Add band combinations for intra-band non-contiguous EN-DC to the relevant table in clause 5.5B.3. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5 #99 |  |  | 1
All BCS0 | 3.2-3 | 38.521-3 - General | 38.521-3 | 5.5B.4 | Inter-band EN-DC | DC_71A_n2A/DC_71A_n2A | Add inter-band EN-DC configurations within FR1 to the relevant table in clause 5.5B.4. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5 #99 |  |  | 1 | 100% | 100%
All BCS0 | 3.2-4 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.4.2.3 .1 | ΔTIB,c for inter-band EN-DC | DC_71A_n2A/DC_71A_n2A | Add ΔTIB,c for inter-band EN-DC within FR1 to the relevant table in clause 6.2B.4.2.3. |  | RAN5 #99 |  |  | 1 | 100% | 100%
All BCS0 | 3.2-5 | 38.521-3 - RF Tx | 38.521-3 | 7.3B.2.0.3 | Inter-band EN-DC | DC_71A_n2A/DC_71A_n2A | Add Reference sensitivity exceptions for EN-DC within FR1 to the relevant table in clause 7.3B.2.0.3. |  | RAN5 #99 |  |  | 1 | 100% | 100%
All BCS0 | 3.2-6 | 38.521-3 - General | 38.521-3 | 7.3B.3.2 | Reference sensitivity ΔRIB,c for Intra-band non-contiguous EN-DC | DC_71A_n2A/DC_71A_n2A | For Intra-band non-contiguous EN-DC configurations add ΔRIB,c for Intra-band non-contiguous EN-DC to the relevant table in clause 7.3B.3.2. |  | RAN5 #99 |  |  | 1
All BCS0 | 3.2-7 | 38.521-3 - General | 38.521-3 | 7.3B.3.3.1 | ΔRIB,c for EN-DC in two bands | DC_71A_n2A/DC_71A_n2A | For EN-DC in two bands inter-band EN-DC configurations add ΔRIB,c in relevant table in clause 7,3B.3.3.1 |  | RAN5 #99 |  |  | 1 | 100% | 100%
All BCS0 | 3.2-8 | 38.521-3 - General | 38.521-3 | 7.3B.3.3.2 | ΔRIB,c for EN-DC in three bands | DC_71A_n2A/DC_71A_n2A | For EN-DC in three bands inter-band EN-DC configurations add ΔRIB,c in relevant table in clause 7,3B.3.3.2 |  | RAN5 #99 |  |  | 1
All BCS0 | 3.2-9 | 38.521-3 - General | 38.521-3 | 7.3B.3.3.3 | ΔRIB,c for EN-DC in four bands | DC_71A_n2A/DC_71A_n2A | For EN-DC in four bands inter-band EN-DC configurations add ΔRIB,c in relevant table in clause 7,3B.3.3.3 |  | RAN5 #99 |  |  | 1
All BCS0 | 3.2-10 | 38.521-3 - General | 38.521-3 | 7.3B.3.3.4 | ΔRIB,c for EN-DC in five bands | DC_71A_n2A/DC_71A_n2A | For EN-DC in five bands inter-band EN-DC configurations add ΔRIB,c in relevant table in clause 7,3B.3.3.4 |  | RAN5 #99 |  |  | 1
All BCS0 | 3.2-11 | 38.521-3 - General | 38.521-3 | 7.3B.3.3.5 | ΔRIB,c for EN-DC six bands | DC_71A_n2A/DC_71A_n2A | For EN-DC in six bands inter-band EN-DC configurations add ΔRIB,c in relevant table in clause 7,3B.3.3.5 |  | RAN5 #99 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 |  |  | 2
DL/UL BCS0 | 3.3-1 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.1.1 | UE Maximum Output Power for Intra-Band Contiguous EN-DC Note! This WP item is dependent on MOP TP analysis (Step 2, WP item 2-1) | DC_71A_n2A/DC_71A_n2A | For Intra-band contiguous EN-DC configurations within FR1: Update MOP for intra band contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.2B.1.1 based on TP analysis in 38.905 (WP item 2-1). |  | RAN5 #99 |  |  | 1
DL/UL BCS0 | 3.3-2 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.1.2 | UE Maximum Output Power for Intra-Band Non-Contiguous EN-DC Note! This WP item is dependent on MOP TP analysis (Step 2, WP item 2-1) | DC_71A_n2A/DC_71A_n2A | For Intra-band non contiguous EN-DC configurations within FR1: Update MOP for intra band non contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.2B.1.12based on TP analysis in 38.905 (WP item 2-1). |  | RAN5 #99 |  |  | 1
DL/UL BCS0 | 3.3-3 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.1.3 | UE Maximum Output Power for Inter-Band EN-DC within FR1 Note! This WP item is dependent on MOP TP analysis (Step 2, WP item 2-1) | DC_71A_n2A/DC_71A_n2A | For Inter-band configurations within FR1: Update maximum output power for inter-band EN-DC within FR1 to the relevant table in minimum conformance requirements/initial condition/test requirements in clause 6.2B.1.3 based on TP analysis in 38.905 (WP item 2-1). |  | RAN5 #99 | R5-230895 |  | 1 | 100% | 100% |  | 100% | 100%
DL/UL BCS0 | 3.3-4 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.3.1 | UE Additional Maximum Output Power reduction for Intra-band contiguous EN-DC Note! This WP item is dependent on A-MPR TP analysis (Step 2, WP item 2-2) | DC_71A_n2A/DC_71A_n2A | For Intra-band contiguous EN-DC configurations within FR1: Update A-MPR for intra band contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.2B.3.1 based on TP analysis in 38.905 (WP item 2-2). |  | RAN5 #99 |  |  | 1
DL/UL BCS0 | 3.3-5 | 38.521-3 - RF Tx | 38.521-3 | 6.2B.3.2 | UE Additional Maximum Output Power reduction for Intra-Band Non-Contiguous EN-DC Note! This WP item is dependent onA-MPR TP analysis (Step 2, WP item 2-2) | DC_71A_n2A/DC_71A_n2A | For Intra-band non-contiguous EN-DC configurations within FR1: Update A-MPR for intra band non-contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements of in clause 6.2B.3.2 based on TP analysis in 38.905 (WP item 2-2). |  | RAN5 #99 |  |  | 1
DL/UL BCS0 | 3.3-6 | 38.521-3 - RF Tx | 38.521-3 | 6.5B.3.1.2 | Spurious emission band UE co-existence for intra-band contiguous EN-DC | DC_71A_n2A/DC_71A_n2A | For Intra-band contiguous EN-DC configurations within FR1: Update Spurious Emission band UE co-existence for intra band contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.5B.3.1.2. |  | RAN5 #99 |  |  | 1
DL/UL BCS0 | 3.3-7 | 38.521-3 - RF Tx | 38.521-3 | 6.5B.3.2.2 | Spurious emission band UE co-existence for intra-band non-contiguous EN-DC | DC_71A_n2A/DC_71A_n2A | For Intra-band non-contiguous EN-DC configurations within FR1: Update Spurious Emission band UE co-existence for intra band non-contiguous EN-DC within FR1 (intra band contiguous) to minimum conformance requirements/initial condition/test requirements in clause 6.5B.3.2.2. |  | RAN5 #99 |  |  | 1
DL/UL BCS0 | 3.3-8 | 38.521-3 - RF Tx | 38.521-3 | 6.5B.3.3.1 | General Spurious Emissions for Inter-band EN-DC within FR1 Note! This WP item is dependent spurious emission TP analysis (Step 2, WP item 2-4) | DC_71A_n2A/DC_71A_n2A | For Inter-band contiguous EN-DC configurations within FR1: Update General Spurious Emissions for inter-band EN-DC within FR1 to Table 6.5B.3.3.1.5-1 in Test Requirement in clause 6.5B.3.3.1 based on TP analysis in 38.905 (WP item 2-3). |  | RAN5 #99 | R5-231681 |  | 1 | 100% | 100% |  | 100% | 100%
DL/UL BCS0 | 3.3-9 | 38.521-3 - RF Tx | 38.521-3 | 6.5B.3.3.2 | Spurious emission band UE co-existence for Inter-band within FR1 Note! This WP item is dependent spurious TP analysis (Step 2, WP item 2-4) | DC_71A_n2A/DC_71A_n2A | For Inter-band configurations within FR1: Update Spurious Emission band UE co-existence for Inter-band within FR1 (intra band contiguous) to the tables in minimum conformance requirements/initial condition/test requirements in clause 6.5B.3.3.2 based on TP analysis in 38.905 (WP item 2-3). |  | RAN5 #99 | R5-231680 |  | 1 | 100% | 100% |  | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 |  |  | 2
All BCS0 | 3.4-1a | 38.521-3-RF Rx | 38.521-3 | 7.3B.2.3 | Reference sensitivity for Inter-band EN-DC within FR1 (2 CCs) and BCS0 Note! This WP item is dependent on Reference Sensitivity TP analysis (Step 2, WP item 2-3a) | DC_71A_n2A/DC_71A_n2A | For Inter-band configurations within FR1 (2 CCs): Update the tables in initial condition/test requirements in clause 7.3B.2.3 based on TP analysis in 38.905 (WP item 2-3a). |  | RAN5 #99 | R5-231682 |  | 1 | 100% | 100% |  | 100% | 100%
All new BCS | 3.4-1b | 38.521-3-RF Rx | 38.521-3 | 7.3B.2.3 | Reference sensitivity power level for EN_DC within FR1 (2CCs) and BCS > 0 Note! This WP item is dependent on Reference Sensitivity TP analysis (Step 2, WP item 2-3b) |  | For new BCS of Inter-band configurations within FR1 (2 CCs): Update the tables in initial condition/test requirements in clause 7.3B.2.3 based on TP analysis in 38.905 (WP item 2-3a). |  | RAN5 #99 |  |  | 1 |  | 0% |  | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 |  |  | 2
| 3.5-1 | [5 empty] | No changes needed |  | RAN5 #99 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 | [5 empty] | No changes needed |  | RAN5 #99 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
All | 4-1 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2B.2.1 | Intra-band contiguous EN-DC within FR1 | DC_71A_n2A/DC_71A_n2A | Add configurations for intra-band contiguous EN-DC within FR1 to the relevant table in clause A.4.3.2B.2.1. |  | RAN5 #99 |  |  | 1
All | 4-2 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2B.2.2 | Intra-band non-contiguous EN-DC within FR1 | DC_71A_n2A/DC_71A_n2A | Add configurations for intra-band non-contiguous EN-DC within FR1 to the relevant table in clause A.4.3.2B.2.2. |  | RAN5 #99 |  |  | 1
All | 4-3 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2B.2.1~A.4.3.2B.2.5 | Inter-band EN-DC within FR1 | DC_71A_n2A/DC_71A_n2A | Add configurations for inter-band EN-DC within FR1 to the relevant table in relevant clauses A.4.3.2B.2.1~A.4.3.2B.2.5. |  | RAN5 #99 | R5-231797 |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N31: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N45: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N57: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N68: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N86: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N101: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N109: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N116: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N123: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.4.0 | RAN5#98 | No changes. Same as v1.3.0.
v1.3.0 | RAN5#97 | No changes. Same as v1.2.0.
v1.2.0 | RAN5#96-e | 1. Extended the number of rows in the input table to cope with the case when multiple cut and paste of configurations from PRD21 CADC list are done. 2. Clarify references to TP analysis in dependent test cases.
v1.1.0 | RAN5#95-e | 1. Updated WP template version in WP scope worksheet to get version number from cell A3 in the "Revision History WP template" worksheet. 2. Correcting formulas in cells I5 to I7 on WP worksheet to handle the case when configuration table includes empty cells for the configuration columns. 3. Correcting TS reference in "area" and "TS" columns from 36.521-1 to 38.521-3. 4. Editorial corrections multiple items 5. Added a note to WP-items 3.2-1 to 3.2-7 to remind about merge with "jumbo" CR. 6. Added WP item 3.2-0 about need for discussion paper to add configuration information to chapter 5. 7. Added WP item 1-1.1 to check that sub-NR CA configurations have been completed as part of WP pre-requisite. 8. Corrected reference to inter-band configuration in the task description for WP item 3.3-8.
v1.0.0 | RAN5#94-e | Initial version