## Cover sheet
3GPP TSG-RAN WG5 Meeting #99 | [8 empty] | R5-232727
Incheon, South Korea, May 22th - 26th 2023
Agenda Item: | 7.4.2
Source: | Huawei, Hisilicon
Title: | WP UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR
Work item code: | NR_RF_TxD-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WID on transparent Tx diversity for NR, including test cases and associated test environment, test applicability, test point analysis, etc. At RAN#94 meeting in November 2021 the Rel-17 work item for UE conformance - UE RF requirements for transparent Tx diversity for NR was approved [1]. The purpose of this present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+5%) | 26 (+1) | 26
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 100% (+5.2%) | 26 (+1) | 26
FR1 |  | 100% (+5.2%) | 26 (+1) | 26
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+25%) |  |  | 100% (+25%)
Common ICS | 38.508-2 | 100% |  |  | 100%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 100% (+6.7%) |  |  | 100% (+6.7%)
FR1 RF Tx test cases | 38.521-1 Tx | 100% (+2.1%) | 26 (+1) | 26 | 100% (+2.1%) | 26 (+1) | 26
FR1 RF Rx test cases | 38.521-1 Rx | 100% (+8%) |  |  | 100% (+8%)
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% (+5%) |  |  | 100% (+5%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905 | 100% (+30%) |  |  | 100% (+30%)
5 References
[1] RP-213229 | UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RF_TxD-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Transparent Tx Diversity for NR comprising the necessary new clauses/test cases and updates to existing clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
100% (+5.2%)
56 (+3)
54.6 (+3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | Annex A | Connection Diagrams | Connection Diagrams for Tx diversity | Huawei | RAN5#95 (May-22) | R5-222924 |  | 1 | 100% | 100% |  | 100%
60 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Adding defaulte messages related to TxD | CMCC | RAN5#97 (Nov-22) | R5-225686 |  | 1 | 100% (+50%) | 100% (+50%) |  | 100%
63 |  | 38.508-1 | 5.4 | Default NG-RAN RRC message and information elements contents | Adding defaulte messages related to TxD | Huawei | RAN5#99 (May-23) | R5-232723 |  | 1 | 100% | 100% |  | 100%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | CMCC | RAN5#95 (May-22) | R5-223772 |  | 1 | 100% | 100% |  | 100%
NR RF
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
64 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations |  | Huawei | RAN5#99 (May-23) | R5-232726 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
65 |  | 38.521-1 | 4.2 | Applicability of minimum requirements |  | Huawei | RAN5#99 (May-23) | R5-232726 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
62 |  | 38.521-1 | 4.3 | Specification suffix information |  | Keysight Technologies UK Ltd | RAN5#97 (Nov-22) | R5-227064 |  | 1 | 100% | 100% |  | 100%
61 |  | 38.521-1 | Annex E | Global In-Channel TX-Test |  | Huawei | RAN5#97 (Nov-22) | R5-226914 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100%
56 |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT | Huawei | RAN5#97 (Nov-22) | R5-223782 R5-224790 R5-226915 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
3 |  | 38.521-1 Tx | 6 | Transmitter characteristics | Updating test applicability for all single carrier Tx cases as PC3 UEs and PC2 UEs not supporting TxD. | CMCC | RAN5#95 (May-22) | R5-223773 R5-223774 R5-223775 R5-223776 |  | 1 | 100% (+50%) | 100% (+50%) |  | 100%
58 |  | 38.521-1 Tx | 6.1 | General | Updating general definition for Tx diversity | Huawei | RAN5#95 (May-22) | R5-222930 |  | 1 | 100% | 100% |  | 100%
4 |  | 38.521-1 Tx | 6.2G | Transmitter power for Tx Diversity | New Sub-title |  |  |  |  | 0
5 | Y | 38.521-1 Tx | 6.2G.1 | UE maximum output power for Tx Diversity | PC 2 and PC1.5 specific requirements are specified. (PC 1.5 test case is handled by PC 1.5 work items） Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | Huawei | RAN5#96 (Aug-22) | R5-223777 R5-225687 R5-224242 R5-228056 | Editor’s Note: The following aspects are either missing or not yet determined: - No test points are defined for Power Class 1.5 non-FWA UEs since there is no configuration satisfying MPR=0dB requirements in RAN4. Testing with minimum0.5dB MPR as recommended by RAN4 has been covered in 6.2G.2. | 1 | 100% | 100% |  | 100%
6 | Y | 38.521-1 Tx | 6.2G.2 | UE maximum output power reduction for Tx Diversity | PC 2 and PC1.5 specific requirements are specified. (PC 1.5 test case is handled by PC 1.5 work items） Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | Huawei | RAN5#96 (Aug-22) | R5-223778 R5-224242 R5-227913 |  | 1 | 100% | 100% |  | 100%
7 | Y | 38.521-1 Tx | 6.2G.3 | UE additional maximum output power reduction for Tx Diversity | PC 2 and PC1.5 specific requirements are specified. (PC 1.5 test case is handled by PC 1.5 work items） Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | Huawei | RAN5#96 (Aug-22) | R5-223779 R5-224242 R5-225756 | Editor’s note: The following aspects are either missing or not yet determined: - Tests for network signalling values NS_47 for Power Class 2 with contiguous allocation is complete. - Tests for network signalling values NS_04, NS_50, NS_55 for Power Class 2 and NS_04, NS_47, NS_55 for Power Class 1.5 are FFS. - The test points for Power Class 1.5 FWA UEs are TBD. - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
59 |  | 38.521-1 Tx | 6.2.4 | Configured transmitted power | Introducing SRS IL for UEs with Tx diversity to align with TS 38.101-1 | Apple Portugal | RAN5#95 (May-22) | R5-223781 R5-228057 | No need to test in RAN5 specification | 1 | 100% | 100% |  | 100%
8 | Y | 38.521-1 Tx | 6.2G.4 | Configured transmitted power for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | Google | RAN5#97 (Nov-22) | R5-228055 |  | 1 | 100% | 100% |  | 100%
9 |  | 38.521-1 Tx | 6.3G | Transmitter power for Tx Diversity | New Sub-title |  |  |  |  | 0
10 | Y | 38.521-1 Tx | 6.3G.1 | Minimum output power for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | Huawei | RAN5#96 (Aug-22) | R5-224779 R5-228058 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
11 | Y | 38.521-1 Tx | 6.3G.2 | Transmit OFF power for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. | Huawei | RAN5#96 (Aug-22) | R5-224780 R5-228058 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
12 |  | 38.521-1 Tx | 6.3G.3 | Transmit ON/OFF time mask for Tx Diversity | New Sub-title |  |  |  |  | 0
13 | Y | 38.521-1 Tx | 6.3G.3.1 | General ON/OFF time mask for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. | Huawei | RAN5#96 (Aug-22) | R5-224781 R5-228058 R5-230561 R5-233540 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
14 | Y | 38.521-1 Tx | 6.3G.3.2 | PRACH time mask for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. | Huawei | RAN5#96 (Aug-22) | R5-224782 R5-228058 R5-230561 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
15 | Y | 38.521-1 Tx | 6.3G.3.3 | SRS time mask for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. | Huawei | RAN5#96 (Aug-22) | R5-224783 R5-228058 R5-230561 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
16 |  | 38.521-1 Tx | 6.3G.4 | Power control for Tx Diversity | New Sub-title |  |  |  |  | 0
17 | Y | 38.521-1 Tx | 6.3G.4.1 | Absolute power tolerance for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | Apple | RAN5#97 (Nov-22) | R5-228059 R5-230561 |  | 1 | 100% | 100% |  | 100%
18 | Y | 38.521-1 Tx | 6.3G.4.2 | Relative power tolerance for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | Huawei | RAN5#96 (Aug-22) | R5-224784 R5-228058 R5-230561 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
19 | Y | 38.521-1 Tx | 6.3G.4.3 | Aggregate power tolerance for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | Huawei | RAN5#96 (Aug-22) | R5-224785 R5-228058 R5-230561 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
20 |  | 38.521-1 Tx | 6.4G | Transmit signal quality for Tx Diversity | New Sub-title |  |  |  |  | 0
21 | Y | 38.521-1 Tx | 6.4G.1 | Frequency error for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. | Huawei | RAN5#96 (Aug-22) | R5-225757 R5-228060 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
22 |  | 38.521-1 Tx | 6.4G.2 | Transmit modulation quality for Tx Diversity | New Sub-title |  |  |  |  | 0
23 | Y | 38.521-1 Tx | 6.4G.2.1 | Error Vector Magnitude for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. | Apple | RAN5#97 (Nov-22) | R5-228061 |  | 1 | 100% | 100% |  | 100%
24 | Y | 38.521-1 Tx | 6.4G.2.2 | Carrier leakage for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. | Huawei, Keysight | RAN5#96 (Aug-22) | R5-225758 R5-228060 R5-227934 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
25 | Y | 38.521-1 Tx | 6.4G.2.3 | In-band emissions for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. | Huawei, Keysight | RAN5#96 (Aug-22) | R5-225759 R5-228060 R5-227934 | Editor’s Note: The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
26 | Y | 38.521-1 Tx | 6.4G.2.4 | EVM equalizer spectrum flatness for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. | Huawei | RAN5#97 (Nov-22) | R5-225760 R5-228060 R5-233720 | Editor’s Note: The test case is not completed. The following aspects are either missing or not yet determined: - Update to Annex E is FFS. | 1 | 100% (+10%) | 100% (+10%) |  | 100%
27 |  | 38.521-1 Tx | 6.5G | Output RF spectrum emissions for Tx Diversity | New Sub-title |  | TBD |  |  | 0
28 | Y | 38.521-1 Tx | 6.5G.1 | Occupied bandwidth for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. The occupied bandwidth is defined at each antenna connector. Measurement is defined as the sum of both UE antenna connectors. | China Telecom | RAN5#96 (Aug-22) | R5-225761 R5-228062 | Editor’s Note: The test case is not completed. The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
29 |  | 38.521-1 Tx | 6.5G.2 | Out of band emission for Tx Diversity | New Sub-title |  |  |  |  | 0
30 | Y | 38.521-1 Tx | 6.5G.2.1 | Spectrum emission mask for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | Apple | RAN5#97 (Nov-22) | R5-228063 |  | 1 | 100% | 100% |  | 100%
31 | Y | 38.521-1 Tx | 6.5G.2.2 | Additional spectrum emission mask for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. |  | RAN5#97 (Nov-22) | R5-228064 |  | 1 | 100% | 100% |  | 100%
32 |  | 38.521-1 Tx | 6.5G.2.3 | Adjacent channel leakage ratio for Tx Diversity | New Sub-title |  |  |  |  | 0
33 | Y | 38.521-1 Tx | 6.5G.2.3.1 | NR ACLR for Tx Diversity | PC 2 and PC1.5 specific requirements are specified. (PC 1.5 test case is handled by PC 1.5 work items） Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement for assigned channel and ajacent channel is defined as the sum of both UE antenna connectors. | Huawei | RAN5#97 (Nov-22) | R5-223780 R5-228062 R5-230303 | Editor’s Note: The following aspects are either missing or not yet determined: - The test points for Power Class 1.5 FWA UEs are TBD. - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
33 | Y | 38.521-1 Tx | 6.5G.2.3.2 | UTRA ACLR for Tx Diversity | PC 2 and PC1.5 specific requirements are specified. (PC 1.5 test case is handled by PC 1.5 work items） Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement for assigned channel and ajacent channel is defined as the sum of both UE antenna connectors. | Huawei | RAN5#97 (Nov-22) | R5-228065 | Editor’s Note: The following aspects are either missing or not yet determined: - The test points for Power Class 1.5 FWA UEs are TBD. - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
34 |  | 38.521-1 Tx | 6.5G.3 | Spurious emission for Tx Diversity | New Sub-title |  |  |  |  | 0
35 | Y | 38.521-1 Tx | 6.5G.3.1 | General spurious emissions for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | China Telecom | RAN5#96 (Aug-22) | R5-225761 | Editor’s Note: The test case is not completed. The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
36 | Y | 38.521-1 Tx | 6.5G.3.2 | Spurious emissions for UE co-existence for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | China Telecom | RAN5#97 (Nov-22) | R5-228053 |  | 1 | 100% | 100% |  | 100%
37 | Y | 38.521-1 Tx | 6.5G.3.3 | Additional spurious emissions for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Measurement is defined as the sum of both UE antenna connectors. | China Telecom | RAN5#97 (Nov-22) | R5-228054 |  | 1 | 100% | 100% |  | 100%
38 | Y | 38.521-1 Tx | 6.5G.4 | Transmit intermodulation for Tx Diversity | Requirements are general for PC2 and PC1.5. Adding test case for PC 2 UE supporting Tx diversity and PC 1.5 UE. Minimum requirements apply to each antenna connector. The wanted signal is defined as the sum of output power from both UE antenna connectors. | China Telecom | RAN5#96 (Aug-22) | R5-225762 | Editor’s Note: The test case is not completed. The following aspects are either missing or not yet determined: - Tests for Power Class 3 are FFS. | 1 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
57 |  | 38.521-1 Rx | 7.3.2 | Reference sensitivity power level | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
39 |  | 38.521-1 Rx | 7.4 | Maximum input level | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Apple | RAN5#97 (Nov-22) | R5-225763 R5-228066 |  | 1 | 100% (+20%) | 100% (+20%) |  | 100%
40 |  | 38.521-1 Rx | 7.4A.1 | Maximum input level for CA (2DL CA) | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
41 |  | 38.521-1 Rx | 7.5 | Adjacent channel selectivity | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
42 |  | 38.521-1 Rx | 7.5A.1 | Adjacent channel selectivity for CA (2DL CA) | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
43 |  | 38.521-1 Rx | 7.6.2 | In-band blocking | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
44 |  | 38.521-1 Rx | 7.6A.2.1 | In-band blocking for CA (2DL CA) | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
45 |  | 38.521-1 Rx | 7.6.3 | Out-of-band blocking | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
46 |  | 38.521-1 Rx | 7.6A.3.1 | Out-of-band blocking for CA (2DL CA) | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
47 |  | 38.521-1 Rx | 7.6.4 | Narrow band blocking | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
48 |  | 38.521-1 Rx | 7.6A.4.1 | Narrow band blocking for CA (2DL CA) | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
49 |  | 38.521-1 Rx | 7.7 | Spurious response | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
50 |  | 38.521-1 Rx | 7.7A.1 | Spurious response for CA (2DL CA) | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
51 |  | 38.521-1 Rx | 7.8.2 | Wide band Intermodulation | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
52 |  | 38.521-1 Rx | 7.8A.2.1 | Wide band Intermodulation for CA (2DL CA) | Changes are general for PC2 and PC1.5. Updating test procedure to set UE transmitter power for Tx diversity | Huawei | RAN5#97 (Nov-22) | R5-228066 |  | 1 | 100% | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases | [6 empty] | RAN5#97 (Nov-22)
53 |  | 38.522 | 4 | Test case conditions and selection criteria | Adding test case condition for Tx Diversity | CMCC | RAN5#95 (May-22) | R5-223783 |  | 0.3 | 100% | 100% |  | 100%
54 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | 1. Adding applicability for new test cases in TS 38.521-1. 2. Updating applicability for single carrier Tx cases in TS 38.521-1. | CMCC, Huawei | RAN5#97 (Nov-22) | R5-223783 R5-225764 R5-225765 R5-228040 R5-230576 |  | 0.3 | 100% (+10%) | 100% (+10%) |  | 100%
TR 38.905: Test Point analysis receiver and transmitter test cases
55 |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | Test point analysis for FR1 RF Test cases | Huawei | TBD | R5-222927 R5-222928 R5-222929 |  | 1 | 100% (+30%) | 100% (+30%) |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.