## Cover sheet
R5-233198
3GPP TSG-RAN5 Meeting #99 Incheon, Korea, May 22nd – 26th, 2023
Agenda Item: | 7.4.2
Source: | Qualcomm Incorporated
Title: | Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking
Work item code: | ID_UAS-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 6% (+6%) | 0 | 7 (+7)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 8.3% (+8.3%) | 0 | 7 (+7)
FR1 |  | 8.3% (+8.3%) | 0 | 7 (+7)
FR2 |  | 8.3% (+8.3%) | 0 | 7 (+7)
LTE |  | 0%
TDD |  | 0%
FDD |  | 0%
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | TDD |  |  | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 7 (+7) | 0% | 0 | 7 (+7) | 0% | 0 | 7 (+7)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-230716 | Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | ID_UAS-UEConTest
WP Scope: |  | <WP Scope description> | [13 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | Yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  | FR1 | FR2 | TDD | FDD
[15 empty] | 8.3% (+8.3%) | 8.3% (+8.3%) | 0% | 0%
[15 empty] | 12 (+12) | 12 (+12) | 4 (+4) | 4 (+4)
[15 empty] | 12 (+12) | 12 (+12) | 4 (+4) | 4 (+4)
0%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  | TBD |  |  | 1 | 0% |  | 0% |  |  |  | 0% | 0%
TS 36.523-1: Protocol test cases
2 |  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  | TBD |  |  | 1 | 0% |  | 0% |  |  |  | 0% | 0%
TS 36.523-2: Applicability for Protocol test cases
3 |  | 36.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  | TBD |  |  | 1 | 0% |  | 0% |  |  |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
4 |  | 36.523-3 | NA | Introduction of General and Signaling Test Environment for Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking |  |  | TBD |  |  | 1 | 0% |  | 0% |  |  |  | 0% | 0%
5GS
5GS Common
TS 38.508-1: Common test environment
5 |  | 38.508-1 | 4.6, 4.7, 4.9 | Introduction of General and Signaling Test Environment for Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking | ASN.1 and other updates | Qualcomm |  |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.508-2: Common ICS
6 |  | 38.508-2 | A.4.1 | Introduction of common implementation conformance statements for Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking | Add ICS as needed for the test case applicability statements for the new test cases | Qualcomm | RAN5#99 (May-23) |  | R5-233202 | 1 | 50% | 50% |  |  | 50% | 50%
TS 38.523-1: Protocol test cases
NAS
|  | 38.523-1 | 9.1 | 5GS mobility management | [5 empty] | 0
|  | 38.523-1 | 9.1.x | UAS / Mobility management aspects | [5 empty] | 0
7 | Y | 38.523-1 | 9.1.x.1 | UAS / Initial registration / UUAA / Rejected | TS 24.501, clauses 4.22.2, 5.4.5.2.3, 5.5.1, 5.5.1.2.2, 5.5.1.2.4, 5.5.1.2.5 | Qualcomm | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
8 | Y | 38.523-1 | 9.1.x.2 | UAS / Mobility and periodic registration update / UUAA / Rejected | TS 24.501, clauses 4.22.2, 5.5.1.2.2, 5.5.1.2.5, 5.5.2.3.2 | Ericsson | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
9 | Y | 38.523-1 | 9.1.x.3 | UAS / De-registration / UE-inittiated / Network-initiated | TS 24.501, clauses 4.22.2, 5.5.1.3.2, 5.5.1.3.4 | Nokia | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
10 | Y | 38.523-1 | 9.1.x.4 | UAS / Generic UE configuration update / Revocation | TS 24.501, clauses 4.22.2, 5.4.4.2, 5.4.4.3 | Nokia | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
|  | 38.523-1 | 10.1 | 5GS session management
|  | 38.523-1 | 10.1.x | UAS / Session management aspects
11 | Y | 38.523-1 | 10.1.x.1 | UAS / UE requested PDU session establishment / UUAA / Release | TS 24.501, clauses 6.3.2.2, 6.4.1.2, 6.4.1.3 | Ericsson | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
12 | Y | 38.523-1 | 10.1.x.2 | UAS / UE requested PDU session establishment / UUAA / C2 authorisation / Release | TS 24.501, clauses 6.3.2.2, 6.4.1.2, 6.4.1.3 |  |  |  |  | 1 | 0% | 0% |  |  | 0% | 0%
13 | Y | 38.523-1 | 10.1.x.3 | UAS / UE requested PDU session modification / C2 authorization | TS 24.501, clauses 6.3.2.2, 6.4.1.2, 6.4.1.4 |  |  |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
14 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | Qualcomm | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
15 |  | 38.523-3 | NA | Introduction of General and Signaling Test Environment for Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking |  | Qualcomm | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
Overall WP completion
16 |  |  |  | Overall Definition and scope of WI | [5 empty] | 1 | 50% | 50% |  |  | 50% | 50%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.