## Cover sheet
3GPP TSG-RAN WG5 Meeting #99 | [8 empty] | R5-233496
Incheon, Korea, 22nd May 2023 - 26th May 2023
Agenda Item: | 7.4.2
Source: | Samsung
Title: | WP - UE Conformance - NR support for high speed train scenario in frequency range 2
Work item code: | NR_HST_FR2-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WI ‘NR_HST_FR2’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover RF, Demod and RRM conformance test specifications for NR_HST_FR2.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 27% (+9%) | 0 | 23.2
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | 26.8% (+9.2%) | 0 | 23.2
FR2 |  | 26.8% (+9.2%) | 0 | 23.2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 50% (+50%) |  |  | 50% (+50%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%)
NR RF/RRM
FR2 RF common parts | 38.521-2 | 0% |  |  | 0%
FR2 RF Tx test cases | 38.521-2 Tx | 38.1% (+6.9%) | 0 | 14.2 | 38.1% (+6.9%) | 0 | 14.2
FR2 RF Rx test cases | 38.521-2 Rx | 0% | 0 | 2 | 0% | 0 | 2
RF Demod/QSI test cases | 38.521-4 | 0% | 0 | 2 | 0% | 0 | 2
RRM test cases | 38.533 | 17.6% (+17.6%) | 0 | 5 | 17.6% (+17.6%) | 0 | 5
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 27.5% (+27.5%) |  |  | 27.5% (+27.5%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 15% (+15%) |  |  | 15% (+15%)
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5 References
[1] RP-221402 | New WID on UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - NR support for high speed train scenario in frequency range 2 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status
WI code |  | NR_HST_FR2-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to WI ‘NR_HST_FR2’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover RF, Demod and RRM conformance test specifications for NR_HST_FR2.
WP Resp: |  | Sunlin Zhu |  |  | sunlin.zhu@samsung.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2
26.8% (+9.2%)
44 (+1)
34.8 (+1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
LTE RF/RRM
LTE RAN and CN protocols
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | adding release-17 PC6 HST FR2 radio resource control information element | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-233674 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
2 |  | 38.508-1 | 4.6.4 | UE capability information elements | adding release-17 PC6 HST FR2 UE capability information element |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
3 |  | 38.508-2 | A.4 | High Speed Capabilities | adding release-17 PC6 HST FR2 capabilities | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-232238 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
4 |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT for PC6 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-2: FR2 RF test cases - Tx
5 |  | 38.521-2 Tx | 6.1 | General | adding PC6 common uplink configuration | Qualcomm | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
6 |  | 38.521-2 Tx | 6.2.1.0 | General | adding Release-17 FR2 PC6 UE Type | Qualcomm | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
7 | Y | 38.521-2 Tx | 6.2.1.1 | UE maximum output power - EIRP and TRP | adding RF requirement for Release-17 FR2 PC6 UE | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
8 | Y | 38.521-2 Tx | 6.2.1.1_1 | UE maximum output power - EIRP and TRP (Rel16 and forward) | adding RF requirement for Release-17 FR2 PC6 UE with beam correspondence side condition | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
9 | Y | 38.521-2 Tx | 6.2.1.2 | UE maximum output power - Spherical coverage | adding UE spherical coverage for power class 6 | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
10 | Y | 38.521-2 Tx | 6.2.1.2_1 | UE maximum output power - Spherical coverage (Rel16 and forward) | adding UE spherical coverage for power class 6 UE with beam correspondence side condition | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
11 | Y | 38.521-2 Tx | 6.2.2 | UE maximum output power reduction | adding Release-17 FR2 PC6 UE MPR | Huawei | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
12 | Y | 38.521-2 Tx | 6.2.3 | UE maximum output power with additional requirements | adding Release-17 FR2 PC6 UE MPR for NS_202 and NS_203 | Samsung | RAN5#101 (Nov-23) | R5-225771 R5-231665 | Harmonization with TS 38.101-2_6.2.3.3.6 & 6.2.3.4.6 Revised from: R5-224983r1. | 1 | 90% | 90% |  | 90%
13 | Y | 38.521-2 Tx | 6.3.1 | Minimum output power | adding Release-17 FR2 PC6 Minimum output power | Samsung | RAN5#101 (Nov-23) | R5-225773 R5-231667 | Harmonization with TS 38.101-2_6.3.1.3 Revised from: R5-224985r1. | 1 | 90% | 90% |  | 90%
14 | Y | 38.521-2 Tx | 6.4.2.2 | Carrier leakage | adding Release-17 FR2 PC6 Carrier leakage | Samsung | RAN5#101 (Nov-23) | R5-225774 R5-231668 | Harmonization with TS 38.101-2_6.4.2.2.7 Revised from: R5-224986r1. | 1 | 90% | 90% |  | 90%
15 | Y | 38.521-2 Tx | 6.4.2.3 | In-band emissions | adding Release-17 FR2 PC6 In-band emissions | Samsung | RAN5#101 (Nov-23) | R5-225775 R5-231669 | Harmonization with TS 38.101-2_6.4.2.3.7 Revised from: R5-224987r1. | 1 | 90% | 90% |  | 90%
16 | Y | 38.521-2 Tx | 6.2D.1.1 | UE maximum output power - EIRP and TRP for UL MIMO | adding Release-17 FR2 PC6 UE maximum output power for UL MIMO | Samsung | RAN5#101 (Nov-23) | R5-225772 R5-231666 | Harmonization with TS 38.101-2_6.2D.1.6 Revised from: R5-224984r1. | 1 | 90% | 90% |  | 90%
17 | Y | 38.521-2 Tx | 6.2D.1.2 | UE maximum output power - Spherical coverage for UL MIMO | adding Release-17 FR2 PC6 UE spherical coverage for UL MIMO | SGS Wireless | RAN5#101 (Nov-23) | R5-232515 | Measurement Uncertainties and Test Tolerances are FFS for power class 1, 2 , 4, 5 and 56. The test case is incomplete for band n259. | 1 | 90% (+90%) | 90% (+90%) |  | 90%
18 | Y | 38.521-2 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | adding Release-17 FR2 PC6 UE maximum output power reduction for modulation / channel bandwidth for UL MIMO | Qualcomm | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
19 | Y | 38.521-2 Tx | 6.2D.3 | UE maximum output power with additional requirements for UL MIMO | adding Release-17 FR2 PC6 UE maximum output power with additional requirements for UL MIMO | Qualcomm | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
20 | Y | 38.521-2 Tx | 6.3D.1 | Minimum output power for UL MIMO | adding Release-17 FR2 PC6 Minimum output power for UL MIMO | SGS Wireless | RAN5#101 (Nov-23) | R5-232516 | Measurement Uncertainty and Test Tolerances are FFS. - OTA test procedure for UL MIMO is still under investigation - TP analysis is FFS. | 0.1 | 90% (+90%) | 90% (+90%) |  | 90%
21 | Y | 38.521-2 Tx | 6.6 | Beam correspondence | adding Release-17 FR2 PC6 Beam correspondence | Qualcomm | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
22 | Y | 38.521-2 Tx | Multi places | Multi sections | Checking all test cases and adding PC6 to configuration tables where 'inner full configuration' is used for testing | Qualcomm | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-2: FR2 RF test cases - Rx
23 | Y | 38.521-2 Rx | 7.3.2 | Reference sensitivity power level | adding Release-17 FR2 PC6 Reference sensitivity power level | SGS Wireless | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
24 | Y | 38.521-2 Rx | 7.3.4 | EIS spherical coverage | adding Release-17 FR2 PC6 EIS spherical coverage | SGS Wireless | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-4: Demod/QSI reporting test cases
25 | Y | 38.521-4 | 4.5.3.2 | Noc for NR operating bands in FR2 | add Noc power level for power class 6 UE | SGS Wireless | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
26 | Y | 38.521-4 | 7.2.2.2.4 | Minimum requirements for HST-DPS | add Minimum requirements for HST-DPS |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
27 |  | 38.521-4 | B.3.4 | FR2 HST-DPS Channel Profile | add new sub-title and introduction for the FR2 HST-DPS Channel Profile |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
28 |  | 38.521-4 | B3.4.1 | Unidirectional Deployment Channel Profile | add Unidirectional Deployment Channel Profile for HST FR2 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
29 |  | 38.521-4 | B3.4.2 | Bidirectional Deployment Channel Profile | add Bidirectional Deployment Channel Profile for HST FR2 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
30 |  | 38.522 | 4 | Test case conditions and selection criteria | Adding Test case conditions and selection criteria | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-233506 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
31 |  | 38.522 | 4.1.2 | FR2 standalone conformance test cases | Adding applicability for test cases in 38.521-2 | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
32 |  | 38.522 | 4.1.4 | Performance conformance test cases | Adding applicability for test cases in 38.521-4 | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
33 |  | 38.522 | 4.2 | RRM conformance test cases | Adding applicability for test cases in 38.533 | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-233506 |  | 1 | 10% (+10%) | 10% (+10%) |  | 10%
TS 38.533: RRM test cases
34 |  | 38.533 | 7.1.1.0.1 | Minimum conformance requirements for intra-frequency cell re-selection | update minimum conformance requirements for intra-frequency cell re-selection | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0%
35 | Y | 38.533 | 7.1.1.7 | Cell reselection to FR2 intra-frequency NR case for FR2 power class 6 UE configured with highSpeedMeasFlagFR2-r17 | This test is to verify the requirement for the intra frequency NR cell reselection requirements specified in clause 4.2.2.3 for FR2 power class 6 UE configured with highSpeedMeasFlagFR2-r17. | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
36 | Y | 38.533 | 7.4.1.1 | NR UE Transmit Timing Test for FR2 | The purpose of this test is to verify that the UE can follow frame timing change of the connected gNodeb and that the UE initial transmit timing accuracy, maximum amount of timing change in one adjustment, minimum and maximum adjustment rate are within the specified limits. | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
37 |  | 38.533 | 7.5.8 | Active TCI state switch delay | add sub-title |  | RAN5#101 (Nov-23) |  |  |  | 100% (+100%) | 100% (+100%) |  | 100%
38 |  | 38.533 | 7.5.8.3 | MAC-CE based active TCI state switch for HST FR2 scenario | add sub-title |  | RAN5#101 (Nov-23) |  |  |  | 100% (+100%) | 100% (+100%) |  | 100%
39 | Y | 38.533 | 7.5.8.3.1 | NR PCell FR2 HST active TCI state switch for a known TCI state | The purpose of this test is to verify the active TCI state switch delay requirement for FR2 power class 6 UE. | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-233507 | - Test tolerance and measurement uncertainty analysis are missing | 1 | 90% (+90%) | 90% (+90%) |  | 90%
40 | Y | 38.533 | 7.6.1.5 | NR SA event triggered reporting test without gap under non-DRX for UE configured with highSpeedMeasCA-Scell-r17 | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the TDD intra-frequency cell search requirements for FR2 power class 6 UE configured with highSpeedMeasFlagFR2-r17 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
41 | Y | 38.533 | 7.6.3.5 | SSB based L1-RSRP measurement when DRX is used for power class 6 UE configured with highSpeedMeasFlagFR2-r17 | The purpose of this test is to verify that the power class 6 UE makes correct reporting of L1-RSRP measurement when highSpeedMeasFlagFR2-r17 is configured. This test will partly verify the L1-RSRP measurement requirements for power class 6 UE configured with highSpeedMeasFlagFR2-r17 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
42 |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases | SAMSUNG | RAN5#101 (Nov-23) | R5-233633 |  | 1 | 30% (+30%) | 30% (+30%) |  | 30%
43 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | TT analysis for RRM Test cases |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
44 |  | 38.905 |  | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 |  | RAN5#101 (Nov-23) |  |  | 1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.