## Cover sheet
3GPP TSG-RAN WG5 Meeting #99 | [10 empty] | R5-233769
Incheon, Korea (Republic Of), 22nd May 2023 - 26th May 2023
Agenda Item: | 7.4.2
Source: | Nokia, Nokia Shanghai Bell
Title: | WP LTE-NR & NR-NR Dual Connectivity and NR CA enhancements
Work item code: | LTE_NR_DC_CA_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The technical objective of this work item is to provide conformance test specifications for the Release 16 DCCA enhancements requirements. More specifically, the WI covers the following conformance areas: Develop RRM test cases for DCCA enhancement requirements defined in RAN4; Develop MAC and RRC signaling test cases for DCCA enhancement requirements defined in RAN2;
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+2%) | 38 (-18) | 41 (-27)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 99.7% (+2.7%) | 25 (-20) | 28 (-27)
FR1 |  | 99.9% (+1.6%) | 25 (-20) | 26 (-27)
FR2 |  | 99.1% (+5.6%) | 18 (+6) | 20
FR1 + FR2 |  | 100% (+2.4%) | 4 (+2) | 4
NSA Option 3 (EN-DC) |  | 100% (+1.9%) | 9 (+2) | 9
FR1 |  | 100% (+2%) | 7 (+1) | 7
FR2 |  | 100% (+2%) | 7 (+1) | 7
FR1 + FR2 |  | 100% (+0.7%) | 1 | 1
NSA Option 4 (NE-DC) |  | 100% (+0.2%) | 4 | 4
FR1 |  | 100% (+0.2%) | 4 | 4
FR2 |  | 100% (+0.2%) | 4 | 4
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | NSA Option 4 (NE-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+3.7%) |  |  | 100% (+2.5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%)
Common ICS | 38.508-2 | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%)
UE specific test functions | 38.509
NR RF/RRM
RF test cases | 38.521-1 | 100% | 4 (-27) | 4 (-27) | 100% | 4 (-27) | 4 (-27)
RRM test cases | 38.533 | 98% (+20.3%) | 7 (+3) | 10 | 98.8% (+13.8%) | 3 (+1) | 4 | 95% (+45%) | 0 | 2 |  |  |  | 100% (+5%) | 2 (+1) | 2 | 100% (+5%) | 2 (+1) | 2
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% |  |  | 100% |  |  | 100% | [5 empty] | 100% |  |  | 100%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 59.4% (+22%) |  |  | 75% (+25%) |  |  | 0% | [5 empty] | 100% (+50%) |  |  | 100% (+50%)
Test point analysis | 38.905 | 100% (+62.6%) |  |  | 100% (+50%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% (+1.4%) | 27 (+6) | 27 | 100% (+1.7%) | 18 (+6) | 18 | 100% (+1.7%) | 18 (+6) | 18 | 100% (+2.5%) | 4 (+2) | 4 | 100% | 5 | 5 | 100% | 5 | 5 | 100% | 1 | 1 | 100% | 4 | 4 | 100% | 4 | 4
Applicability Protocol test cases | 38.523-2 | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-222021 | UE Conformance Test Aspects - LTE-NR & NR-NR Dual Connectivity and NR CA enhancements
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP LTE-NR & NR-NR Dual Connectivity and NR CA enhancements | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status
WI code |  | LTE_NR_DC_CA_enh-UEConTest
WP Scope: |  | <WP Scope description> | [14 empty] | vs Area
WP Resp: |  | Matti Kangas |  |  | matti.kangas@nokia.com | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | NSA Option 4 (NE-DC)
TS Resp: |  | - |  |  | -
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | NSA Option 4 (NE-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[14 empty] | Overall |  | 99.9% (+1.6%) | 99.1% (+5.6%) | 100% (+2.4%) | 100% (+2%) | 100% (+2%) | 100% (+0.7%) | 100% (+0.2%) | 100% (+0.2%)
[14 empty] | Number of WP items |  | 63 (+1) | 27 (+1) | 8 | 14 (+1) | 14 (+1) | 5 | 9 | 9 | 1
[14 empty] | Sum weight of WP items |  | 54 (+0.1) | 20.7 (+0.1) | 4.4 | 7.7 (+0.1) | 7.7 (+0.1) | 1.4 | 4.4 | 4.4 | 0
[14 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
52 |  | 38.508-1 | 4.3.1.1.7 | Definition of common test environment for DCCA testing | Introduce NR-DC configurations clause 4.3.1.1.7, add DC_n48A-n70A. Update A.3.1.1 to cover NR-DC. Addition of SIB11 to common environment for early measurements. Modification of SIB1 in common environment for idle/inactive measurements. | Nokia, Nokia Shanghai Bell | RAN5#97 (Nov-22) | R5-222308, R5-223755, R5-223400, R5-223399 |  | 0.1 | 100% (+5%) | 100% (+5%) | 100% (+5%) | 100% (+5%) |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
109 |  | 38.508-1 | 6.2.3.6 | Test frequencies for NR-DC signalling testing | Introduce NR DC in FR1 into test frequencies for NR DC configurations for signalling testing. | Nokia, Nokia Shanghai Bell | RAN5#97 (Nov-22) | R5-224179 |  | 0.1 | 100% | 100% |  |  |  | 100%
TS 38.508-2: Common ICS
53 |  | 38.508-2 | A.4.3.6, A.4.3.5 | Definition of test capabilities for DCCA testing | Addition of Measurement Capabilities for Idle/Inactive measurements testcase Addition of direct SCG SCell activation capability | Nokia, Nokia Shanghai Bell, TDIA, CATT, Lenovo, Motorola Mobility | RAN5#97 (Nov-22) | R5-223401, R5-224178, R5-227475, R5-227549 |  | 0.1 | 100% (+5%) | 100% (+5%) | 100% (+5%) | 100% (+5%) |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
NR RF/RRM
TS 38.521-1: RF test cases
110 |  | 38.521-1 | 3.2 | Symbols | Add inter-band NR-DC operation to the symbols clause. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-224167 |  | 1 | 100% | 100% |  |  |  | 100%
77 |  | 38.521-1 | 5.5B | Configurations for NR-DC | Add configuration DC_n48A-n70A. Add clarifying note to Configurations for inter-band CA (two bands) in clause 5.5A.3.1. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223769 |  | 1 | 100% | 100% |  |  |  | 100%
78 |  | 38.521-1 | 6.2B | Transmitter power for NR-DC | New clause for NR-DC | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222310 |  | 1 | 100% | 100% |  |  |  | 100%
79 |  | 38.521-1 | 6.2B.0 | General | Add requirement for NR-DC | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222310 |  | 1 | 100% | 100% |  |  |  | 100%
80 | Y | 38.521-1 | 6.2B.1.1 | UE maximum output power for NR-DC | Add requirement for DC_n48A-n70A | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222310 |  | 1 | 100% | 100% |  |  |  | 100%
81 | Y | 38.521-1 | 6.2B.2.1 | UE maximum output power reduction for NR-DC | Add requirement for NR-DC | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222311, R5-225950 |  | 1 | 100% | 100% |  |  |  | 100%
82 | Y | 38.521-1 | 6.2B.3.1 | UE additional maximum output power reduction for NR-DC | Add requirement for NR-DC | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-222312 |  | 1 | 100% | 100% |  |  |  | 100%
83 | Y | 38.521-1 | 6.2B.4.1 | Configured output power for NR-DC | Add requirements to Configured transmitted power level for NR-DC and ΔTIB,c for NR-DC configuration DC_n48-n70 | Nokia, Nokia Shanghai Bell, CAICT | RAN5#96 (Aug-22) | R5-222313, R5-227730 |  | 1 | 100% | 100% |  |  |  | 100%
96 |  | 38.521-1 | 6.3B.1 | Minimum output power for NR-DC | Add NR-DC Minimum output power in clause 6.3B.1 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223756 |  | 1 | 100% | 100% |  |  |  | 100%
97 |  | 38.521-1 | 6.3B.2 | Transmit OFF power for NR-DC | Add NR-DC clause 6.3B.2 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223757 |  | 1 | 100% | 100% |  |  |  | 100%
98 |  | 38.521-1 | 6.3B.3 | Transmit ON/OFF time mask for NR-DC | Add NR-DC clause 6.3B.3 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223758 |  | 1 | 100% | 100% |  |  |  | 100%
84 |  | 38.521-1 | 6.3B | Output power dynamics for NR-DC | Add reference to requirements clause 6.3A | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223756 |  | 1 | 100% | 100% |  |  |  | 100%
99 |  | 38.521-1 | 6.4B.1 | Frequency error for NR-DC | Add NR-DC Frequency error in clause 6.4B.1 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223759 |  | 1 | 100% | 100% |  |  |  | 100%
100 |  | 38.521-1 | 6.4B.2 6.4B.2.1 | Transmit modulation quality for NR-DC | Add NR-DC clause 6.4B.2. Add NR-DC Error Vector Magnitude in clause 6.4B.2.1 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223760 |  | 1 | 100% | 100% |  |  |  | 100%
101 |  | 38.521-1 | 6.4B.2.2 | Carrier leakage for NR-DC | Add NR-DC clause 6.4B.2.2 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223761 |  | 1 | 100% | 100% |  |  |  | 100%
102 |  | 38.521-1 | 6.4B.2.3 | In-band emissions for NR-DC | Add NR-DC clause 6.4B.2.3 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223762 |  | 1 | 100% | 100% |  |  |  | 100%
85 |  | 38.521-1 | 6.4B | Transmit signal quality for NR-DC | Add refernce to requirements clause 6.4A | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223759 |  | 1 | 100% | 100% |  |  |  | 100%
111 |  | 38.521-1 | 6.5A.3.2 | Inter-band spurious emission for UE co-existence | Include spurious emission and test configurations. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223766, R5-224169. R5-224170 |  | 1 | 100% | 100% |  |  |  | 100%
103 |  | 38.521-1 | 6.5B.1 | Output RF spectrum emissions for NR-DC | Add NR-DC Occupied bandwidth in clause 6.5B.1 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223763 |  | 1 | 100% | 100% |  |  |  | 100%
104 |  | 38.521-1 | 6.5B.2 6.5B.2.2 | Out of band emission for NR-DC | Add NR-DC clause 6.5B.2. Add NR-DC Spectrum emission mask in clause 6.5B.2.2 | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223764 |  | 1 | 100% | 100% |  |  |  | 100%
105 |  | 38.521-1 | 6.5B.2.4.1.0.3 6.5B.2.4.1.1 6.5B.2.4.2 | NR ACLR for Inter-band NR-DC NR ACLR for NR-DC UTRA ACLR | Add NR-DC clause 6.5B.2.4. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223765 |  | 1 | 100% | 100% |  |  |  | 100%
106 |  | 38.521-1 | 6.5B.3 | Spurious emission for NR-DC | Add NR-DC for clause 6.5B.3. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223766 |  | 1 | 100% | 100% |  |  |  | 100%
107 |  | 38.521-1 | 6.5B.4 | Transmit intermodulation for NR-DC | Add NR-DC for clause 6.5B.4. | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223767 |  | 1 | 100% | 100% |  |  |  | 100%
86 |  | 38.521-1 | 6.5B | Output RF spectrum emissions for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-223763 |  | 1 | 100% | 100% |  |  |  | 100%
87 |  | 38.521-1 | 7.3B | Reference sensitivity for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-224171 |  | 1 | 100% | 100% |  |  |  | 100%
88 |  | 38.521-1 | 7.4B | Maximum input level for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-224172 |  | 1 | 100% | 100% |  |  |  | 100%
89 |  | 38.521-1 | 7.5B | Adjacent channel selectivity for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-224173 |  | 1 | 100% | 100% |  |  |  | 100%
90 |  | 38.521-1 | 7.6B | Blocking characteristics for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-224174 |  | 1 | 100% | 100% |  |  |  | 100%
91 |  | 38.521-1 | 7.7B | Spurious response for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-224175 |  | 1 | 100% | 100% |  |  |  | 100%
92 |  | 38.521-1 | 7.8B | Intermodulation characteristics for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-224176 |  | 1 | 100% | 100% |  |  |  | 100%
93 |  | 38.521-1 | 7.9B | Spurious emissions for NR-DC | Add refernce to requirements clause | Nokia, Nokia Shanghai Bell | RAN5#96 (Aug-22) | R5-224177 |  | 1 | 100% | 100% |  |  |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
1 |  | 38.522 | 4.0 | Test case conditions and selection criteria | Add new ICS statements. | Nokia, Nokia Shanghai Bell, Ericsson | RAN5#97 (Nov-22) | R5-225949, R5-233686 |  | 0.1 | 100% | 100% | 100% (+100%) |  |  | 100% | 100% |  | 100% | 100%
108 |  | 38.522 | 4.1.1 | RF conformance test cases | Add testcase applicability statements for the new test cases introduced for 38.521-1 | Nokia, Nokia Shanghai Bell | RAN5#97 (Nov-22) | R5-225949 |  | 0.1 | 100% | 100% |  |  |  | 100%
2 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. | Nokia, Nokia Shanghai Bell, Ericsson | RAN5#97 (Nov-22) | R5-221296, R5-231806, R5-233686 |  | 0.1 | 100% | 100% | 100% |  |  | 100% | 100% |  | 100% | 100%
TS 38.533: RRM test cases
|  | 38.533 | 8.2.2 | E-UTRA – NR Inter-RAT Early Measurement Reporting | New sub-clause header
94 | Y | 38.533 | 8.2.2.1 | E-UTRA – NR FR1 Early Measurement Reporting | Test Purpose(s): Early measurements of E-UTRA serving cell and NR carrier at FR1, RSRP and RSRQ measurement accuracy. TS: 38.133 A.8.2.2.1, TS: 36.133 4.9.2.4, 9.11.1A, 9.11.2A, 9.1.2B and 9.1.5B | Ericsson | RAN5#96 (Aug-22) | R5-225154, R5-231144 |  | 1 | 100% |  | 100% | [5 empty] | 100%
95 | Y | 38.533 | 8.2.2.2 | E-UTRA – NR FR2 Early Measurement Reporting | Test Purpose(s): Early measurements of E-UTRA serving cell and NR carrier at FR2, RSRP and RSRQ measurement accuracy. TS: 38.133 A.8.2.2.2, TS: 36.133 4.9.2.4, 9.11.1A, 9.11.2A, 9.1.2B and 9.1.5B | Ericsson | RAN5#96 (Aug-22) | R5-225748, R5-231744 |  | 1 | 100% |  | 100% | [6 empty] | 100%
|  | 38.533 | 6.6.9 | Idle Mode CA/DC Measurements | New sub-clause header
75 | Y | 38.533 | 6.6.9.1 | NR SA FR1 SA Idle mode CA/DC measurement for FR1 | Test Purpose(s): Early measurements of NR serving cell and NR inter frequency carrier both at FR1, RSRP and RSRQ measurement accuracy. TS:38.133 4.4, 10.1.4B, 10.1.9B, A.6.6.9 | Ericsson | RAN5#96 (Aug-22) | R5-221301, R5-225152, R5-231223 |  | 1 | 100% | 100% |  |  |  | 100%
|  | 38.533 | 6.6.15 | Idle Mode inter-RAT CA/DC Measurements | New sub-clause header
76 | Y | 38.533 | 6.6.15.1 | NR SA FR1 Idle Mode measurements of inter-RAT CA candidate cells for early reporting | Test Purpose(s): Early measurement of NR serving cell at FR1 and inter RAT carrier, RSRP and RSRQ measurement accuracy. TS:38.133 4.4, 10.1.2B, 10.1.7B, 10.2.4, 10.2.5, A.6.6.15 | Ericsson | RAN5#96 (Aug-22) | R5-221302, R5-225153, R5-231743 |  | 1 | 100% | 100% |  |  |  | 100%
23 | Y | 38.533 | 4.5.3.5 | Direct SCell activation at SCell addition of known SCell in FR1 | Test Purpose(s): The purpose of this test is to verify that the direct SCell activation time is within the requirements, when the SCell in FR1 is known by the UE at the time of activation. TS: 38.133 8.2.1.2.8, 8.3.4, A.4.5.3.5 | Nokia, Nokia Shanghai Bell | RAN5#99 (May-23) | R5-231726, R5-233747 | RAN5#99 post meeting: R4 approved R4-2307240 => R5-233747 approved RAN5#99: Depending on RAN4 TDoc R4-2307240 5/23 Moderator (E///): Can be agreed once RAN4 dependency is cleared. | 1 | 100% (+10%) |  | 100% (+10%) | [5 empty] | 100%
24 | Y | 38.533 | 5.5.3.7 | Direct SCell activation at SCell addition of known SCell in FR2 | Test Purpose(s): The purpose of this test case is the same as for the test defined in testcase 4.5.3.5 except the SCell is in FR2 intra-band. TS: 38.133 8.2.1.2.8, 8.3.4, A.5.5.3.7 | Nokia, Nokia Shanghai Bell | RAN5#99 (May-23) | R5-231727 |  | 1 | 100% (+10%) |  | 100% (+10%) | [6 empty] | 100%
25 | Y | 38.533 | 6.5.3.4 | Direct SCell activation at SCell addition of known SCell in FR1 | Test Purpose(s): The purpose of this test is to verify fulfillment of direct SCell activation delay and interruption requirements at SCell addition. TS: 38.133 8.2.2, 8.3.4, A.6.5.3.4 | Nokia, Nokia Shanghai Bell | RAN5#99 (May-23) | R5-231728, R5-233748 | RAN5#99 post meeting: R4 approved R4-2307240 => R5-233748 approved RAN5#99: Depending on RAN4 TDoc R4-2307240 5/23 Moderator (E///): Can be agreed once RAN4 dependency is cleared | 1 | 100% (+10%) | 100% (+10%) |  |  |  | 100%
68 | Y | 38.533 | 6.5.3.5 | Direct SCell activation at handover with known SCell in FR1 | Test purpose(s): This test is to verify the requirement for the FDD-FDD and TDD-TDD intra frequency handover with direct SCell activation requirements. TS: 38.133 8.2.2., 8.3.5, A.6.5.3.5 | Nokia, Nokia Shanghai Bell | RAN5#99 (May-23) | R5-231729, R5-233749 | TT analysis pending due to RAN5 discussion about UE noise cancellation. Will be provided through TEI as soon as RAN5 agrees upon this RAN5#99 post meeting: R4 approved R4-2307240 => R5-233749 approved RAN5#99: Depending on RAN4 TDoc R4-2307240 5/23 Moderator (E///): Can be agreed once RAN4 dependency is cleared | 1 | 95% (+45%) | 95% (+45%) |  |  |  | 95%
26 | Y | 38.533 | 7.5.3.4 | Direct SCell activation at SCell addition of known SCell in FR2 | Test Purpose(s): The purpose of this test is to verify that the delay and interruption for direct SCell activation delay at SCell addition are within the requirements. TS: 38.133 8.2.2, 8.3.4, A.7.5.3.4 | Nokia, Nokia Shanghai Bell | RAN5#99 (May-23) | R5-231730, R5-233605 | TT analysis pending due to RAN5 discussion about UE noise cancellation. Will be provided through TEI as soon as RAN5 agrees upon this | 1 | 95% (+45%) | 95% (+45%) |  |  |  |  | 95%
69 | Y | 38.533 | 7.5.3.5 | Direct SCell activation at handover with known SCell in FR2 | Test Purpose(s): This test is to verify the requirements for the FR2 handover with direct SCell activation. TS: 38.133 8.2.2, 8.3.5, A.7.5.3.5 | Nokia, Nokia Shanghai Bell | RAN5#99 (May-23) | R5-231731, R5-233604 | TT analysis pending due to RAN5 discussion about UE noise cancellation. Will be provided through TEI as soon as RAN5 agrees upon this | 1 | 95% (+45%) | 95% (+45%) |  |  |  |  | 95%
|  | 38.533 | Void | SCell dormancy switch | New subclause header | Void
28 |  | 38.533 | Void | E-UTRAN – NR FR1 PSCell SCell dormancy switch of single FR1 SCell outside active time | Test Purpose(s): The purpose of this test is to verify the DL BWP switch delay requirement on multiple CCs for RRC-based BWP switch. TS: 38.133 8.2.1, 8.6, A.4.5.6.5.1 | Void |  |  | No industry interest was shown on Scell dormancy. | 0
29 |  | 38.533 | Void | E-UTRAN – NR FR1 PSCell SCell dormancy switch of two FR1 SCells inside active time | Test Purpose(s): The purpose of this test is to verify the delay requirement of BWP switching from dormancy to non-dormancy and from non-dormancy to dormancy on SCell and interruption requirements for NR victim cell and interruption requirement for E-UTRA victim. TS: 38.133 8.2.1, 8.6, A.4.5.6.5.2 TS: 36.133 7.32.2.7 | Void |  |  | No industry interest was shown on Scell dormancy. | 0
|  | 38.533 | Void | SCell dormancy switch | New subclause header | Void
30 |  | 38.533 | Void | E-UTRAN – NR FR2 PSCell SCell dormancy switch of single FR2 SCell inside active time | Test Purpose(s): The purpose of this test is to verify the interruption due to RRM and CSI measurement during SCell dormancy on spCell is within the limits for NR victim cell, the SCell dormancy switch delay is within the requirement and the SCell dormancy switch interruption is within the limits for NR victim cell. TS: 38.133 8.2.1, 8.6, A.5.5.6.4.1 | Void |  |  | No industry interest was shown on Scell dormancy. | 0
31 |  | 38.533 | Void | E-UTRAN – NR FR1 PSCell SCell dormancy switch of two FR2 SCells outside active time | Test Purpose(s): The purpose of this test is to verify the NR SCell dormant BWP switch delay requirements, interruption requirements due to the NR SCell dormant BWP switch for NR victim cells and for E-UTRA victim cell, interruption requirements due to CSI and RRM measurements on the NR dormant SCells, NR victim cells and E-UTRA victim cell. TS: 38.133 8.2.1, 8.6, A.5.5.6.4.2 | Void |  |  | No industry interest was shown on Scell dormancy. | 0
|  | 38.533 | Void | SCell dormancy switch | New subclause header | Void
32 |  | 38.533 | Void | NR FR1 PCell SCell dormancy switch of single FR1 SCell outside active time | Test Purpose(s): The purpose of this test is to verify the SCell dormancy switch delay requirements when the UE is triggered to switch between dormancy to non-dormancy and non-dormancy to dormancy outside the DRX active time. Further the test purpose is to verify the interruption rate on other serving cells when the UE performing CSI and RRM measurements on dormant SCell(s) and also to verify the interruption requirement on other active serving cell. TS: 38.133 8.2.2, 8.6, A.6.5.6.4.1 | Void |  |  | No industry interest was shown on Scell dormancy. | 0
33 |  | 38.533 | Void | NR FR1 PCell SCell dormancy switch of two FR1 SCells inside active time | Test Purpose(s): The purpose of this test is to verify fulfillment of SCell dormancy switching delay requirements, requirements on interruptions due to SCell dormancy switching and requirements on interruptions due to CSI and RRM measurements on dormant SCells. TS: 38.133 8.2.2, 8.6, A.6.5.6.4.2 | Void |  |  | No industry interest was shown on Scell dormancy. | 0
|  | 38.533 | Void | SCell dormancy switch | New subclause header | Void
34 |  | 38.533 | Void | NR FR2 PCell SCell dormancy switch of single FR2 SCell inside active time | Test Purpose(s): The purpose of this test is to verify that the Dormant SCell BWP switch delay requirements are within the requirements for UE configured with a single downlink SCell, when the dormancy indication is received in any of the first 3 OFDM symbols or is received after the first 3 OFDM symbols. TS: 38.133 8.2.2, 8.6, A.7.5.6.4.1 | Void |  |  | No industry interest was shown on Scell dormancy. | 0
35 |  | 38.533 | Void | NR FR1 PCell SCell dormancy switch of two FR2 SCells outside active time | Test Purpose(s): The purpose of this test is to verify fulfillment of SCell dormancy switching delay requirements when the UE is triggered to switch between non-dormancy and dormancy outside DRX active time. TS: 38.133 8.2.2, 8.6, A.7.5.6.4.2 | Void |  |  | No industry interest was shown on Scell dormancy. | 0
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
55 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | Define TT and MU for the RRM testcases | Nokia, Nokia Shanghai Bell, Ericsson | RAN5#99 (May-23) | R5-231147, R5-231148, R5-231745, R5-233653, R5-233750 | TT analysis pending for TC 6.5.3.5, 7.5.3.4 and 7.5.3.5. See TC comments for further info RAN5#99 post meeting: R4 approved R4-2307240 => R5-233750 approved RAN5#99: Depending on RAN4 TDoc R4-2307240 5/23 Moderator (E///): Can be agreed once RAN4 dependency is cleared | 0.1 | 68.8% (+31.2%) | 37.5% (+12.5%) | 100% (+50%) |  |  | 75% | 0% |  | 100% | 100%
TR 38.905: Test point analysis
115 |  | 38.905 | 4.1.3.2 | Test point (TP) analysis for A-MPR | For each two band UL NR-DC inter-band configuration perform UE-coexistence spurious emission TP analysis as described in TR 38.905. Document the TP analysis by a CR to TR 38.905 including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. | Nokia, Nokia Shanghai Bell | RAN5#96-e (Aug-22) | R5-225749 | Spurious emission TPA for corresponding configuration CA_n48A-n70A | 0.1 | 100% (+62.5%) | 100% (+75%) |  |  |  | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Layer 2
36 |  | 38.523-1 | Void | Dormant Bandwidth Part (BWP) operation UL/DL | Test Purpose(s): SCell having dormant BWP, BWP switching | Void |  |  | No industry interest was shown on Scell dormancy. | 0
RRC
|  | 38.523-1 | 8.1.5.11 | Idle/Inactive Measurements | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0
37 | Y | 38.523-1 | 8.1.5.11.1 | Idle/Inactive Measurements / Idle mode / SIB11 configuration / Measurement of NR cells | Test Purpose(s): NR-NR Early measurement reporting, Idle mode, Measurement configuration through SIB11, measurement of NR cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-217952, R5-223407, R5-227550 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
38 | Y | 38.523-1 | 8.1.5.11.2 | Idle/Inactive Measurements / Idle mode / RRCRelease configuration / Measurement of NR cells | Test Purpose(s): NR-NR Early measurement reporting, Idle mode, Measurement configuration through RRCRelease message, measurement of NR cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-217776, R5-223403, R5-227551 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
39 | Y | 38.523-1 | 8.1.5.11.3 | Idle/Inactive Measurements / Inactive mode / SIB11 configuration / Measurement of NR cells | Test Purpose(s): NR-NR Early measurement reporting, Inactive mode, Measurement configuration through SIB11, measurement of NR cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-222003, R5-223405, R5-227552, R5-232729 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
40 | Y | 38.523-1 | 8.1.5.11.4 | Idle/Inactive Measurements / Inactive mode / RRCRelease configuration / Measurement of NR cells | Test Purpose(s): NR-NR Early measurement reporting, Inactive mode, Measurement configuration through RRCRelease message, measurement of NR cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-222005, R5-223406, R5-227553, R5-232730 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
|  | 38.523-1 | 8.2.6.3 | Idle/Inactive Measurements | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0
41 | Y | 38.523-1 | 8.2.6.3.1 | Idle/Inactive Measurements / Idle mode / EN-DC / SIB5 & SIB24 configuration | Test Purpose(s): LTE-NR Early measurement reporting, Idle mode, Measurement configuration through LTE SIB5 and LTE SIB24. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#95 (May-22) | R5-227554, R5-231584, R5-232197 |  | 1 | 100% |  | 100% | [5 empty] | 100% | 100%
42 | Y | 38.523-1 | 8.2.6.3.2 | Idle/Inactive Measurements / Idle mode / EN-DC / RRCConnectionRelease configuration | Test Purpose(s): LTE-NR Early measurement reporting, Idle mode, Measurement configuration through RRCConnectionRelease. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#95 (May-22) | R5-227555, R5-231585, R5-233455 |  | 1 | 100% |  | 100% | [5 empty] | 100% | 100%
73 | Y | 38.523-1 | 8.2.6.3.3 | Idle/Inactive Measurements / Inactive mode / NE-DC / SIB11 configuration | Test Purpose(s): NR-LTE Early measurement reporting, Inactive mode, Measurement configuration through SIB11, measurement of E-UTRA cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-222004, R5-227556 |  | 1 | 100% |  |  | 100% | [7 empty] | 100% | 100%
74 | Y | 38.523-1 | 8.2.6.3.4 | Idle/Inactive Measurements / Inactive mode / NE-DC / RRCRelease configuration | Test Purpose(s): NR-LTE Early measurement reporting, Inactive mode, Measurement configuration through RRCRelease message, measurement of E-UTRA cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-222006, R5-227557 |  | 1 | 100% |  |  | 100% | [7 empty] | 100% | 100%
71 | Y | 38.523-1 | 8.2.6.3.5 | Idle/Inactive measurements / Idle mode / NE-DC / SIB11 configuration | Test Purpose(s): NR-LTE Early measurement reporting, Idle mode, Measurement configuration through SIB11, measurement of E-UTRA cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-217775, R5-223402, R5-227558 |  | 1 | 100% |  |  | 100% | [7 empty] | 100% | 100%
72 | Y | 38.523-1 | 8.2.6.3.6 | Idle/Inactive measurements / Idle mode / NE-DC / RRCRelease configuration | Test Purpose(s): NR-LTE Early measurement reporting, Idle mode, Measurement configuration through RRCRelease message, measurement of E-UTRA cells. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) | R5-217777, R5-223404, R5-227559 |  | 1 | 100% |  |  | 100% | [7 empty] | 100% | 100%
43 | Y | 38.523-1 | 8.1.1.4.4 | RRC resume / Suspend-Resume / RRC reconfiguration / Active MCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell while resuming from inactive state after receiving RRCResume message. Intra-band contiguous carriers. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214390, R5-225199, R5-227561, R5-230094 | TF160 - SCell activation must be checked with data loopback (Ericsson agreed to make this update in the next meeting). This was updated during the RAN5#98. | 1 | 100% (+5%) | 100% (+5%) |  |  |  | 100% | 100%
64 | Y | 38.523-1 | 8.1.1.4.5 | RRC resume / Suspend-Resume / RRC reconfiguration / Active MCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell while resuming from inactive state after receiving RRCResume message. Intra-band non-contiguous carriers. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214391 |  | 1 | 100% (+5%) | 100% (+5%) |  |  |  | 100% | 100%
65 | Y | 38.523-1 | 8.1.1.4.6 | RRC resume / Suspend-Resume / RRC reconfiguration / Active MCG SCell addition / Inter-band CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell while resuming from inactive state after receiving RRCResume message. Inter-band carriers. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214392 |  | 1 | 100% (+5%) | 100% (+5%) |  |  |  | 100% | 100% | 100%
44 | Y | 38.523-1 | 8.1.1.4.7 | RRC resume / Suspend-Resume / RRC reconfiguration / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCResume message. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214433, R5-225200, R5-226313, R5-230095, R5-233482 | TF160 - SCell activation must be checked with data loopback (Ericsson agreed to make this update in the next meeting). These testcases need to be changed to use RRCReconfiguration instead of RRCSetup. | 1 | 100% (+5%) | 100% (+5%) |  |  |  | 100% | 100%
66 | Y | 38.523-1 | 8.1.1.4.8 | RRC resume / Suspend-Resume / RRC reconfiguration / Active SCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCResume message. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214434, R5-232317 | TF160 - SCell activation must be checked with data loopback (Ericsson agreed to make this update in the next meeting). These testcases need to be changed to use RRCReconfiguration instead of RRCSetup. | 1 | 100% (+5%) | 100% (+5%) |  |  |  | 100% | 100%
67 | Y | 38.523-1 | 8.1.1.4.9 | RRC resume / Suspend-Resume / RRC reconfiguration / Active SCG SCell addition / Inter-band CA | Test Purpose(s): NR-CA Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCResume message. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#96 (Aug-22) | R5-214435, R5-233483 | TF160 - SCell activation must be checked with data loopback (Ericsson agreed to make this update in the next meeting). These testcases need to be changed to use RRCReconfiguration instead of RRCSetup. | 1 | 100% (+5%) | 100% (+5%) |  |  |  | 100% | 100% | 100%
|  | 38.523-1 | 8.2.7 | RRC resume | New sub-clause header |  | RAN5#97 (Nov-22) |  |  | 0
|  | 38.523-1 | 8.2.7.1 | RRC resume / EN-DC | New sub-clause header |  | RAN5#97 (Nov-22) |  |  | 0
|  | 38.523-1 | 8.2.7.2 | RRC resume / NR-DC
112 | Y | 38.523-1 | 8.2.7.2.1 | RRC resume / Suspend-Resume / RRC reconfiguration / NR-DC / Resume with SCG | Test Purpose(s): NR-DC TS:38.331 | Qualcomm | RAN5#97 (Nov-22) | R5-227435 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
46 | Y | 38.523-1 | 8.1.2.1.5.4 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active MCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#97 (Nov-22) | R5-227562 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
58 | Y | 38.523-1 | 8.1.2.1.5.5 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active MCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band non-contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#97 (Nov-22) | R5-226315 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
59 | Y | 38.523-1 | 8.1.2.1.5.6 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active MCG SCell addition / Inter-band CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Inter-band carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#97 (Nov-22) | R5-226316 |  | 1 | 100% | 100% |  |  |  | 100% | 100% | 100%
|  | 38.523-1 | 8.2.4.1.2 | NR CA / NR SCell addition / modification / release / Success / NR-DC | New sub-clause header |  | RAN5#92 (Aug-21)
47 | Y | 38.523-1 | 8.2.4.1.2.1 | NR CA / NR SCell addition / modification / release / Success / NR-DC / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-DC Direct SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Lenovo, Motorola Mobility | RAN5#96 (Aug-22) | R5-223497, R5-227565 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
60 | Y | 38.523-1 | 8.2.4.1.2.2 | NR CA / NR SCell addition / modification / release / Success / NR-DC / Active SCG SCell addition / Intra-band non-contiguous CA | Test Purpose(s): NR-DC Direct SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band non-contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Lenovo, Motorola Mobility | RAN5#96 (Aug-22) | R5-223497, R5-227565 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
61 | Y | 38.523-1 | 8.2.4.1.2.3 | NR CA / NR SCell addition / modification / release / Success / NR-DC / Active SCG SCell addition / Inter-band CA | Test Purpose(s): NR-DC Direct SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Inter-band carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Lenovo, Motorola Mobility | RAN5#96 (Aug-22) | R5-223497, R5-227565 |  | 1 | 100% | 100% |  |  |  | 100% | 100% | 100%
48 | Y | 38.523-1 | 8.2.4.1.1.4 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): MR-DC Direct NR SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRC(Connection)Reconfiguration message. Intra-band contiguous carriers. TS:36.331 5.3.5.3; TS:38.331 5.3.5.3; TS38.321 5.9 | Lenovo, Motorola Mobility | RAN5#97 (Nov-22) | R5-224929 |  | 1 | 100% |  | 100% | [5 empty] | 100% | 100%
62 | Y | 38.523-1 | 8.2.4.1.1.5 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Active SCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): MR-DC Direct NR SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRC(Connection)Reconfiguration message. Intra-band non-contiguous carriers. TS:36.331 5.3.5.3; TS:38.331 5.3.5.3; TS38.321 5.9 | Lenovo, Motorola Mobility | RAN5#97 (Nov-22) | R5-224929 |  | 1 | 100% |  | 100% | [5 empty] | 100% | 100%
63 | Y | 38.523-1 | 8.2.4.1.1.6 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Active SCG SCell addition / Inter-band CA | Test Purpose(s): MR-DC Direct NR SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRC(Connection)Reconfiguration message. Inter-band carriers. TS:36.331 5.3.5.3; TS:38.331 5.3.5.3; TS38.321 5.9 | Lenovo, Motorola Mobility | RAN5#97 (Nov-22) | R5-224929 |  | 1 | 100% |  | 100% | [5 empty] | 100% | 100% | 100%
114 | Y | 38.523-1 | 8.2.7.3.1 | RRC Resume / Suspend-Resume / RRC reconfiguration/ NE-DC / Resume with SCG | **** TP1: [TS 36,331: 5.3.5.3; TS 38,331: 5.2.2.2.2] WITH: UE in NR RRC_INACTIVE state and sends RRCResumeRequest message to resume RRC Connection WHEN: UE receives a RRCResume message including mrdc-SecondaryCellGroup set to eutra-SCG THEN: UE successfully transmits RRCResumeComplete message | ZTE | RAN5#98 (Feb-23) | R5-231576 | [13 empty] | 100% | 100% | 100%
113 | Y | 38.523-1 | 8.2.6.2.4 | Processing delay / RRC_INACTIVE / Latency check / NR-DC | Test Purpose(s): Latency check RRC Resume messages when UE in RRC_INACTIVE state. TS:38.331: 5.3.13.4, Clause 12 | Qualcomm | RAN5#98 (Feb-23) | R5-231460 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
49 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add new ICS statements. | Nokia, Nokia Shanghai Bell, Ericsson, Lenovo, Motorola Mobility | RAN5#97 (Nov-22) | R5-216333, R5-216334, R5-217953, R5-222002, R5-223408, R5-223409, R5-225322, R5-227564, R5-227563, R5-227474, R5-231465, R5-231485, R5-233484 |  | 0.1 | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
50 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | Nokia, Nokia Shanghai Bell, Ericsson, Lenovo, Motorola Mobility | RAN5#97 (Nov-22) | R5-216333, R5-216334, R5-217953, R5-222002, R5-223408, R5-223409, R5-225322, R5-227564, R5-227563, R5-227474, R5-231465, R5-231485, R5-233484 |  | 0.1 | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
51 |  | 38.523-3 | TBD | TBD | Update test environment if necessary. | TBD | RAN5#97 (Nov-22) |  |  | 0.1
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.