## Cover sheet
RAN5 meeting #100 | [10 empty] | R5-234315
Toulouse, France, Aug 21-25 2023
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance – NR small data transmissions in INACTIVE state
Work item code: | NR_SmallData_INACTIVE-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 85% | 6 (+6) | 8 (+8)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 80% | 6 (+6) | 8 (+8)
FR1 |  | 80% | 6 (+6) | 8 (+8)
FR2 |  | 80% | 6 (+6) | 8 (+8)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 85% (+85%) |  |  | 85% (+85%) |  |  | 85% (+85%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 77.5% (+77.5%) | 6 (+6) | 8 (+8) | 77.5% (+77.5%) | 6 (+6) | 8 (+8) | 77.5% (+77.5%) | 6 (+6) | 8 (+8)
Applicability Protocol test cases | 38.523-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-221238 | UE Conformance – NR small data transmissions in INACTIVE state
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | NR small data transmissions in INACTIVE state | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column. |  | Current meeting status | [9 empty] | Previous meeting status baseline | [8 empty] | WP rapporteur's private information. These columns will be removed in the clean copy created by "Create clean WP for publishing".
WI code |  | NR_SmallData_INACTIVE-UEConTest
WP Scope: |  | <WP Scope description> | [14 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | Yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | N/A |  |  | N/A
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | N/A | N/A |  | FR1 | FR2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [21 empty] | WP rapporteur internal notes |  | Company <-> Contact email address(es)
[27 empty] | Start of source data | [18 empty] | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[14 empty] | Overall |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | Start of Current Meeting Data | 0.84667 | 0.78125 | [7 empty] | End of Current Meeting Data
[14 empty] | Number of WP items |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | 16 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Sum weight of WP items |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | 15 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Contribution by work plan analysis |  | 0% | [10 empty] | 0% | [9 empty] | 0.05
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 6 | Introduction of General and Signaling Test Environment for Rel-17 Small Data Transmission Tests | ASN.1 and other updates All RRC updates from 38.331 | Qualcomm | RAN5#99 (May-23) | R5-225352 R5-225353 R5-225354 R5-225355 R5-231447 |  | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 85% | 85% | [9 empty] | #NAME? | #NAME?
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.4 | Introduction of common implementation conformance statements for Rel-17 Small Data Transmission Tests | Add ICS as needed for the test case applicability statements for the new test cases | Qualcomm | RAN5#98 (Feb-23) | R5-224331 R5-231593 R5-231596 R5-231446 R5-231597 |  | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
TS 38.523-1: Protocol test cases
MAC
17 |  | 38.523-1 | 7.1 | NR Layer 2 | [5 empty] | 0 | #NAME? | #NAME? | #NAME? | #NAME? | [12 empty] | #NAME? | #NAME?
18 |  | 38.523-1 | 7.1.1 | MAC |  |  | RAN5#97 (Nov-22) |  |  | 0 | #NAME? | #NAME? | [14 empty] | #NAME? | #NAME?
19 |  | 38.523-1 | 7.1.1.13 | Small Data Transmission (SDT) |  |  | RAN5#97 (Nov-22) |  |  | 0 | #NAME? | #NAME? | [14 empty] | #NAME? | #NAME?
20 | Y | 38.523-1 | 7.1.1.13.1 | RA Based SDT/2-step RACH/Successful (1) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold} then { UE shall initiate 2-step RA based SDT procedure } } (2) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is greater than sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold} then { UE shall not initiate RA based SDT procedure and starts normal RRC Resume procedure} } (3) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is below the configured sdt-RSRP-Threshold} then { UE shall not initiate RA based SDT procedure and starts normal RRC Resume procedure } } | TS 38.321, clauses 5.1.1b, 5.1.1c | Motorola Mobility | RAN5#98 (Feb-23) | R5-227483 R5-231589 R5-233413 R5-233415 | Specific message contents FFS to be resolved | 1 | #NAME? | #NAME? |  |  |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
21 | Y | 38.523-1 | 7.1.1.13.2 | RA Based SDT/4-step RACH/Successful (1) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold} then { UE shall initiate 4-step RA based SDT procedure } } (2) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is greater than sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold} then { UE shall not initiate RA based SDT procedure and starts normal RRC Resume procedure} } (3) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is not configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is below the configured sdt-RSRP-Threshold} then { UE shall not initiate RA based SDT procedure and starts normal RRC Resume procedure } } | TS 38.321, clauses 5.1.1b, 5.1.1c | Motorola Mobility | RAN5#98 (Feb-23) | R5-227484 R5-231590 R5-232092 R5-233416 | Specific message contents FFS to be resolved | 1 | #NAME? | #NAME? |  |  |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
26 | Y | 38.523-1 | 7.1.1.13.3 | RA Based SDT/2-step RACH/not complete/ RA_TYPE to 4-stepRA | TS 38.321, clauses 5.1.1b, 5.1.1c | Motorola Mobility | RAN5#98 (Feb-23) | R5-231444 R5-232093 |  | 1 | #NAME? | #NAME? |  |  |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
22 | Y | 38.523-1 | 7.1.1.13.4 | RA Based SDT/4-step RA based SDT/Time Alignment Timer expiry | TS 38.321, clauses 5.1.1b, 5.1.1c, 5.2 | Motorola Mobility | RAN5#98 (Feb-23) | R5-231445 R5-232095 |  | 1 | #NAME? | #NAME? |  |  |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
28 | Y | 38.523-1 | 7.1.1.13.5 | 7.1.1.13.5 RA Based SDT/ CG Based SDT/ cg-SDT-TimeAlignmentTimer Test Purpose (TP) (1) 38.321 5.27.1 with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is configured and Random Access resources for RA-SDT is configured } ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold and at least one SSB configured for CG-SDT with SS-RSRP above cg-SDT-RSRP-ThresholdSSB and cg-SDT-TimeAlignmentTimer is running} then { UE shall initiate CG based SDT procedure } } (2) 38.321 5.27.1 with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is configured and Random Access resources for RA-SDT is configured } ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold and at least one SSB configured for CG-SDT with SS-RSRP above cg-SDT-RSRP-ThresholdSSB and cg-SDT-TimeAlignmentTimer expires } then { UE shall initiate RA based SDT procedure } } (3) 38.321 5.2 and 38.331 5.3.13.5 --- if this TP have already covered by 8.1.5.13.2, I will delete it. with { UE in NR RRC_INACTIVE state and CG-SDT is ongoing} ensure that { when { cg-SDT-TimeAlignmentTimer expires before receiving network response for the UL CG-SDT transmission with CCCH message } then { UE consider ongoing CG-SDT procedure as terminated and perform the actions upon going to RRC_IDLE with release cause 'RRC Resume failure' } } (4) 38.321 5.2 with { UE in NR RRC_INACTIVE state and CG-SDT is ongoing} ensure that { when { cg-SDT-TimeAlignmentTimer expires after receiving network response for the UL CG-SDT transmission with CCCH message } then { UE does not consider ongoing CG-SDT procedure as terminated and UE shall perform uplink transmission using legacy Random Access } } | TS 38.321, clauses 5.2, 5.27.1 and 5.27.2; TS 38.331, clauses 5.3.13.5 | Huawei, Hisilicon | RAN5#99 (May-23) | R5-231591 R5-232969 |  | 1 | #NAME? | #NAME? |  |  |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
RRC
4 |  | 38.523-1 | 8.1 | NR RRC | Existing sub-clause header |  |  |  |  | 0
5 |  | 38.523-1 | 8.1.5 | RRC others | Existing sub-clause header |  |  |  |  | 0 |  |  | #NAME? | #NAME?
11 |  | 38.523-1 | 8.1.5.1 | UE capability transfer | Existing sub-clause header |  |  |  |  | 0 | #NAME? | #NAME? | #NAME? | #NAME? | [12 empty] | #NAME? | #NAME?
12 |  | 38.523-1 | 8.1.5.1.1 | UE capability transfer / Success | TS 38.331, clauses 6.3.3 | Qualcomm | RAN5#97 (Nov-22) | R5-227571 |  | 0 | #NAME? | #NAME? | #NAME? | #NAME? |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
6 |  | 38.523-1 | 8.1.5.13 | Small Data Transmission | Existing sub-clause header |  |  |  |  | 0 | #NAME? | #NAME? | #NAME? | #NAME? | [12 empty] | #NAME? | #NAME?
7 | Y | 38.523-1 | 8.1.5.13.1 | RRC SDT/CG based SDT/Success (1) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold and at least one SSB configured for CG-SDT with SS-RSRP above cg-SDT-RSRP-ThresholdSSB} then { UE shall initiate CG based SDT procedure and starts RRC Resume procedure } } (2) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is greater than sdt-DataVolumeThreshold} then { UE shall not initiate CG based SDT procedure and starts normal RRC Resume procedure } } (3) with { UE in NR RRC_INACTIVE state and SDT-CG-Config-r17 is configured} ensure that { when { UE has small data to transmit and the data volume of the pending UL data across all RBs configured for SDT is less than or equal to sdt-DataVolumeThreshold and RSRP is above the configured sdt-RSRP-Threshold and at least one SSB configured for CG-SDT with SS-RSRP above cg-SDT-RSRP-ThresholdSSB is not available} then { UE shall not initiate CG based SDT procedure and starts normal RRC Resume procedure } } | TS 38.331, clauses 5.3.1.1, 5.3.8.3,5.3.13.1, 5.3.13.1b, 5.3.13.2, 5.3.13.3 | Huawei, Hisilicon | RAN5#98 (Feb-23) | R5-231592 R5-232096 | Previously assigned TC 8.1.5.13.2 'RRC SDT/CG based SDT/Failure' is removed from WP as requirements are coverd in Clause 8.1.5.13.1 & 7.1.1.13.5 | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
9 | Y | 38.523-1 | 8.1.5.13.2 | RRC SDT/CG based SDT ongoing/Data on non-SDT Radio Bearers (1) with { UE in NR RRC_INACTIVE state and CG based SDT procedure is ongoing} ensure that { when { UE has data to transmit on non-SDT Radio Bearers} then { UE shall send UEAssistanceInformation message with nonSDT-DataIndication set } } | TS 38.331, clauses 5.3.1.1, 5.3.8.3,5.3.13.1, 5.3.13.1b, 5.3.13.2, 5.3.13.3 | Nokia | RAN5#99 (May-23) | R5-231594 | TC number has been updated to 8.1.5.13.2(as previosly assigned TC 8.1.5.13.2 was deleted) | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 10% | 10% | [9 empty] | #NAME? | #NAME?
27 | Y | 38.523-1 | 8.1.5.13.3 | RRC SDT/CG based SDT /SDT-SRB2-Indication | TS 38.331, clauses 5.3.1.1, 5.3.8.3,5.3.13.1, 5.3.13.1b, 5.3.13.2, 5.3.13.3 TS 24.501 clause 5.3.1.4. | Nokia | RAN5#99 (May-23) | R5-231595 R5-235356 | TC number has been updated to 8.1.5.13.3(as previosly assigned TC 8.1.5.13.2 was deleted) | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
TS 38.523-2: Applicability for Protocol test cases
23 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 |  |  | RAN5#99 (May-23) | R5-227592 |  | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
TS 38.523-3: Protocol test suites (TTCN)
24 |  | 38.523-3 | NA | Introduction of General and Signaling Test Environment for SDT |  |  | RAN5#99 (May-23) |  |  | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 0% | 0% | [9 empty] | #NAME? | #NAME?
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
29 |  | 38.522 | 4.0, 4.2 | Add test case applicability statements for the new test cases introduced in 38.533 |  |  | RAN5#98 (Feb-23) |  |  | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
TS 38.533: RRM test cases
30 |  | 38.533 | 7.2.1.1 | TA Validation for CG-SDT in FR2 |  | Nokia | RAN5#100 (Aug-23) | R5-232130 | Editor’s note: This test case is incomplete. The following aspects are either missing or TBD - Test procedure, some parameters are not complete in RAN4. In particular, timers T1, T2, T3, T4, T5 are missing. - Message contents - Test requirements are not completed in RAN4 - TT analysis is missing - Annex F | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  |  | 55% | [9 empty] | #NAME? | #NAME?
31 |  | 38.533 | 6.2.1 | NR SA FR1 Configured Grant based Small Data Transmissions (CG-SDT) |  | Qualcomm | RAN5#100 (Aug-23) | R5-234674 R5-235895 | Editor's Note: - MU and TT analysis is incomplete - Some test parameters are still in brackets | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 75% | [10 empty] | #NAME? | #NAME?
TS 38.903 Derivation of test tolerances and measurement uncertainty for User Equipment (UE) conformance test cases
32 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | Also includes TT analysis zip files |  | RAN5#100 (Aug-23) |  |  | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  |  | 0% | [9 empty] | #NAME? | #NAME?
[10 empty] | 1 |  |  | #NAME? | #NAME? | [12 empty] | #NAME? | #NAME?
Overall WP completion
25 |  |  |  | Overall Definition and scope of WI |  |  | RAN5#101 (Dec-23) |  |  | 1 | #NAME? | #NAME? | #NAME? | #NAME? |  | 100% | 100% | [9 empty] | #NAME? | #NAME?
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row. | [26 empty] | End of source data
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.