## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: SS: System Simulator
UE: User Equipment

## Slide 3
Test Models – 5G:
  Rel-15:
    Proposed test model update for intra-frequency multi-cells test cases, to prevent/mitigate the inter-cell PDCCH clash for SIB1 & Other SI.
    Semantic clarification on NR ASP ActTimeList for AS security.
  Rel-17:
    EN-DC UPIP: endorsed updates to EN-DC test model and E-UTRA ASPs.
    PowSavEnh: endorsed initial test model and NR ASPs updates.
    Baseline upgrade to Jun’23: endorsed updates to 5GC NAS type definitions + TTCN updates when using new NR ASN.1.
  Prose CRs to TS 38.523-3 submitted at RAN5#100 for the above.
Test models & ASPs design Progress at TTCN Workshop #62 (6th Jul’23)
Notes: ASP: Abstract Service Primitive

## Slide 4
Test Models – NB-IoT:
  Rel-17 NTN: endorsed NB-IoT ASP updates to add support of new MAC CEs.
  Rel-17 baseline upgrade to Jun’23: Endorsed TTCN updates when using new NB-IoT ASN.1.
  Prose CR to TS 36.523-3 submitted at RAN5#100 for the above.
Test Models – LTE:
  Rel-17 baseline upgrade to Jun’23: Endorsed TTCN updates when using new E-UTRA ASN.1.
  Prose CR to TS 36.523-3 submitted at RAN5#100 for the above.
Test Models – POS:
  Rel-17 NR POS Enh: Endorsed updates to NR ASPs to add support of new MAC CEs.
RAN5 TTCN Workshop #62 material:
  https://portal.3gpp.org/Home.aspx#/meeting?MtgId=60554
Test models & ASPs design Progress at TTCN Workshop #62 (6th Jul’23)

## Slide 5: TTCN development Progress for period: Jun to Aug’23
Completed:
  LTE Rel-16:
    RRC DL segmentation
  5G Rel-17:
    Network slicing enhancements phase2
    5GC eCPSOR
  IMS:
    Rel-15 IMS emergency over NR/5GC
Progressed:
  5G Rel-15:
    NE-DC
  5G Rel-16:
    MR-DC & NR CA enhancements
    V2X
  5G Rel-17:
    RedCap HD-FDD
    SON/MDT enhancements
  Mission Critical:
    Rel-16 MCVideo, MCData over LTE
Started:
  NB-IoT Rel-17:
    Non-terrestrial networks (NTN)
  5G Rel-16:
    NR 2-step RACH
    Redirection with MPS Indication
  5G Rel-17:
    NR UE power saving enhancements
    NR RAN slicing enhancements
    NR UL data compression
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 6: TTCN verification Progress for period: 17th May --> 15th Aug’23
Completed:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE/C2K Inter-RAT | Rel-8 | 088 | 13 / 13 | = | 
LTE/C2K Inter-RAT | Rel-10 | 180 | 1 / 1 | = | 
LTE/GERAN Inter-RAT | Rel-10 | 182/184 | 1 / 1 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 7: TTCN verification Progress for period: 17th May --> 15th Aug’23
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC access stratum | Rel-15 | 503 | 95 / 102 | = | 
NR/5GC access stratum | Rel-15 | 503 | 151 / 160 | +1 | Prio1: 92/95 ; Prio2: 59/65
NR/5GC NR-DC | Rel-15 | 503 | 11 / 13 | = | Prio1: 9/11 ; Prio2: 2/2
NR/5GC NAS | Rel-15 | 504 | 75 / 76 | = | Prio1: 35/35 ; Prio2: 40/41
NR/5GC NR CA | Rel-15 | 510 | 30 / 32 | = | Prio1: 14/15 ; Prio2: 16/17
EN-DC NR CA | Rel-15 | 512 | 13 / 17 | = | Prio1: 12/13 ; Prio2: 1/4 +1 under verification
Inter-RAT SON/MDT | Rel-16 | none | 3 / 4 | = | 
5G private network - SNPN | Rel-16 | 518 | 7 / 9 | +1 | Prio1: 3/3 ; Prio2: 3/4
NR mobility enhancements | Rel-16 | 522 | 10 / 13 | = | Prio1: 5/7 ; Prio2: 5/6
NR UE power saving | Rel-16 | 533 | 2 / 9 | +1 | +1 under verification
NR RRC DL segmentation | Rel-16 | 538 | 1 / 2 | = | 
MR-DC & NR CA enhancements | Rel-16 | none | 3 / 28 | = | 
Reduced capability (RedCap) | Rel-17 | 530 | 4 / 6 | +1 | Prio1: 4/4 ; Prio2: 0/2
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 17th May --> 15th Aug’23
Progressed – IMS, Positioning, MCX:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE positioning | Rel-9+ | 166, RTF-115 | 17 / 27 | +2 | 
MCPTT over LTE | Rel-14 | 288, RFT-153 | 37 / 51 | = | Prio1: 32/42 ; Prio2: 5/9 +1 under verification
IMS eCall over LTE (34.229) | Rel-14 | 298 | 5 / 12 | = | 
MCData over LTE | Rel-14 | 329, RFT-153 | 4 / 28 | = | Prio1: 3/15 ; Prio2: 1/13
MCPTT enhancements over LTE | Rel-15 | 330, RFT-153 | 2 / 22 | = | Prio1: 2/15 ; Prio2: 0/7 +3 under verification
IMS over NR/5GC | Rel-15 | 505 | 92 / 94 | +1 | Prio1: 19/19 ; Prio2: 73/75
5G Positioning | Rel-15 | 506 | 9 / 10 | = | Left: TC 9.3.3.1B
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 17th May --> 15th Aug’23
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
CA intra-band contiguous | Rel-11 | 162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | 245 | 6 / 9 | = | 
eDRX | Rel-13 | 253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | 254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | 254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | 257 | 72 / 73 | = | Left: TCs 22.1.1.M2
LAA | Rel-13 | 272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | 295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
IMS eCall over LTE (36.523) | Rel-14 | 298 | 3 / 9 | = | 
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 10: TTCN verification Progress for period: 17th May --> 15th Aug’23
Started:
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
IMS eCall over NR/5GC (38.523) | Rel-16 | 537 | 2 / 5 | +2 | +2 under verification
5G network slicing enhancements – Phase 2 | Rel-17 | none | 2 / 13 | +2 | +1 under verification
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
5G CP SOR enhancements in connected mode | Rel-17 | 534 | 0 / 6 |  | +3 under verification
NB-IoT NTN | Rel-17 | 333_NB | 0 / 7 |  | +3 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 11
2022 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | TTCN Status (as of Aug’23) / Comments
5GS: NE-DC (option 4) | Rel-15 | N,L | Q4’23 | 34 | Q1’22-Q4’23 | 1 | 76% (@iwd-23wk24)
5G V2X with NR sidelink | Rel-16 | N,L | Q4’23 | 72 | Q4’20-Q1’24 | 2 | 42% (@iwd-23wk24)
MR-DC & NR CA enhancements | Rel-16 | N,L | Q2’23 | 29 | Q1’22-Q3’23 | 1 | 75% (@iwd-23wk24)
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q4’23 | 15 | Q1’22-Q1’24 | 2 | Not started
IMS eCall over NR | Rel-16 | N | Q1’23 | 20 | Q3’21-Q1’23 | 0.5 | 100% (@iwd-23wk12)
NR positioning | Rel-16 | N | Q3’23 | 29 | Q2’21-Q3’23 | 0.2 | 90% (@iwd-22wk49)
NR MIMO enhancements | Rel-16 | N | Q4’22 | 1 | Q4’22-Q4’23 | 0.3 | Not started
NR 2-step RACH | Rel-16 | N | Q4’22 | 12 | Q3’22-Q3’23 | 1 | 33% (@iwd-23wk24)
NW slicing enhancements - Phase2 | Rel-17 | N | Q2’23 | 13 | Q4’22-Q2’23 | 0.5 | 100% (@iwd-23wk24)
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q4’23 | >11 | Q4’22-Q4’23 | 2 | 25% (@iwd-23wk24)
Reduced capability NR UE (RedCap) | Rel-17 | N | Q4’23 | >12 | Q4’22-Q4’23 | 1.5 | 72% (@iwd-23wk12)
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 43 | Q4’22-Q1’24 | 4 | Not started
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q1’24 | 1.5 | 7% ; Test Model work
NR UE power saving enhancements | Rel-17 | N | Q3’23 | 5 | Q4’22-Q4’23 | 1.5 | 20% (@iwd-23wk24)
NR RAN slicing enhancements | Rel-17 | N | Q3’23 | 8 | Q4’22-Q4’23 | 1.5 | 37% (@iwd-23wk24)
NR sidelink enhancements | Rel-17 | N | Q4’23 | 2 | Q4’22-Q1’24 | 0.5 | Not started ; no prose
NR sidelink relay | Rel-17 | N | Q4’23 | 19 | Q4’22-Q1’24 | 2 | Not started ; no prose
TEIx_Test (new TC coverage) | Rel-15+ | All | n/a | 10 | Q1’23-Q4’23 | 1 | 2023 total after RAN5#99: 4 new tests
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | >349 |  | 75 | person-months
TTCN workplan 2023
Status of 2022 tasks carried over and maintenance
Notes: Note: TTCN of some features initially started in 2022 will only be completed in 2023 due to availability of prose late in CY2022, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12
2023 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | TTCN Status (as of Aug’23) / Comments
MCX enhancements | R15to16 | L | Q3’24 | 79 | Q1’23-Q4’24 | 4 | 50% (@iwd-23wk24)
Inter-system mobility between untrusted non-3GPP and 3GPP | Rel-15 | L,N | Q2’23 | 7 | Q1’23-Q4’23 | 3 | Not started
5G access traffic steering, switch and splitting | Rel-16 | N | Q2’23 | 7 | Q1’23-Q4’23 | 1.5 | Not started
NB-IoT/eMTC for non-terrestrial networks (NTN) | Rel-17 | L | Q3’23 | >14 | Q1’23-Q4’23 | 3 | 30% (@iwd-23wk24)
5G control plane steering of roaming for UE in connected mode enhancements (CP SOR) | Rel-17 | N | Q1’23 | 6 | Q1’23-Q2’23 | 1 | 100% (@iwd-23wk24)
NR UL data compression (UDC) | Rel-17 | N | Q2’23 | 9 | Q1’23-Q3’23 | 2 | 90% (@iwd-23wk24)
NR industrial IoT and URLLC enhancements | Rel-17 | N | Q4’23 | 6 | Q1’23-Q4’23 | 1.5 | Not started
User plane integrity protection for EPC (UPIP) | Rel-17 | L,N | Q4’23 | 9 | Q1’23-Q4’23 | 1.5 | 5% ; Test Model work
NR coverage enhancements | Rel-17 | N | Q4’23 | 9 | Q1’23-Q1’24 | 1.5 | Not started
NR small data Tx in INACTIVE state | Rel-17 | N | Q3’23 | 8 | Q1’23-Q1’24 | 1.5 | Not started
NR positioning enhancements | Rel-17 | N | Q4’23 | 3 | Q1’23-Q4’23 | 1 | 5% ; Test Model work
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q4’23 | >22 | Q1’23-Q1’24 | 3 | Not started ; no prose
5G non-public network enhancements | Rel-17 | N | Q4’23 | 17 | Q1’23-Q1’24 | 2 | Not started ; no prose
NR QoE management and optimizations | Rel-17 | N | Q1’24 | 4 | Q1’23-Q1’24 | 1 | Not started ; no prose
NR MIMO further enhancements | Rel-17 | N | Q4’23 | 3 | Q1’23-Q1’24 | 1 | Not started ; no prose
New/extended bands & band combinations | R16to18 | L,N | Q2’25 | n/a | Q1’21-Q2’25 | 0.5 | 17% (@iwd-22wk49)
Total: |  |  |  | >203 |  | 29 | person-months
TTCN workplan 2023
Status of new 2023 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 13
2023 workload is estimated at 104 person-months (pm), see previous slides.
PCG#49/OP#48 approved the 3GPP funding of 58 pm for 2023 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2023.
Current commitments for 2023 are as follows:
3GPP companies / 3GPP MRPs committed to provide 20 pm as voluntary contributions for 2023 TTCN development.
Total resources of 104 pm  no estimated funding gap.
TTCN funding 2023
Status
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#49/OP#48 approved (decision OP48/05)
CTIA/PTCRB | 12 | NE-DC, NR IIoT/URLLC, MCX, RedCap
GCF | 12 | NR V2X, NR 2-step RACH, NR Rel-17 enh., RedCap, MCX
Qualcomm | 2 | NR-U, SDT, NTN-IoT
Total: | 84 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Anritsu | 1 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | NTN-IoT
Total: | 20 | 

## Slide 14
Course of action to secure funding for TF160 work in 2024:
  Prior to RAN5#100 meeting (August), a request to identify the potential TTCN development tasks in 2024 has been made to 3GPP members.
  At RAN5#100, a provisional ‘TTCN Tasks List’ shall be endorsed by RAN5.
  The TTCN Tasks List will be presented at RAN#101 (Sept) for TSG RAN initial endorsement.
  The RAN Chair will then present the List to 3GPP PCG/OP (Oct) in order to support TF160 request for the TTCN funding in 2024.
  The finalized TTCN Tasks List will be reviewed and endorsed at RAN5#101 (Nov) for TSG RAN approval at RAN#102 (Dec).
Based on feedback from several RAN5 member companies and 3GPP MRPs, the list of TTCN tasks presented in the next slides has been produced by the TF160 Leader.
Preparing for 2024 TTCN Work
Overview

## Slide 15
2023 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2024 WkLoad | 3GPP related Work Item
MCX enhancements | R15to16 | L | Q3’24 | 79 | Q1’23-Q4’24 | 4 | MCProtoc16_enh2MCPTT_eMCData2-ConTest
5G V2X with NR sidelink | Rel-16 | N,L | Q4’23 | 72 | Q4’20-Q1’24 | 2 | 5G_V2X_NRSL_eV2XARC-UEConTest
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q4’23 | 15 | Q1’22-Q1’24 | 1 | NR_unlic-UEConTest
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 43 | Q4’22-Q1’24 | 2 | NR_MBS_5MBS_5MBUSA-UEConTest
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q1’24 | 1 | LTE_NR_MUSIM_plus_CT1-UEConTest
NR sidelink enhancements | Rel-17 | N | Q4’23 | 2 | Q4’22-Q1’24 | 0.5 | NR_SL_enh-UEConTest
NR sidelink relay | Rel-17 | N | Q4’23 | 19 | Q4’22-Q1’24 | 1.5 | NR_SL_Relay-UEConTest
NR coverage enhancements | Rel-17 | N | Q4’23 | 9 | Q1’23-Q1’24 | 0.5 | NR_cov_enh-UEConTest
NR small data Tx in INACTIVE state | Rel-17 | N | Q3’23 | 8 | Q1’23-Q1’24 | 0.5 | NR_SmallData_INACTIVE-UEConTest
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q4’23 | >22 | Q1’23-Q1’24 | 1 | NR_NTN_solutions_plus_CT-UEConTest
5G non-public network enhancements | Rel-17 | N | Q4’23 | 17 | Q1’23-Q1’24 | 1 | NG_RAN_PRN_enh_plus_CT-UEConTest
NR QoE management and optimizations | Rel-17 | N | Q1’24 | 4 | Q1’23-Q1’24 | 0.5 | NR_QoE-UEConTest
NR MIMO further enhancements | Rel-17 | N | Q4’23 | 3 | Q1’23-Q1’24 | 1 | NR_feMIMO-UEConTest
New/extended bands & band combinations | R16to18 | L,N | Q2’25 | n/a | Q1’21-Q2’25 | 0.5 | NR_lic_bands_BW_R18-UEConTest NR_CADC_NR_LTE_DC_R1x-UEConTest, LTE_CA_R17-UEConTest (new)
TEIx_Test (new TC coverage) | Rel-15+ | All | n/a | 10 | Q1’24-Q4’24 | 2 | TEIx_Test
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | ~317 |  | 70 | person-months
Preparing for 2024 TTCN Work – Tasks List
2023 tasks completion and maintenance
Notes: Note: TTCN of some features initially started in 2023 will only be completed in 2024 due to availability of prose late in CY2023, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 16
2024 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2024 WkLoad | 3GPP related Work Item
Further MR-DC enhancement | Rel-17 | N | Q1’24 | 10 | Q1’24-Q2’24 | 2 | LTE_NR_DC_enh2-UEConTest
UAS connectivity, identification and tracking | Rel-17 | N | Q4’24 | 7 | Q1’24-Q4’24 | 1.5 | ID_UAS-UEConTest
IMS voice & NW usability no E-UTRA in 5GS | Rel-17 | N,L | Q1’24 | 2 | Q1’24-Q2’24 | 0.5 | ING_5GS-UEConTest
IMS data channel | Rel-17 | N,L | Q3’24 | 10 | Q1’24-Q4’24 | 2 | IMSProtoc17_dataCH-UEContest
5G ATSSS - Phase2 | Rel-17 | N | Q3’24 | 10 | Q2’24-Q4’24 | 2 | ATSSS_Ph2-UEConTest (new)
Signal level enhanced network selection | Rel-18 | L | Q2’24 | 4 | Q3’24-2025 | 1 | SENSE-UEContest (new)
Further NR coverage enhancements | Rel-18 | N | 2024 | 10 | Q3’24-2025 | 2 | NR_cov_enh2
Further NR mobility enhancements | Rel-18 | N | 2024 | 10 | Q3’24-2025 | 2 | NR_Mob_enh2
Multi-carrier enhancements for NR | Rel-18 | N | 2024 | 5 | Q3’24-2025 | 1 | NR_MC_enh
Network energy savings for NR | Rel-18 | N | 2024 | 5 | Q3’24-2025 | 1 | Netw_Energy_NR
Enhanced RedCap NR UE | Rel-18 | N | 2024 | 10 | Q3’24-2025 | 2 | NR_redcap_enh
IoT NTN enhancements | Rel-18 | L | 2024 | 12 | Q3’24-2025 | 2 | IoT_NTN_enh
XR enhancements for NR | Rel-18 | N | 2024 | 10 | Q3’24-2025 | 2 | NR_XR_Enh
Expanded and improved NR positioning | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 1 | NR_pos_enh2
Dual Tx/Rx MUSIM | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 1 | NR_DualTxRx_MUSIM
Enhancements of NR MBS | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 1 | NR_MBS_enh
NR sidelink relay enhancements | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 1 | NR_SL_relay_enh
NR support for UAV | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 1 | NR_UAV, UAS_Ph2
Enhanced LTE support for UAV | Rel-18 | L | 2024 | FFS | Q3’24-2025 | 1 | LTE_UAV_enh, UAS_Ph2
Non-Public Networks Phase 2: NG-RAN aspects | Rel-18 | N | 2024 | 10 | Q3’24-2025 | 2 | eNPN_Ph2-NGRAN-Core
NR NTN enhancements | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 2 | NR_NTN_enh, 5GSAT_Ph2
Total: |  |  |  | >115 |  | 31 | person-months
Preparing for 2024 TTCN Work – Tasks List
New 2024 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 17
2024 Funding: 2024 workload is estimated at 101 person-months (pm), see previous slides.
  Funding will be requested to 3GPP PCG/OP.
    Typically, only part of necessary funding provided by PCG/OP
      example: 58 person-months in 2023
  Funding shall also be obtained through voluntary contributions from 3GPP companies and/or MRPs.
    Commitments received to date:
   RAN / RAN5 member companies and 3GPP MRPs are respectfully asked to consider providing funding support for the TTCN tasks in 2024.
Funding |  | 
Entity | Person-months | Comments
3GPP | TBD | 
TBD | TBD | 
Total: | TBD | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Keysight | 1 | 
TBD | TBD | 
Total: | 15 | 
Preparing for 2024 TTCN Work

## Slide 18
Request to RAN5: RAN5 is requested to endorse
  The 2024 TTCN Tasks List presented in the previous slides,
  The request from RAN5 to TSG RAN and PCG/OP for a 3GPP funding of 58 person-months in 2024.
  Note: Additional contributions of 43 person-months are expected to be found from other sources for 2024.
Preparing for 2024 TTCN Work
Funding

## Slide 19: Annexes

## Slide 20: TTCN deliveries and baseline 2023 schedule
One TTCN-2 full delivery (FDD & LCR TDD) and four TTCN-3 full deliveries.
Type definitions baseline upgrade planned in 2023:
  Rel-17 Phase2: partial upgrade to Rel-17 Jun'23 baseline for NR+5GC+E-UTRA due to new/updated ASN.1+tabular IEs required by Rel-17 NR/5GC & NB-IoT test cases.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
 wk05 |  |  | 03-Feb |  | GCF CAG#73 (7-9 Feb)
 wk07 |  |  | 17-Feb |  | PTCRB PVG#100 (21-23 Feb)
 wk12 | 24-Mar | 20-Mar | 24-Mar | TTCN-3 | 
 wk16 |  |  | 21-Apr |  | GCF CAG#74 (25-28 Apr)
 wk19 |  |  | 12-May |  | PTCRB PVG#101 (16-18 May)
 wk24 | 16-Jun | 12-Jun | 16-Jun | TTCN-3 | 
 wk29 |  |  | 21-Jul |  | GCF CAG#75 (25-27 Jul)
 wk32 |  |  | 11-Aug |  | PTCRB PVG#102 (15-17 Aug)
wk37 | 15-Sep | 11-Sep | 15-Sep | TTCN-3 Rel-17 phase2 baseline upgrade | Partial upgrade to Rel-17 Jun'23 baseline for NR+5GC+E-UTRA
wk41 |  |  | 13-Oct |  | GCF CAG#76 (17-19 Oct)
wk44 |  |  | 03-Nov |  | PTCRB PVG#103 (7-9 Nov)
wk48 | 30-Nov | 27-Nov |  | TTCN2 (FDD) | 
wk48 | 01-Dec | 27-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 08-Dec | 04-Dec | 08-Dec | TTCN-3 | 

## Slide 21: Minutes of TTCN Sidebar
Tuesday 22nd August @5PM CET.
Agenda and minutes:
  See RAN5#100_TTCN_Sidebar-v3.zip