## Cover sheet
3GPP RAN5 meeting #102 | [10 empty] | R5-240667
Athens, Greece, Feb 26th - March 1st, 2024
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking
Work item code: | ID_UAS-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 95% | 3 | 12
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 95% | 0 | 6
FR1 |  | 95% | 0 | 6
FR2 |  | 95% | 0 | 6
LTE |  | 95% | 3 | 6
TDD |  | 95% | 3 | 6
FDD |  | 95% | 3 | 6
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | TDD |  |  | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 90% |  |  | 90% |  |  | 90%
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  | 100%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 91.7% | 1 | 6 | 91.7% | 1 | 6 | 91.7% | 1 | 6
Applicability Protocol test cases | 38.523-2 | 100% |  |  | 100% |  |  | 100%
Test suites (TTCN) | 38.523-3 | 50% |  |  | 50% |  |  | 50%
EUTRA
EUTRA Common
Common test environment | 36.508 | 100%
EUTRA RAN and CN protocols
Protocol test cases | 36.523-1 | 95% | 3 | 6
Applicability Protocol test cases | 36.523-2 | 100%
Test suites (TTCN) | 36.523-3 | 0%
5 References
[1] RP-230716 | Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | ID_UAS-UEConTest
WP Scope: |  | <WP Scope description> | [13 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | Yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  | FR1 | FR2 | TDD | FDD
[15 empty] | 85% | 85% (+5%) | 45.4% (+2.7%) | 45.4% (+2.7%)
[15 empty] | 13 | 13 | 9 | 9
[15 empty] | 13 | 13 | 6.5 (-1) | 6.5 (-1)
0%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
17 |  | 36.508 |  | Introduction of General and Signaling Test Environment for Rel-17 UAS in EPS |  | Qualcomm | RAN5#103 (May-24) | R5-237414 |  |  | 100% |  | 100% |  |  |  | 100% | 100%
TS 36.523-1: Protocol test cases
2 | Y | 36.523-1 | 10.10.1 | UAS / UE requested PDN connection establishment / UUAA / Success | (1) with { UE in EMM-REGISTERED state } ensure that { when { UE is triggered to request connectivity to an additional PDN for UAS services } then { the UE transmits a PDN CONNECTIVITY REQUEST message with service-level-AA container including CAA-level UAV ID for USS communication } } (2) with { UE having transmitted a PDN CONNECTIVITY REQUEST message with service-level-AA container including CAA-level UAV ID for USS communication } ensure that { when { UE receives MODIFY EPS BEARER CONTEXT REQUEST message with service-level-AA container including service-level-AA response parameter with the SLAR field set to "Service level authentication and authorization was successful" as part of UUAA-SM procedure } then { the UE considers UUAA-SM procedure as successful and transmits MODIFY EPS BEARER CONTEXT ACCEPT message } } | Qualcomm | RAN5#103 (May-24) | R5-237415 | TS 24.301, clauses 6.3.13.2, 6.4.3.1, 6.4.3.2, 6.4.3.3 and 6.5.1.2. | 1 | 90% |  | 90% |  |  |  | 90% | 90%
20 | Y | 36.523-1 | 10.10.2 | UAS / UE requested PDN connection establishment / UUAA Re-authentication and Re-authorization with USS | with { UE having peformed successful UUAA-SM procedure for USS communication } ensure that { when { UE receives MODIFY EPS BEARER CONTEXT REQUEST message with service-level-AA container } then { the UE transmits MODIFY EPS BEARER CONTEXT ACCEPT message } } | Qualcomm | RAN5#102 (Feb-24) | R5-241608 | TS 24.301, clauses 6.3.13.2, 6.4.3.2, 6.4.3.3 | 1 | 100% |  | 100% |  |  |  | 100% | 100%
21 | Y | 36.523-1 | 10.10.3 | UAS / UE requested PDN connection establishment / UUAA / Authorization of C2 Communication / Modification / Release | (1) with { UE having peformed successful UUAA-SM procedure for USS communication } ensure that { when { UE is triggered to request connectivity to an additional PDN for C2 communication } then { the UE transmits a PDN CONNECTIVITY REQUEST message with service-level-AA container including parameters service-level device ID, service-level-AA payload, service-level-AA payload type for C2 communication } } (2) with { UE having peformed successful UUAA-SM procedure for USS communication, establishes PDN connection with service-level-AA container including CAA-level UAV ID for C2 communication } ensure that { when { UE receives MODIFY EPS BEARER CONTEXT REQUEST message with service-level-AA container including service-level-AA response parameter with the C2AR field set to "C2 authorization was successful" } then { the UE transmits MODIFY EPS BEARER CONTEXT ACCEPT message } } (3) with { UE having peformed successful authorization for C2 communication } ensure that { when { UE receives MODIFY EPS BEARER CONTEXT REQUEST message for modification of C2 communication } then { the UE transmits MODIFY EPS BEARER CONTEXT ACCEPT message } } (4) with { UE having peformed successful authorization for C2 communication } ensure that { when { UE recieves Deactivate EPS Bearer Context Request message for releasing C2 communication } then { the UE successfully releases the PDN connection for C2 communication } } | Qualcomm | RAN5#103 (May-24) | R5-237416 | TS 24.301, clauses 6.3.13.3, 6.4.3.1, 6.4.3.2, 6.4.3.3 and 6.5.1.2 | 1 | 90% |  | 90% |  |  |  | 90% | 90%
22 | Y | 36.523-1 | 10.10.4 | UAS / UE requested PDN connection establishment / UUAA / Authorization failure of C2 Communication | (1) with { UE having peformed successful UUAA-SM procedure for USS communication establishes PDN connection with service-level-AA container including CAA-level UAV ID for C2 communication } ensure that { when { UE receives MODIFY EPS BEARER CONTEXT REQUEST message with service-level-AA container including service-level-AA response parameter with the C2AR field set to "C2 authorization was not successful or C2 authorization is revoked" } then { the UE transmits MODIFY EPS BEARER CONTEXT ACCEPT message } } | Qualcomm | RAN5#102 (Feb-24) | R5-241609 | TS 24.301, clauses 6.3.13.3, 6.4.3.1, 6.4.3.2 and 6.4.3.3 | 1 | 100% |  | 100% |  |  |  | 100% | 100%
23 | Y | 36.523-1 | 10.10.5 | UAS / UE requested PDN connection establishment / UUAA Revocation by USS | (1) with { UE having peformed successful UUAA-SM procedure for USS communication } ensure that { when { UE receives Deactivate EPS Bearer Context Request message with service-level-AA container including service-level-AA response parameter with the SLAR field set to "Service level authentication and authorization was not successful or service level authorization is revoked" } then { the UE transmits DEACTIVATE EPS BEARER CONTEXT ACCEPT message } } | Qualcomm | RAN5#103 (May-24) | R5-237417 | TS 24.301, clauses 6.3.13.2, 6.4.4.1, 6.4.4.2 and 6.4.4.3 | 1 | 90% |  | 90% |  |  |  | 90% | 90%
24 | Y | 36.523-1 | 10.10.6 | UAS / UE requested PDN connection establishment / UUAA / Revocation of C2 Communication | (1) with { UE having performed successful authorization for C2 communication } ensure that { when { UE receives Deactivate EPS BEARER CONTEXT REQUEST message with service-level-AA container including service-level-AA response parameter with the C2AR field set to "C2 authorization was not successful or C2 authorization is revoked" } then { the UE transmits DEACTIVATE EPS BEARER CONTEXT ACCEPT message } } | Qualcomm | RAN5#102 (Feb-24) | R5-241610 | TS 24.301, clauses 6.3.13.3, 6.4.4.1, 6.4.4.2, and 6.4.4.3 | 1 | 100% |  | 100% |  |  |  | 100% | 100%
TS 36.523-2: Applicability for Protocol test cases
3 |  | 36.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
18 |  | 36.523-2 |  | Add test case applicability statements for the new test cases introduced in 36.523-1 |  | Qualcomm | RAN5#102 (Feb-24) | R5-236922 R5-241043 |  | 0.5 | 100% |  | 100% |  |  |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
4 |  | 36.523-3 | NA | Introduction of General and Signaling Test Environment for Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking | [5 empty] | 1
19 |  | 36.523-3 |  | Introduction of General and Signaling Test Environment for Rel-17 UAS in EPS |  |  | TBD |  |  |  | 0% |  | 0% |  |  |  | 0% | 0%
5GS
5GS Common
|  | 38.508-1 | 4.6, 4.7, 4.9 | Introduction of General and Signaling Test Environment for Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking | ASN.1 and other updates | Qualcomm | RAN5#102 (Feb-24) | R5-237408 |  | 1 | 90% | 90% |  |  | 90% | 90%
|  | 38.508-2 | A.4.1 | Addition of PICS for UE support of Uncrewed Aerial Systems | Add ICS as needed for the test case applicability statements for the new test cases | Qualcomm | RAN5#100 (Aug-23) | R5-233202 |  | 1 | 100% | 100% |  |  | 100% | 100%
|  | 38.523-1 | 9.1 | 5GS mobility management | [5 empty] | 0
|  | 38.523-1 | 9.1.x | UAS / Mobility management aspects | [5 empty] | 0
7 | Y | 38.523-1 | 9.1.5.1.17 | Initial registration / Success / UAS | with { UE is powered on and has sent a REGISTRATION REQUEST message } ensure that { when { UE receives Service-level-AA container IE with service-level-AA pending indication in REGISTRATION ACCEPT } then { UE shall send a REGISTRATION COMPLETE message to acknowledge reception of the service-level-AA pending indication, and the UE shall not attempt to perform another registration procedure or to establish a PDU session for USS communication } | Qualcomm | RAN5#101 (Nov-23) | R5-235440, R5-237409 | UUAA-MM procedure reffered in this test is FFS | 1 | 90% | 90% |  |  | 90% | 90%
8 | Y | 38.523-1 | 9.1.5.2.11 | UAS / Mobility and periodic registration update / UUAA / Rejected | (1) with { UE in 5GMM-REGISTERED state and successfully authenticated for UAS services through UUAA-MM procedure } ensure that { when { UE initiates a Mobility and periodic registration procedure on an NGC cell and receives a REGISTRATION REJECT message including 5GMM cause value #79 (UAS services not allowed) } then { UE enters the state GMM-REGISTERED.ATTEMPTING-REGISTRATION-UPDATE 5U2 NOT UPDATED and shall not attempt registration procedure for UAS services } } | Ericsson | RAN5#100 (Aug-23) | R5-237412 R5-241607 | UUAA-MM procedure reffered in this test is FFS | 1 | 90% | 90% |  |  | 90% | 90%
9 | Y | 38.523-1 | 9.1.6.2.3 | UAS / De-registration / UE-initiated / Network-initiated | (1) with { the UE in 5GMM-REGISTERED state and successfully authenticated for UAS services through UUAA-MM procedure } ensure that { when { the UE reauthentication through UUAA-MM procedure fails and the network initiates the de-registration procedure by sending a DEREGISTRATION REQUEST message to the UE with cause value “UAS services not allowed” } then { UE responds to DEREGISTRATION REQUEST with DEREGISTRATION ACCEPT message } } (2) with { the UE in 5GMM-REGISTERED state and successfully authenticated for UAS services through UUAA-MM procedure } ensure that { when { the aerial UE subscription information is changed and the network initiates the de-registration procedure by sending a DEREGISTRATION REQUEST message to the UE with cause value “UAS services not allowed” } then { UE responds to DEREGISTRATION REQUEST with DEREGISTRATION ACCEPT message } } | Nokia | RAN5#100 (Aug-23) | R5-235386 R5-241605 | Specific message contents to be defined | 1 | 90% | 90% |  |  | 90% | 90%
10 | Y | 38.523-1 | 9.1.4.2 | UAS / Generic UE configuration update / Revocation | (1) with { the UE in 5GMM-REGISTERED state and successfully authenticated for UAS services through UUAA-MM procedure } ensure that { when { the network informs UE about revocation with CONFIGURATION UPDATE COMMAND and initiates UE deregistration with DEREGISTRATION REQUEST using cause “UAS services not allowed” } then { the UE acknowledges revocation information with CONFIGURATION UPDATE COMPLETE message and completes the de-registration procedure with DEREGISTRATION ACCEPT message } } | Nokia | RAN5#101 (Nov-23) | R5-235387, R5-237411 | UUAA-MM procedure referred in this TC is FFS | 1 | 90% | 90% |  |  | 90% | 90%
|  | 38.523-1 | 10.1 | 5GS session management
|  | 38.523-1 | 10.1.x | UE-requested PDU session establishment
11 | Y | 38.523-1 | 10.1.4.2 | UAS / UE requested PDU session establishment / UUAA / Release | (1) with { UE in 5GMM-REGISTERED state } ensure that { when { UE requests establishment of a new sPDU session for UAS services by sending PDU Session establishment Request message } then { The UE successfully complete the PDU session establishment procedure } } (2) with { the UE is in PDU SESSION ACTIVE state} ensure that { when { UE is made to Release the PDU Session } then { the UE successfully completes the PDU session release procedure } } | Ericsson | RAN5#101 (Nov-23) | R5-237413 | UUAA procedure is FFS Test procedure needs to be updated for UE performing UUAA | 1 | 90% | 90% |  |  | 90% | 90%
12 | Y | 38.523-1 | 10.1.4.3 | UAS / UE requested PDU session establishment / UUAA / C2 authorisation / Modification / Release | (1) with { the UE in 5GMM-REGISTERED state and successfully authenticated for UAS services through UUAA-MM procedure and } ensure that { when { UE-requested PDU session by sending PDU Session establishment Request message for C2 communication } then { The UE successfully completes the PDU session establishment procedure for C2 communication} } (2) with { the UE is in PDU SESSION ACTIVE state for C2 communication } ensure that { when { UE is made to Modify the PDU Session for C2 communication } then { the UE successfully completes the PDU session modification procedure for C2 communication } } (3) with { the UE is in PDU SESSION ACTIVE state for C2 communication } ensure that { when { UE is made to Release the PDU Session for C2 communication } then { the UE successfully completes the PDU session release procedure for C2 communication } } | Motorola Mobility | RAN5#100 (Aug-23) | R5-235388, R5-237410 R5-241606 | UUAA-MM procedure referred in this TC is FFS Test procedure might need to be updated on PDU session procedure for UAS and C2 communication. | 1 | 90% | 90% |  |  | 90% | 90%
13 | Y | 38.523-1 | 10.1.4.x | UAS / UE requested PDU session modification / C2 authorization | VOID |  |  |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
14 |  | 38.523-2 | 4.1, 4.2 | Applicability for UAS Test Case for Initial Registration |  | Qualcomm | RAN5#100 (Aug-23) | R5-235421, R5-235422 |  | 1 | 100% | 100% |  |  | 100% | 100%
25 |  | 38.523-3 | 4.1, 4.2 | Applicability for UUAA MM deregistration testcases |  | Nokia | RAN5#100 (Aug-23) | R5-235422 |  | 1 | 100% | 100% |  |  | 100% | 100%
26 |  | 38.523-4 | 4.1, 4.2 | Applicability for UAS Test Cases 10.1..4.2 |  | Ericsson | RAN5#101 (Nov-23) | R5-236892, |  | 1 | 100% | 100% |  |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
15 |  | 38.523-3 | NA | Introduction of General and Signaling Test Environment for Support of Uncrewed Aerial Systems Connectivity, Identification and Tracking |  | Qualcomm |  |  |  | 1 | 30% | 30% |  |  | 0% | 0%
Overall WP completion
16 |  |  |  | Overall Definition and scope of WI | [5 empty] | 1 | 65% (+32.5%) | 65% (+32.5%) |  |  | 65% | 65%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.