## Cover sheet
3GPP TSG RAN WG5 Meeting #108 | [7 empty] | R5-253902
Bengaluru, India, August 25 - 29, 2025
Agenda Item: | 7.5.2
Source: | CMCC, CBN
Title: | WP UE Conformance - Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28
Work item code: | NR_n28_PC2_40MHz_CBW-UEConTest
Release: | Rel-19
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
At the RAN#107 meeting in March 2025 the Rel-19 RAN5 work item for UE Conformance of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item to introduce the Rel-19 PC2 and 40MHz CBW in n28 into RAN5 test specifications. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet 'WP' shows the status for each impacted/newly introduced test cases.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 92% (+38%) | 1 | 1
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 92% (+37.6%) | 1 | 1
FR1 |  | 92% (+37.6%) | 1 | 1
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+25%) |  |  | 100% (+25%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%)
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 90.9% (+37.1%) | 1 | 1 | 90.9% (+37.1%) | 1 | 1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-250249 | New WID on UE Conformance - Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_n28_PC2_40MHz_CBW-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance for NR PC2 and 40MHz n28 support comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
92% (+37.6%)
41 (+20)
38.2 (+19)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.3.1.0A | Mid test channel bandwidth | Update Mid test channel bandwidth for NR operating band n28 if necessary | CMCC | RAN5#108 (Aug-25) | R5-252102 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% |  | 100%
2 |  | 38.508-1 | 4.3.1.0B | Low test channel bandwidth | Update Low test channel bandwidth for NR operating band n28 if necessary | CMCC | RAN5#108 (Aug-25) |  | CMCC Dan Song <songdan@chinamobile.com> | 0 | 0% | 0% |  | 0%
3 |  | 38.508-1 | 4.3.1.0C | High test channel bandwidth | Update High test channel bandwidth for NR operating band n28 if necessary | CMCC | RAN5#108 (Aug-25) | R5-252102 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% |  | 100%
4 |  | 38.508-1 | 4.3.1.1.1.28 | Reference test frequencies for NR operating band n28 | Introduction of Reference test frequencies for NR operating band n28 with CBW=40MHz | CMCC | RAN5#108 (Aug-25) | R5-252102 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of common implementation conformance statements for Rel-19 PC2 40MHz n28 UE | CMCC | RAN5#108 (Aug-25) | R5-253907 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6 |  | 38.521-1 | 5.3.5 | UE channel bandwidth per operating band | Update "Table 5.3.5-1: Channel Bandwidths for each NR band" for n28 with CBW=40MHz | CMCC | RAN5#108 (Aug-25) | R5-253440 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.521-1 | 6.2.1 | UE maximum output power | [5 empty] | 0
7 |  | 38.521-1 | 6.2.1.3 | Minimum conformance requirements | Add PC2 and toleranxe values for n28, including descriptive text after the table | CMCC | RAN5#108 (Aug-25) | R5-253903 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
8 |  | 38.521-1 | 6.2.1.5 | Test requirement | Add the test requirement for PC2 n28 | CMCC | RAN5#108 (Aug-25) | R5-253903 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.2.2 | UE maximum output power reduction | [5 empty] | 0
9 |  | 38.521-1 | 6.2.2.3 | Minimum conformance requirements | Update "Table 6.2.2.3-3: ∆MPR" for PC2 40MHz n28 | CMCC | RAN5#108 (Aug-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
10 |  | 38.521-1 | 6.2.2.5 | Test requirement | Update "Table 6.2.2.5-2a" for PC2 40MHz n28 with ∆MPR=0.5dB | CMCC | RAN5#108 (Aug-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
|  | 38.521-1 | 6.2.3 | UE additional maximum output power reduction | [5 empty] | 0
|  | 38.521-1 | 6.2.3.3 | Minimum conformance requirements | [5 empty] | 0
11 |  | 38.521-1 | 6.2.3.3.1 | General | Update NS_17 and NS_18 related information in "Table 6.2.3.3.1-1: Additional maximum power reduction (A-MPR)" for PC2 40MHz n28 as per "Table 6.2.3.1-1: Additional maximum power reduction (A-MPR)" in TS 38.101-1 | CMCC | RAN5#108 (Aug-25) | R5-253438 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
12 |  | 38.521-1 | 6.2.3.3.13 | A-MPR for NS_18 | 1) Update "Table 6.2.3.3.13-0" and "Table 6.2.3.3.13-1" for PC3 40MHz n28 2) Add new table "Table 6.2.3.3.13-2: A-MPR regions for NS_18 (power class 2)" 3) Add new table "Table 6.2.3.3.13-3: A-MPR for NS_18 for 1Tx and 2Tx (power class 2)" | CMCC | RAN5#110 (Feb-26) | R5-253438 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
13 | Y | 38.521-1 | 6.2.3.3.33 | A-MPR for NS_17 | Add new tables for "A-MPR for NS_17" as per "6.2.3.33 A-MPR for NS_17" in TS 38.101-1 | CMCC | RAN5#110 (Feb-26) | R5-253438 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
|  | 38.521-1 | 6.2.3.4 | Test description | [5 empty] | 0
14 |  | 38.521-1 | 6.2.3.4.1 | Initial conditions | 1) Update "Table 6.2.3.4.1-11: Test Configuration table for NS_18" for 40MHz and indicate "(Power Class 3)" in the table title; 2) Add new test configuration table for "NS_18(Power Class 2)"; 3) Add new test configuration table for "NS_17(Power Class 2)" | Ericsson | RAN5#109 (Nov-25) | R5-255232 | Ericsson Lawrence Moore<lawrence.moore@ericsson.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
34 |  | 38.521-1 | 6.2.3.4.3 | Message contents | Update the message condition for n28 | Huawei | RAN5#109 (Nov-25) | R5-255232 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
15 |  | 38.521-1 | 6.2.3.5 | Test requirement | 1) Update "Table 6.2.3.5-8: UE Power Class 3 test requirements (NS_18)" for 40MHz; 2) Add new table "Table 6.2.3.5-8a: UE Power Class 2 test requirements (NS_18)"; 3) Add new table "Table 6.2.3.5-9: UE Power Class 2 test requirements (NS_17)" | Ericsson | RAN5#109 (Nov-25) | R5-255232 | Ericsson Lawrence Moore<lawrence.moore@ericsson.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.2D.1 | UE maximum output power for UL MIMO | [5 empty] | 0
16 |  | 38.521-1 | 6.2D.1.3 | Minimum conformance requirements | Add PC2 and toleranxe values for n28 | CMCC | RAN5#108 (Aug-25) | R5-255264 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
17 |  | 38.521-1 | 6.2D.1.5 | Test requirement | Add the test requirement for PC2 n28 | CMCC | RAN5#108 (Aug-25) | R5-255264 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.2D.2 | UE maximum output power reduction for UL MIMO | [5 empty] | 0
18 |  | 38.521-1 | 6.2D.2.5 | Test requirement | Add the test requirement for PC2 n28, in Table 6.2D.2.5-2,Table 6.2D.2.5-2a, Table 6.2D.2.5-2b, Table 6.2D.2.5-2c | CMCC | RAN5#108 (Aug-25) | R5-255265 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | [5 empty] | 0
19 |  | 38.521-1 | 6.2D.3.4.1 | Initial conditions | Add test configuration table for NS_17 and NS_18 for PC2. （NS_18 for PC3 is missing) | Huawei | RAN5#108 (Aug-25) | R5-255233 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
20 |  | 38.521-1 | 6.2D.3.4.3 | Message contents | Add message exception for NS_17 and NS_18 | Huawei | RAN5#108 (Aug-25) |  | Huawei Guchunying <guchunying@huawei.com> | 1 | 0% | 0% |  | 0%
21 |  | 38.521-1 | 6.2D.3.5 | Test requirement | Add test requirements for NS_17 and NS_18 for PC2 （NS_18 for PC3 is missing) | Huawei | RAN5#108 (Aug-25) | R5-255233 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.2G.1 | UE maximum output power for Tx Diversity | [5 empty] | 0
22 |  | 38.521-1 | 6.2G.1.3 | Minimum conformance requirements | Add PC2 and toleranxe values for n28 | CMCC | RAN5#108 (Aug-25) | —— | CMCC,Luyang Zhao <zhaoluyang@chinamobile.com> No changes are needed. | 1 | 100% (+100%) | 100% (+100%) |  | 100%
23 |  | 38.521-1 | 6.2G.1.5 | Test requirement | Add the test requirement for PC2 n28 | CMCC | RAN5#108 (Aug-25) | R5-255266 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.2G.2 | UE maximum output power reduction for Tx Diversity | [5 empty] | 0
24 |  | 38.521-1 | 6.2G.2.5 | Test requirement | Add the test requirement for PC2 n28, considering 0.5dB deltaMPR for 40MHz | Huawei | RAN5#108 (Aug-25) | R5-255267 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.2G.3 | UE additional maximum output power reduction for Tx Diversity | [5 empty] | 0
25 |  | 38.521-1 | 6.2G.3.2 | Test applicability | Update Test applicability for NS_18. | Huawei | RAN5#108 (Aug-25) | R5-254784 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
25 |  | 38.521-1 | 6.2G.3.3 | Minimum conformance requirements | Add test configuration table for NS_17 and NS_18 for PC2 (PC3 is missing) | Huawei | RAN5#108 (Aug-25) | R5-254784 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
26 |  | 38.521-1 | 6.2G.3.4.1 | Initial conditions | Add test configuration table for NS_17 and NS_18 for PC2 (PC3 is missing) | Huawei | RAN5#108 (Aug-25) | R5-254784 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
27 |  | 38.521-1 | 6.2G.3.4.3 | Message contents | Add message exception for NS_17 and NS_18 for PC2 | Huawei | RAN5#108 (Aug-25) | R5-254784 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
28 |  | 38.521-1 | 6.2G.3.5 | Test requirement | Add test requirements for NS_17 and NS_18 for PC2 (PC3 is missing) | Huawei | RAN5#108 (Aug-25) | R5-254784 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.5.3.3 | Additional spurious emissions | [5 empty] | 0
29 |  | 38.521-1 | 6.5.3.3.3.3 | Minimum conformance requirements (network signalling value "NS_18") | Adding 40MHz to NS_18 | Huawei | RAN5#108 (Aug-25) | R5-255232 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
30 |  | 38.521-1 | 6.5.3.3.4.1 | Initial conditions | Adding test configuration information for NS_17 and NS_18 for PC2; For existing test configuration table for NS_18 PC3, add 40MHz. | Huawei | RAN5#108 (Aug-25) | R5-255232 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
31 |  | 38.521-1 | 6.5.3.3.5.3 | Test requirement (network signalling value “NS_18”) | Adding 40MHz to NS_18 | Huawei | RAN5#108 (Aug-25) | R5-255232 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.5D.3_1.3 | Additional spurious emissions for UL MIMO (Rel-16 onward) | [5 empty] | 0
32 |  | 38.521-1 | 6.5D.3_1.3.4.1 | Initial conditions | Adding test configuration information for NS_17 and NS_18 for PC2; (PC3 is missing) Checking test configuration and exceptions for NS_18. | Huawei | RAN5#108 (Aug-25) | R5-255233 | Huawei Guchunying <guchunying@huawei.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.5G.3.3 | Additional spurious emissions for Tx Diversity | [5 empty] | 0
33 |  | 38.521-1 | 6.5G.3.3.4 | Test description | Update editor's note Check references in 6.5G.3.3.4 | Huawei | RAN5#108 (Aug-25) | R5-254784 | Huawei Guchunying <guchunying@huawei.com> Refer to TC 6.5.3.3 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
|  | 38.521-1 | 7.3.2 | Reference sensitivity power level | [5 empty] | 0
16 |  | 38.521-1 | 7.3.2.3 | Minimum conformance requirements | 1) Update "Table 7.3.2.3-1a: Two antenna port reference sensitivity QPSK PREFSENS for FDD bands" for n28 with CBW=40MHz; 2) Update "Table 7.3.2.3-1c: Reference Sensitivity Degradation from PC3 to PC2 for FDD bands for UE not supporting Tx Diversity" for n28 with CBW=40MHz; 3) Update "Table 7.3.2.3-1d Reference Sensitivity Degradation from PC3 to PC2 for FDD bands for UE supporting Tx Diversity" for n28 with CBW=40MHz; 4) Update "Table 7.3.2.3-3: Uplink configuration for reference sensitivity" for n28 with CBW=40MHz | CMCC | RAN5#108 (Aug-25) | R5-252101 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
|  | 38.521-1 | 7.3.2.4 | Test description | [5 empty] | 0
17 |  | 38.521-1 | 7.3.2.4.1 | Initial conditions | Update "Table 7.3.2.4.1-3: Uplink configuration for reference sensitivity, LCRB @ RBstart format" for n28 with CBW=40MHz; | Ericsson | RAN5#109 (Nov-25) | R5-253439 | Ericsson Lawrence Moore<lawrence.moore@ericsson.com> | 1 | 100% | 100% |  | 100%
18 |  | 38.521-1 | 7.3.2.5 | Test requirement | 1) Update "Table 7.3.2.5-1a: Two antenna port Reference sensitivity QPSK PREFSENS for FDD bands for PC3" for PC3 n28 with CBW=40MHz; 2) Update "Table 7.3.2.5-2a: Four antenna port Reference sensitivity QPSK PREFSENS FDD bands for PC3" for PC3 n28 with CBW=40MHz | Ericsson | RAN5#109 (Nov-25) | R5-253439 | Ericsson Lawrence Moore<lawrence.moore@ericsson.com> | 1 | 100% | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
19 |  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria if necessary |  | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
20 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for 38.521-1 Rel-19 PC2 40MHz n28 test case if necessary. | CMCC | RAN5#109 (Nov-25) |  | CMCC Dan Song <songdan@chinamobile.com> | 0.1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
21 |  | 38.905 | 4.1.2.1 | A-MPR, A-SEM and A-SE FR1 test cases for single carrier and UL MIMO | Update TP analysis for NS_17 and NS_18 | Ericsson | RAN5#109 (Nov-25) | R5-255234 | Ericsson Lawrence Moore<lawrence.moore@ericsson.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.