## Cover sheet
3GPP TSG-RAN WG5 Meeting #108 | [7 empty] | R5-254645
Bengaluru, IN, 29th - 25th Aug 2025
Agenda Item: | 7.5.2
Source: | China Telecom, MediaTek
Title: | WP for UE Conformance – NR power class 2 RedCap (Reduced Capability) UE in FR1
Work item code: | NR_PC2_RedCap_UE-UEConTest
Release: | Rel-19
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
3GPP TSG RAN WG4 has created the WID for NR power class 2 RedCap (Reduced Capability) UE in FR1. The WI is aimed to increase the maximum transmit power from PC3 23dBm to PC2 26dBm for RedCap UE and extend cell coverage for NR deployment as well as improve the data rate of cell edge RedCap UE. Following requirements are introduced under this WI:  Apply the PC2 RF requirements for non-RedCap UE to RedCap UE, based on 1Tx architecture with 26 dBm PA. − The PC2 RF requirements include: UE maximum output power, Tx power tolerance, MPR, A-MPR and RSD requirements if needed. − For TDD bands, PC2 RF requirements for non-RedCap UE can be re-used for PC2 RedCap UE in a band agnostic way. o Note: Not differentiate the applicable form factors for TDD bands in the specification. The core part of this WI will be 100% completed at RAN#108 (June 2025). It’s time for 3GPP TSG RAN WG5 to start working on the corresponding conformance testing part to meet the industry interest.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0% | 0%
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 5% (+5%) | 0% | 0%
FR1 |  | 5% (+5%) | 0 | 0
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
NR RF/RRM
FR1 RF Tx test cases | 38.521-1 Tx | 0% |  |  | 0%
FR1 RF Rx test cases | 38.521-1 Rx | 0% |  |  | 0%
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905
5 References
[1] RP-251456 | New WID on UE Conformance – NR power class 2 RedCap (Reduced Capability) UE in FR1
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for UE Conformance – NR power class 2 RedCap (Reduced Capability) UE in FR1 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_PC2_RedCap_UE-UEConTest
WP Scope: |  | The objective of this work item is to develop RF UE conformance test cases for NR power class 2 RedCap (Reduced Capability) UE in FR1, and this work item will involve the corresponding NR bands.
WP Resp: |  | Zhengyang Liu, Daiwei Zhou |  |  | liuzy18@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp:
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
5% (+5%)
6 (+6)
3.2 (+3.2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4 | Introduction of Test Environment | Add related Test Environment | All companies | RAN5#113 (Nov-26) |  |  | 0.1 | 0% | 0% |  | 0%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Tx
2 |  | 38.521-1 Tx | 6.2I.1 | UE maximum output power for RedCap | Add PC2 test requirement for RedCap UE | MediaTek | RAN5#113 (Nov-26) |  |  | 1 | 0% | 0% |  | 0%
3 |  | 38.521-1 Tx | 6.2I.2a | UE maximum output power for eRedCap | Add PC2 test requirement for eRedCap UE | MediaTek | RAN5#113 (Nov-26) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
4 |  | 38.521-1 Rx | 7.3I.2 | Reference sensitivity power level for RedCap | Add PC2 RedCap UE equipped with 2 Rx antenna ports reference sensitivity test case | China Telecom | RAN5#113 (Nov-26) |  |  | 1 | 0% | 0% |  | 0%
5 |  | 38.521-1 Rx | 7.3I.2 | Reference sensitivity power level for RedCap | Add PC2 RedCap UE equipped with 1 Rx antenna ports reference sensitivity test case for band n1 | China Telecom | RAN5#113 (Nov-26) |  |  | 1 | 0% | 0% |  | 0%
6 |  | 38.521-1 Rx | 7.3I.2 | Reference sensitivity power level for RedCap | Add PC2 RedCap UE equipped with 1 Rx antenna ports reference sensitivity test case for band n3 | China Telecom | RAN5#113 (Nov-26) |  |  | 1 | 0% | 0% |  | 0%
7 |  | 38.521-1 Rx | 7.3I.3 | Reference sensitivity power level for eRedCap | Add PC2 eRedCap UE test requirements | China Telecom | RAN5#113 (Nov-26) |  |  | 1 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
8 |  | 38.522 | 4.1.1 | RF/FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1 | All companies | RAN5#113 (Nov-26) |  |  | 0.1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
9 |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | Add TP analysis for test cases in 38.521-1 |  | RAN5#113 (Nov-26) |  |  | TBD | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.