## Slide 1
SA1 Report to TSG SA#100 SP-230505
José Almodóvar
SA1 Chair, KPN
Alain Sultan
SA1 Secretary, ETSI MCC
SP-230505 3GPP TSG#100, 12 – 16 June 2023, Taipei
© 3GPP 2023

## Slide 2: Short Summary

## Slide 3: Summary - overall
SA1 Rel-19 work is on track:
  Our goal remains to have 80% of the normative work by August 2023 (in time for Stage-2 content definition).
  Our achievements at SA#100 are:
    Studies: All TRs are over 80 % completion (including 7 TRS for approval)
      except fora newly approved TR just started (on FS_ISN).
    Normative: 8 corresponding normative Rel-19 WIDs for approval
      also 2 new “mini WIDs” for approval.
For two topics, namely AmbientIoT and DualSteer, the TRs and corresponding normative WIDs were not agreed due to sustained objections at SA1#102 on the requirements and KPIs.
Cooperation among companies will be required to solve this issue.

## Slide 4
3GPP Release 19 timeline
TSG#93-e
SA1 Stage 1 80%
100%
TSG#94-e
TSG#95-e
TSG#96
TSG#97-e
TSG#98
TSG#99
TSG#100
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
RAN4
content def.
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
RAN Rel-19 workshop
SA Rel-19
Workshop (TBC)
SA St.2 Content approval
SA1 expected completion dates:
SA1#103 21-25 Aug 2023 80% normative ready
SA1#104 13-17 Nov 2023 100% normative ready

## Slide 5: General Information and statistics

## Slide 6: SA1 Officials
Chairman:
  Jose Almodovar (KPN) 1
Vice Chairmen:
  Xu Xia (China Telecom)2
  Yusuke Nakano (KDDI)3
Secretary:
  Alain Sultan (MCC)
1 Re-elected for third term May 2023
2 Re-elected for second term November 2021
3 Elected November 2021

## Slide 7: Statistics
 | Q4 21 | Q1 22 | Q2 22 | Q3 22 | Q4 22 | Q1 23 | Q2 23
Attended delegates | e-meeting | e-meeting | e-meeting | e-meeting | 334_F2F + 69_remote | 184_F2F + 88_remote | 276_F2F + 69_remote
Docs at meeting end | 328+290r | 213+236r | 293+437r | 397+711r | 720 | 811 | 786
Docs at meeting start | 200 | 170 | 197 | 295 | 278 | 320 | 326
Incoming LS | 24 | 23 | 22 | 29 | 26 | 21 | 32
Outgoing LS | 8 | 6 | 8 | 2 | 7 | 5 | 10
Agreed CRs | 80 | 14 | 17 | 10 | 12 | 8 | 26
Agreed alignment CRs | 6 | 0 | 3 | 0 | 0 | 0 | 4
New Study Items | 0 | 6 | 6 | 0 | 0 | 1 | 0
New Work Items | 0 | 0 | 1 | 4 | 1 | 4 | 10
Revised WID/SID | 1 | 0 | 2 | 1 | 0 | 1 | 0
TR/TS for Information | 0 | 0 | 0 | 1 | 2 | 6 | 0
TR/TS for Approval | 2 | 0 | 0 | 0 | 1 | 0 | 7

## Slide 8: Meeting Calendar
Meeting | Date | Location
SA1#103 | 21-25 Aug 2023 | Gothenburg
SA1#104 | 13-17 Nov 2023 | Chicago - (mega meeting)
SA1#105 | 26 Feb - 1 Mar 2024 | Europe
SA1#106 | 27- 31 May 2024 | Korea

## Slide 9: Previous SA1 reports
TSG Meeting & location | Tdoc number | SA1 meeting(s) covered & location
SA#89e | SP-200778 | SA1#91e, e-meeting
SA#90e | SP-201022 | SA1#92e, e-meeting
SA#91e | SP-210195 | SA1#93e, e-meeting
SA#92e | SP-210500 | SA1#94e, e-meeting; SA1#94bis-e, e-meeting
SA#93e | SP-211029 | SA1#95e, e-meeting
SA#94e | SP-211506 | SA1#96e, e-meeting
SA#95e | SP-220077 | SA1#97e, e-meeting
SA#96e | SP-220427 | SA1#98e, e-meeting
SA#97e | SP-220931 | SA1#99e, e-meeting
SA#98e | SP-221256 | SA1#100, Toulouse
SA#99 | SP-230214 | SA1#101, Athens

## Slide 10: Work Summary: pre Rel-19 Work

## Slide 11: Pre-Rel-19 agreed CR packages
CR Package title | #CRs | Release
TEI12 | 4 | Rel-15
AHGC | 2 | Rel-18
AIML_MT | 2 | Rel-18
MINT, SENSE | 2 | Rel-18
MPS_WLAN | 3 | Rel-18
TEI18 | 2 | Rel-18

## Slide 12
TEI15 - Agenda item 15 Rel-15 CRs: |  |  |  |  |  | 
SP-230525 | S1-231684 | Aligning the RAN sharing related definitions for quality improvement | TEI15 | 22.101 | 0589r- | Rel-15
 | S1-231685 | Aligning the RAN sharing related definitions for quality improvement | TEI15 | 22.101 | 0590r- | Rel-16
 | S1-231686 | Aligning the RAN sharing related definitions for quality improvement | TEI15 | 22.101 | 0591r1 | Rel-17
 | S1-231393 | Aligning the RAN sharing related definitions for quality improvement | TEI15 | 22.101 | 0588r- | Rel-18
Release-15

## Slide 13: Release-18 (1/2)
AIML_MT - Agenda item 18.1 Rel-18 CRs: |  |  |  |  |  | 
SP-230527 | S1-231473 | Clarification on AI-ML KPIs | AIML_MT | 22.261 | 0685r2 | Rel-18
 | S1-231474 | Clarification on AI-ML KPIs | AIML_MT | 22.261 | 0686r2 | Rel-19
AHGC - Agenda item 18.1 Rel-18 CRs: |  |  |  |  |  | 
SP-230526 | S1-231475 | Notification of updated list of participants of Ad hoc Group Emergency Alert | AHGC | 22.280 | 0161r3 | Rel-18
 | S1-231719 | Notification of updated list of participants of Ad hoc Group Emergency Alert | AHGC | 22.280 | 0163r3 | Rel-19
MINT,SENSE - Agenda item 18.1 Rel-18 CRs: |  |  |  |  |  | 
SP-230530 | S1-231371 | Clarification on selection of Forbidden PLMN during Disaster Conditions when Operator controlled signal threshold applies | MINT, SENSE | 22.011 | 0350r1 | Rel-18
 | S1-231372 | Clarification on selection of Forbidden PLMN during Disaster Conditions when Operator controlled signal threshold applies | MINT, SENSE | 22.011 | 0351r1 | Rel-19

## Slide 14: Release-18 (2/2)
MPS_WLAN - Agenda item 18.1 Rel-18 CRs: |  |  |  |  |  | 
SP-230531 | S1-231205 | Correction to MPS requirements | MPS_WLAN | 22.153 | 0059r- | Rel-18
 | S1-231206 | Correction to MPS requirements | MPS_WLAN | 22.153 | 0060r- | Rel-19
TEI18 - Agenda item 18.1 Rel-18 CRs: |  |  |  |  |  | 
SP-230534 | S1-231396 | Corrections of scope and reference including editorial fixes | TEI18 | 22.268 | 0078r1 | Rel-18
 | S1-231398 | UE based geo-fencing requirements for KPAS | TEI18 | 22.268 | 0079r1 | Rel-19
TEI18 - Agenda item 18.1 Rel-18 CRs: |  |  |  |  |  | 
SP-230535 | S1-231756 | Multiple Access Technologies | TEI19, MPS_WLAN | 22.153 | 0062r2 | Rel-18

## Slide 15: Work Summary: Rel-19 Work

## Slide 16
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
950003 | Study on Integrated Sensing and Communication | FS_Sensing | 06/06/2023 | 80% | SP-220717 | 90% | TR sent for approval, target date changed to 09/2023
1000026 | Integrated Sensing and Communication | Sensing | 12/12/2023 | - | SP-230507 | 0% | NEW
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 03/03/2023 | 80% | SP-220085 | 90% | TR NOT sent for approval, normative WID not approved yet
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | 03/03/2023 | 75% | SP-220353 | 90% | TR 22.856 for approval
1000028 | Localized Mobile Metaverse Services | Metaverse | 12/12/2023 | - | SP-230509 | 0% | NEW
950006 | Study on Network Sharing Aspects | FS_NetShare | 03/03/2023 | 80% | SP-220087 | 95% | TR 22.851 for approval
1000029 | Network Sharing Aspects | NetShare | 12/12/2023 | - | SP-230511 | 35% | NEW
950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | 09/09/2023 | 50% | SP-220437 | 80% | New target:: Dec. 2023
1000031 | FRMCS Phase 5 | FRMCS_Ph5 | 12/12/2023 | - | SP-230512 | 0% | NEW
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | 06/06/2023 | 75% | SP-220439 | 95% | TR 22.876 for approval
1000030 | AI/ML Model Transfer Phase2 | AIML_MT_Ph2 | 12/12/2023 | - | SP-230514 | 0% | NEW
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | 06/06/2023 | 80% | SP-220679 | 90% | TR 22.865 for approval
1000024 | Satellite access - Phase 3 | 5GSAT_Ph3 | 12/12/2023 | - | SP-230516 | 0% | NEW
960017 | Study on UAV Phase 3 | FS_UAV_Ph3 | 06/06/2023 | 65% | SP-220954 | 95% | TR 22.843 for approval
1000032 | UAV Phase 3 | UAV_Ph3 | 12/12/2023 | - | SP-230518 | 0% | NEW
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | 06/06/2023 | 75% | SP-220445 | 90% | Normative WID not approved yet
SA1 Work Plan Rel-19 (1/3)

## Slide 17
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
960019 | Study on Energy Efficiency as service criteria | FS_EnergyServ | 06/06/2023 | 70% | SP-230235 | 90% | TR 22.882 for approval
1000033 | Energy Efficiency as service criteria | EnergyServ | 12/12/2023 | - | SP-230520 | 0% | NEW
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | 09/09/2023 | 70% | SP-220447 | 80% | 
990053 | Study on Interconnect of SNPN | FS_ISN | 12/12/2023 | 0% | SP-230236 | 30% | Study ongoing
990052 | Supporting UE Mobility for XR Services | XRMobility | 06/06/2023 | 50% | SP-230233 | 50% | 
990049 | PS Data Off for IMS Data Channel Service | IMSDCDataOff | 03/03/2023 | 0% | SP-230227 |  | ??
1000025 | UE-to-UE Multi Hop Relay | UEMHopRelay | 06/06/2023 | - | SP-230521 | 100% | New “Mini WID”
1000027 | Preventing Excessive Data Exposure within an NPN | SecNPN | 06/06/2023 | - | SP-230523 | 100% | New “Mini WID”
960015 | Study on roaming value added services | FS_RVAS | 12/12/2022 | 100% | SP-220442 | - | 
990051 | Roaming Value-Added Services | RVAS | 03/03/2023 | 100% | SP-230231 | - | 
850044 | Study on Supporting of Railway Smart Station Services | FS_RAILSS | 08/09/2022 | 100% | SP-190838 | - | 
990050 | Edge Computing for Industrial Scenarios | EDGINDUS | 03/03/2023 | 100% | SP-230229 | - | 
970044 | Multi-path relay | MultiRelay | 19/09/2022 | 100% | SP-220943 | - | 
SA1 Work Plan Rel-19 (2/3)

## Slide 18
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
970044 | Multi-path relay | MultiRelay | 19/09/2022 | 100% | SP-220943 | - | 
970043 | Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services | DTT4MBS | 19/09/2022 | 100% | SP-220941 | - | 
SA1 Work Plan Rel-19 (3/3)
For more information, see the full Work Plan at: https://ftp.3gpp.org/information/Work_Plan

## Slide 19: Rel-19 Study Items and corresponding Normative Items

## Slide 20: FS_Sensing
TR 22.837 for approval at this plenary in SP-230506 (Cover Sheet S1-231816 + TR S1-231331)
Progress since previous SA meeting
  Updated and merged definitions to cover target sensing service area and moving target sensing service area. New definitions on sensing assistance.
  Editorial and common terminology changes
  Resolving of Editor’s notes
  22 CPRs agreed
  KPI consolidation agreed with Editor’s notes
  TR sent for approval
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/23): 100%
  Topics to be completed: Finalization of CPRs and consolidated KPIs
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950003 | Study on Integrated Sensing and Communication | FS_Sensing | 06/06/2023 | 80% | SP-220717 | 90% | TR sent for approval, target date changed to 09/2023

## Slide 21: Sensing
New WID for approval at this plenary in SP-230507 (from S1-231778)
Progress since previous SA meeting
  WID agreed
  Skeleton agreed
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/23): 80%
  Topics to be completed: Consolidated CPR and KPIs to be introduced in new TS and reference to be provided in TS22.261
  SA1#104 (11/23): 100%
  Topics to be completed: Finalization of normative work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000026 | Integrated Sensing and Communication | Sensing | 12/12/2023 | - | SP-230507 | 0% | New WID

## Slide 22: FS_AmbientIoT
Progress since previous SA meeting
  20+ pCR to update the use cases have been agreed, focusing on update of KPI values, removal of the FFS/EN and further polish of the potential requirement
  3 pCR on CPR consolidation and KPI consolidation have been agreed
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/2023): 95%
  Topics to be completed: Resume CPR and KPI consolidation
  update of KPI etc.
  SA1#104 (11/2023): 100%
  Topics to be completed: Finalize CPR and KPI consolidation
  Remove all the FFS and EN.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 06/06/2023 | 80% | SP-220085 | 90% | TR NOT sent for approval

## Slide 23: FS_Metaverse
Progress since previous SA meeting
  TR conclusions added.
  Remaining Editor's Notes have been resolved.
  The consolidation of potential requirements and KPIs have been completed.
  Clean up and clarification.
  Requirements updated (that previously were under discussion but not yet agreed.)
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/2023): 100%
  Topics to be completed: Consolidate agreed PRs and KPIs, Final clean up
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | 03/03/2023 | 75% | SP-220353 | 90% | TR 22.856 for approval

## Slide 24: Metaverse
New WID for approval at this plenary in SP-230509 (from S1-231790)
Progress since previous SA meeting: not applicable (new item)
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/2023): 80%
  Topics to be completed: Create and substantially complete the work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000028 | Localized Mobile Metaverse Services | Metaverse | 12/12/2023 | - | SP-230509 | 0% | New WD

## Slide 25: FS_NetShare
TR 22.851 for approval at this plenary in SP-230510 (Cover Sheet S1-231796 + TR S1-231336)
Progress since previous SA meeting
  Use cases have been updated,
  Alignment of the whole TR with the definitions has been completed,
  Consolidations have been done following the categorizations,
  Conclusion has been reached.
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (Aug 2023): 100%
  Topics to be completed: final clean up
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950006 | Study on Network Sharing Aspects | FS_NetShare | 03/03/2023 | 80% | SP-220087 | 95% | TR for approval/TSG SA Meeting #100 (June)

## Slide 26: NetShare
            New WID for approval at this plenary in SP-230511 (from S1-231806)
Progress since previous SA meeting
  WID agreed based on TR 22.851.
  2 CRs agreed.
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (Aug 2023): 80%
    Topics to be completed: CRs with requirements.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000029 | Network Sharing Aspects | NetShare | 12/12/2023 | - | SP-230511 | 35% | New WID
NetShare- Agenda item 19 Rel-19 CRs: |  |  |  |  |  | 
SP-230533 | S1-231735 | Add Indirect Network Sharing to TS 22.261 | NetShare | 22.261 | 0682r2 | Rel-18
 | S1-231736 | Add definitions for Indirect Network Sharing | NetShare | 22.261 | 0684r1 | Rel-19

## Slide 27: FS_FRMCS_Ph5
Progress since previous SA meeting
  Agreed CR to the TR22.989, refining of 4 existing use cases
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/23): 90% Topics to be completed: Complete the update of existing use cases
  SA1#104 (11/23): 100% Topics to be completed: Clean-up and finalization
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950003 | Study on Integrated Sensing and Communication | FS_Sensing | 06/06/2023 | 80% | SP-220717 | 90% | TR sent for approval, target date changed to 09/2023
FS_FRMCS_Ph5 - Agenda item 19 Rel-19 CRs: |  |  |  |  |  | 
SP-230528 | S1-231630 | Introduction and updates of Smart railway definitions | FS_FRMCS_Ph5 | 22.989 | 0024r1 | Rel-19
 | S1-231633 | Clean-up of Railway Emergency Communication related use cases | FS_FRMCS_Ph5 | 22.989 | 0026r1 | Rel-19
 | S1-231731 | Transportation convenience service for the passengers for the reduced mobility | FS_FRMCS_Ph5 | 22.989 | 0027r3 | Rel-19
 | S1-231732 | Multiple concurrent mobility services | FS_FRMCS_Ph5 | 22.989 | 0028r3 | Rel-19

## Slide 28: FRMCS_Ph5
New WID for approval at this plenary in SP-230512 (from S1-231806)
Progress since previous SA meeting
  Submission of new WID in order to introduce into stage 1 MC specifications, requirements derived from FS_FRMCS_Ph5
  Agreed CR in this new WID for the usage of multi-talker control in MCPTT Ad hoc Groups used for Railway Emergency Voice communication
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/23): 50%
  SA1#104 (11/23): 100%
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000031 | FRMCS Phase 5 | FRMCS_Ph5 | 12/12/2023 | - | SP-230512 | 0% | NEW
FRMCS_Ph5 - Agenda item 19 Rel-19 CRs: |  |  |  |  |  | 
SP-230529 | S1-231635 | Usage of multi-talker control for Ad hoc Group Emergency Voice Communications | FRMCS_Ph5 | 22.179 | 0076r2 | Rel-19

## Slide 29: FS_AIML_MT_Ph2
TR 22.876 for approval at this plenary in SP-230513 (Cover Sheet S1-231814 + TR S1-231338)
Progress since previous SA meeting
  Consolidated requirements and global KPIs consolidated discussed.
  Conclusions agreed.
  TR sent for approval
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/23): 100%
  Topics to be completed: Clean up.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | 06/06/2023 | 75% | SP-220439 | 95% | TR 22.876 for approval

## Slide 30: AIML_MT_Ph2
New WID for approval at this plenary in SP-230514 (from S1-231807)
Progress since previous SA meeting: not applicable (new item)
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (Aug 2023): 80%
  Topics to be completed: CRs with requirements.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000030 | AI/ML Model Transfer Phase2 | AIML_MT_Ph2 | 12/12/2023 | - | SP-230514 | 0% | New WID

## Slide 31: FS_5GSAT_Ph3
TR 22.865 for approval at this plenary in SP-230515 (Cover Sheet S1-231302 + TR S1-231339)
Progress since previous SA meeting
  Updated use cases and new potential requirements
  Resolved last editor's notes
  Final clean up
  Agreed consolidated potential requirements
  Agreed conclusions
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (Aug 2023): 100%
    Add potential new CPR based on new requirements agreed in May
    Final review
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | 06/06/2023 | 80% | SP-220679 | 90% | TR 22.865 for approval

## Slide 32: 5GSAT_Ph3
New WID for approval at this plenary in SP-230516 (from S1-231738)
Progress since previous SA meeting: not applicable (new item)
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/23): 100%
  Topics to be completed: Finalization of CPRs and consolidated KPIs
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000024 | Satellite access - Phase 3 | 5GSAT_Ph3 | 12/12/2023 | - | SP-230516 | 0% | New WID

## Slide 33: FS_UAV_Ph3
TR 22.843 for approval at this plenary in SP-230517 (Cover Sheet S1-231799 + TR S1-231347)
Progress since previous SA meeting
  2 pCRs on editorial clean-up and abbreviations
  1 pCR on Overview section
  3 new use cases agreed: Multi-PLMN: alternative NWs, Multi-PLMN: concurrent NWs and UAV aerial fly zones.
  3 pCRs on updating existing use cases:
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103: 100%
  Final clean-up for the TR and removal of final Editor’s Notes
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
960017 | Study on UAV Phase 3 | FS_UAV_Ph3 | 06/06/2023 | 65% | SP-220954 | 95% | TR 22.843 for approval

## Slide 34: UAV_Ph3
New WID for approval at this plenary in SP-230518 (from S1-231809)
Progress since previous SA meeting: not applicable (new item)
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103: 80%
    Agree normative requirements
  SA1#104: 100%
    Finalise normative requirements
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000032 | UAV Phase 3 | UAV_Ph3 | 12/12/2023 | - | SP-230518 | 0% | New WID

## Slide 35: FS_DualSteer
Progress since previous SA meeting
  Agreed TR updates and clean-up
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/2023): 100%
  Topics to be completed: ok to re-discuss use cases postponed from S1-102
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | 06/06/2023 | 75% | SP-220445 | 90% | Normative WID not approved yet

## Slide 36: FS_EnergyServ
TR 22.882 for approval at this plenary in SP-230519 (Cover Sheet S1-231774 + TR S1-231341)
Progress since previous SA meeting
  5 new use cases introduced (supporting carbon-aware communication service, energy as service criteria for 5G environment adaptation, pooling coverage layers for EE, communication service with best-effort renewable energy usage, reducing GHG Footprint of application services, communication service with carbon-aware service requirements).
  Editor’s notes have been removed
  Initial consolidation are added
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/23): 100%
  Topics to be completed: Completion of consolidation of the requirements, final clean-up
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
960019 | Study on Energy Efficiency as Service Criteria | FS_EnergyServ | 06/06/2023 | 70% | SP-230235 | 90% | TR 22.882 for approval

## Slide 37: EnergyServ
New WID for approval at this plenary in SP-230520 (from S1-231810)
Progress since previous SA meeting: not applicable (new item)
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (08/23): 50%
  Topics to be completed: CR based on the completion of consolidation of the requirements
  SA1#104 (11/23): 100%
  Topics to be completed: other clean-up
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000033 | Energy Efficiency as service criteria | EnergyServ | 12/12/2023 | - | SP-230520 | 0% | NEW

## Slide 38: FS_SOBOT
Progress since previous SA meeting
  Editorial clean-up
  Update use cases
  New Use Case on MEC for Efficient Management of Geo-surface Sensing Data Using a Group of Aerial Robots
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (Aug 2023): 80%
    Update use cases and potential requirements
    Additional use cases and potential requirements
    Topics to be completed: Sending TR for Information or approval
  SA1#104 (Nov 2023): 100%
    Final consolidation
    Final clean up
    Sending TR for approval if not done previous meeting
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | 09/09/2023 | 70% | SP-220447 | 80% | 

## Slide 39: FS_ISN
Progress since previous SA meeting
  Agreed TR 22.848 skeleton
  Agreed scope
  Added definitions, abbreviations
  Agreed 4 new use cases and potential requirements associated
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#103 (Aug 2023): 80%
    Update use cases and potential requirements
    Additional use cases and potential requirements
    Topics to be completed: Sending TR for Information or approval
  SA1#104 (Nov 2023): 100%
    Final consolidation
    Final clean up
    Sending TR for approval if not done previous meeting
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
990053 | Study on Interconnect of SNPN | FS_ISN | 12/12/2023 | 0% | SP-230236 | 30% | Study just started

## Slide 40: Rel-19 Mini WIDs

## Slide 41: UEMHopRelay
New WID for approval at this plenary in SP-230521 (from S1-231755)
Progress since previous SA meeting
  Mini-WID was agreed during the TSG SA WG 1 Meeting #102
  Associated change request against TS22.261 was agreed to add a new requirement on direct device connection for Public Safety
  Associated change request against TS22.280 was agreed to support private and group communications over one or more ProSe UE-to-UE Relays
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000025 | UE-to-UE Multi Hop Relay | UEMHopRelay | 06/06/2023 | 0% | SP-230521 | 100% | New “Mini WID”
UEMHopRelay - Agenda item 19 Rel-19 CRs: |  |  |  |  |  | 
SP-230522 | S1-231754 | UE-to-UE Multi-Hop Relay 22.261 | UEMHopRelay | 22.261 | 0681r4 | Rel-19
 | S1-231717 | UE-to-UE Multi-hop relay requirements for mission critical communications | UEMHopRelay | 22.280 | 0160r3 | Rel-19

## Slide 42: SecNPN
New WID for approval at this plenary in SP-230523 (from S1-231781)
Progress since previous SA meeting
  Mini-WID was agreed during the TSG SA WG 1 Meeting #102
  CR agreed:
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1000027 | Preventing Excessive Data Exposure within an NPN | SecNPN | 06/06/2023 | - | SP-230523 | 100% | New “Mini WID”
SecNPN - Agenda item 19 Rel-19 CRs: |  |  |  |  |  | 
SP-230524 | S1-231782 | Add requirements on NPN security considerations | SecNPN | 22.261 | 0688r3 | Rel-19

## Slide 43
Thank you