## Slide 1: China Mobile View on 6GDiscussion and Time Plan
China mobile
SP-231587

## Slide 2: Some Considerations on 6G Timeline
5G is still on its half lifespan and on the way to 5G-A.
  A “ten-year/generation” rule is healthy for the ecosystem: return back value for operator&vendor large investment and gain resources for next generation. 6G study shall not too rush to give outside of 3GPP the wrong imprssion of 5G sunset.
  We still need to realize the 5G commitment to the market. The global development of 5G is behind the market expectation. Demonstrate the success/value of 5G/5G-A to the market is the foundation of a successful 6G
The learning process seems just start
  New capabilities beyond communication is emerging, i.e., sensing
  New techologies and scenarios such as AIGC/Distributed Cloud is emerging
  Feedback on 5G vertical scenario deployment are gaining experiences
Learning from 5G standard: avoid rush plan leading to fragmented market/deployment
  Avoid unclear time plan: early drop / main drop / late drop
  Avoid multiple options: SA/NSA, option 2/3/4/5/7
  Sufficient study and clear understanding on scenarios and requirements.
  Deliver a single release for 6G depolyement basis before 2030

## Slide 3: Proposal on 3GPP 6G Timeline
2023 |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
6G SA1 Req SI+WI (R21)
6G CT WI (R21)*
6G OpenAPI frozen
6G ASN.1 frozen
6G SA1 Req SI (R20)
6G SA2 SI (R20)
6G RAN Req SI
6G RAN SI (R20)
6G RAN WI (R21)
6G SA2 WI (R21)
Assumption: On-time delivery of R20 specs for 5G-A (timeline decided later). R20 is the study start of 6G.
The first 6G spec ASN.1/OpenAPI frozen time is expected on 2029.06.
*Generally 12 months gap between stage 2 and 3. Here the long stage 2 leaves room for early start of stage 3
SA1: 15 month SI+18 moth WI
SA2: 21 month SI+18 moth WI

## Slide 4: Annex 1: ITU-R 6G Timeline
Feb 2026: Finalize technical performance requirements;
June 2030: Release IMT-2030 specifications.
ITU-R Working Party 5D structure and work plan
Attachment 2.12,Work plan, timeline, process and deliverables
for the future development of IMT

## Slide 5: Annex 2: Release 20 SA1 work planning
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
TSG#100
June
2023
Now
SA1#102
SA1#103
SA1#104
SA1#105
SA1#106
SA1#107
SA1#108
SA1#109
SA1#110
SA1#111
SA1#112
Rel-20 part 1 (≈50%)
SIDs presentation
SIDs agreement
Rel -20 SA1 Stage 1
Rel-19 Stage 2
Rel-19 Stage 3
Rel-19 Stage 1
Rel-19 TSG Cont. Def
Rel-20 part 2 (≈50%)
presentations
SID(s) agreement
Grey boxes = SA 1 Content definition process
Release 19
Release 20
100%(TBC)
No decision yet from
TSG on timeline
80%(TBC)
Part 1 is endorsed.
Initiate 6G requirements studies and use cases as part of Rel-20 (part-2).
SID for 6G is planned to be approved in September 2024 SA.
S1-233010 endorsed in SA1#104