## Slide 1
Andrew Bennett (SA2 Chair, Samsung)
Maurice Pope (SA2 Support, MCC)
SA2 Status Report to
TSG SA#108

## Slide 2: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 3: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 4: 1) General Aspects (1/7)
SA2 meetings held since SA#107
  SA2#168: 07 – 11 April 2025, Goteborg, Sweden
  SA2#169: 19 – 23 May 2025, Fukuoka, Japan
Upcoming SA2 meetings (Q3 2025)
  SA2#170: 25 – 29 August 2025, Goteborg, Sweden

## Slide 5: 1) General Aspects (2/7)
SA2 WG leadership
  Chair: Andrew Bennett (Samsung)
  Vice Chairs: Dario Serafino Tonesi (Qualcomm), Wanqiang Zhang (Huawei)
  Secretary: Maurice Pope (MCC)
Many thanks to Maurice Pope, and Vice Chairs Wanqiang Zhang and Dario Serafino Tonesi, for their outstanding support during this quarter
The Chair and Vice Chairs were re-elected by acclamation in SA2#169
Many thanks to the moderators of the Rel-20 5GA and Rel-20 6G SID and WID discussions for their great work during Q1 and Q2

## Slide 6: 1) General Aspects (3/7)
Statistics at SA WG2 #168 (07 – 11 April 2025, Goteborg, Sweden):
262 delegates ‘attended’ (checked-in) at SA WG2 #168 114 registered for the on-line broadcast
  1611 documents (including revisions), (470 documents were not handled) including:
    840 CRs (including revisions)
    59 Incoming LSs, of which 15 were postponed
    17 Outgoing LSs Approved
  54 other documents postponed
Total CRs agreed: 141 (excluding agreed CRs which were revised at SA2#169)
Statistics at SA WG2 #169 (19 – 23 May 2025, Fukuoka, Japan):
322 delegates ‘attended’ (checked-in) for SA WG2 #169 107 registered for ‘On-Line’ participation
  1504 documents (including revisions), (465 documents were not handled) including:
    528 CRs (including revisions)
    60 Incoming LSs, of which 10 were postponed
    19 Outgoing LSs Approved
  45 other documents postponed
Total CRs agreed: 79
888 people registered on the SA WG2 e-mail reflector on 2 June 2025

## Slide 7: 1) General Aspects (4/7)
Chart: SA WG2 meeting attendance

## Slide 8: 1) General Aspects (6/7) Document Handling / Meeting
Number of Tdocs
Chart: 

## Slide 9: 1) General Aspects (7/7) SA2 Agreed CRs by Release / Meeting
Number of CRs
Chart: 
| 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 136AH | 137-e | 138-e | 139-e | 140-e | 141-e | 142-e | 143-e | 144-e | 145-e | 146-e | 147-e | 148-e | 149-e | 150-e | 151-e | 152-e | 153-e | 154 | 154AH-e | 155 | 156-e | 157 | 158 | 159 | 160 | 160AH-e | 161 | 162 | 163 | 164 | 165 | 166 | 166AH-e | 167 | 168 | 169
Rel-16 PCR/draftCR | 43 | 80 | 170 | 147 | 181 | 171 | 207 | 250 | 88 | 87 | 71 | 103 | 26 | 39 | 30 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rel-16 CR | 2 | 3 | 66 | 133 | 117 | 233 | 279 | 205 | 260 | 174 | 197 | 248 | 31 | 123 | 79 | 9 | 74 | 8 | 29 | 38 | 0 | 31 | 17 | 1 | 13 | 8 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 2 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Rel-17 PCR/draftCR | 48 | 55 | 91 | 0 | 0 | 348 | 407 | 356 | 276 | 158 | 113 | 146 | 144 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rel-17 CR | 12 | 0 | 0 | 0 | 209 | 135 | 262 | 314 | 189 | 236 | 202 | 107 | 57 | 77 | 45 | 12 | 36 | 4 | 26 | 4 | 24 | 13 | 8 | 4 | 13 | 6 | 0 | 4 | 1 | 0 | 3 | 2 | 0 | 0
Rel-18 PCR/draftCR | 245 | 440 | 599 | 535 | 306 | 69 | 57 | 17 | 27 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rel-18 CR | 0 | 0 | 0 | 0 | 25 | 83 | 240 | 215 | 290 | 272 | 226 | 184 | 198 | 208 | 118 | 75 | 21 | 88 | 41 | 2 | 37 | 15 | 14 | 7
Rel-19 PCR/draftCR | 36 | 31 | 27 | 37 | 0 | 26 | 29 | 168 | 175 | 228 | 85 | 36 | 9 | 13 | 14 | 10 | 17 | 19
Rel-19 CR | 44 | 50 | 39 | 36 | 0 | 0 | 0 | 0 | 0 | 6 | 15 | 144 | 108 | 148 | 179 | 162 | 127 | 72
Rel-20 PCR/draftCR | 40 | 84
Rel-20 CR | 0 | 0

## Slide 10: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 11: 2.1) Rel-16 and before Maintenance (1/1)
Rel-12 |  | None
Rel-13 |  | None
Rel-14 |  | None
Rel-15 | 5GS_Ph1 | TEI18: 1 CR to TS 23.502, 1 CR to TS 23.503 TEI19: 2 CRs to TS 23.501, 2 CRs to TS 23.502, 2 CR to TS 23.503
Rel-15 | Excluding 5GS_Ph1 | None
Rel-16 |  | Vertical_LAN, TEI18: 1 CR to TS 23.501
Maintenance CR’s since SA#107
(Cat A CR’s are not counted in these totals)

## Slide 12: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 13: 2.4) Rel-17 Work Summary
Acronym | Work Item Title | WID# | Progress since last TSG SA meeting
5GSAT_ARCH | Architecture aspects for using satellite access in 5G | SP-200445 | No CRs
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | SP-201107 | No CRs
IIoT | Study on enhanced support of Industrial Internet of Things | SP-200973 | 1 CR to TS 23.501
5G_ProSe | Proximity based Services in 5GS (5G_ProSe) | SP-201132 | No CRs
MUSIM | System enablers for Multi-USIM devices | SP-200978 | No CRs
5MBS | Architectural enhancements for 5G multicast-broadcast services (5MBS) | SP-201106 | No CRs
eNS_Ph2 | Enhancement of Network Slicing Phase 2 | SP-200976 | No CRs
eNA_Ph2 | WID on Enablers for Network Automation for 5G - phase 2 | SP-201133 | 1 CR to TS 23.288
eNPN | Enhanced support of Non-Public Networks | SP-200980 | No CRs
ID_UAS | Support of Unmanned Aerial Systems Connectivity, Identification, and Tracking | SP-200979 | No CRs
eV2XARC_Ph2 | Architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | SP-210090 | No CRs
ATSSS_Ph2 | Access Traffic Steering, Switch and Splitting support in the 5G system architecture Phase 2 | SP-200977 | No CRs
5G_AIS | 5G System Enhancement for Advanced Interactive Services | SP-190564 | No CRs
5G_eLCS _Ph2 | Enhancement to the 5GC LoCation Services-Phase 2 | SP-200082 | No CRs
MPS2 | Multimedia Priority Service (MPS) Phase 2 | SP-200519 | No CRs
MINT | Minimization of Service Interruption | SP-210582 | No CRs
ARCH_NR_REDCAP | Architecture Enhancement for NR Reduced Capability Devices | SP-211100 | No CRs
IoT_SAT_ARCH_EPS | Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS | SP-211306 | No CRs
NR_QoE_enh-Core | [RAN3] Core part: Enhancement on NR QoE management and optimizations for diverse services | RP-223488 | No CRs

## Slide 14: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 15: 2.5) Rel-18 Study/Work (1/5)
Acronym | Work Item Title | WID# | Remarks
5GSATB | 5G System with Satellite Backhaul | SP-230111 | No CRs
5GSAT_Ph2 | Satellite access, Phase2 | SP-230109 | No CRs
PIN | Personal IoT Networks | SP-221343 | No CRs
UAS_Ph2 | Phase 2 of UAS, UAV and UAM | SP-230091 | No CRs
Ranging_SL | Ranging based services and sidelink positioning | SP-230106 | No CRs
5G_eLCS _Ph3 | Enhancement to the 5GC LoCation Services-Phase 3 | SP-230093 | No CRs
5G_ProSe_Ph2 | Proximity-based Services in 5GS Phase 2 | SP-230097 | 1 CR to TS 23.304
GMEC | Generic group management, exposure and communication enhancements | SP-230101 | No CRs

## Slide 16: 2.5) Rel-18 Study/Work (2/5)
Acronym | Work Item Title | WID# | Remarks
AIMLsys | System Support for AI/ML-based Services | SP-230095 | No CRs
5MBS_Ph2 | Architectural enhancements for 5G multicast-broadcast services Phase 2 | SP-230099 | No CRs
eNS_Ph3 | Network Slicing Phase3 | SP-230104 | 2 CRs to TS 23.501, 1 CR to TS 23.503
XRM | XR (Extended Reality) and media services | SP-230092 | 3 CRs to TS 23.501, 2 CRs to TS 23.502, 3 CRs to TS 23.503
NR_REDCAP_Ph2 | 5GS support of NR RedCap UE with long eDRX for RRC_INACTIVE State | SP-230171 | No CRs
NG_RTC | System architecture for next generation real time communication services | SP-230098 | 1 CR to TS 23.228
ATSSS_Ph3 | Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 | SP-221334 | 1 CRs to TS 23.501

## Slide 17: 2.5) Rel-18 Study/Work (3/5)
Acronym | Work Item Title | WID# | Remarks
UPEAS | UPF enhancement for Exposure And SBA | SP-230103 | No CRs
EDGE_Ph2 | Edge Computing Phase 2 | SP-230112 | 2 CRs to TS 23.502, 1 CR to TS 23.548
TRS_URLLC | 5G Timing Resiliency and TSC & URLLC enhancements | SP-230107 | No CRs
VMR | Architecture Enhancements for Vehicle Mounted Relays | SP-230105 | 1 CR to TS 23.501, 1 CR to TS 23.502
5WWC_Ph2 | Support for 5WWC, Phase 2 | SP-230367 | 1 CR to TS 23.502, 2 CRs to TS 23.316
MPS_WLAN | MPS when access to EPC/5GC is WLAN | SP-230108 | No CRs
AMP | 5G AM Policy | SP-221335 | No CRs
eNA_Ph3 | Enablers for Network Automation for 5G - phase 3 | SP-230110 | 1 CR to TS 23.288

## Slide 18: 2.5) Rel-18 Study/Work (4/5)
Acronym | Work Item Title | WID# | Remarks
eNPN_Ph2 | Enhanced support of Non-Public Networks | SP-230096 | No CRs
eUEPO | Enhancement of 5G UE Policy | SP-230094 | 1 CR to TS 23.502
SFC | System Enabler for Service Function Chaining | SP-230120 | No CRs
DetNet | 5GS DetNet interworking | SP-230172 | No CRs
SUECR | Seamless UE context recovery | SP-220810 | No CRs

## Slide 19: 2.5) Rel-18 Study/Work (5/5)
Acronym | Work Item Title | WID# | Remarks
TEI18_SDNAEPC | Secondary DN authentication and authorization in EPS IWK case | SP-220798 | No CRs
TEI18_MLR | Multiple location report for MT-LR Immediate Location Request for the regulatory service | SP-220795 | No CRs
TEI18_MBS4V2X | MBS support for V2X services | SP-220793 | No CRs
TEI18_SLAMUP | Spending Limits for AM and UE Policies in the 5GC | SP-220794 | No CRs
TEI18_ADEE | Enhancement of Application Detection Event Exposure | SP-220796 | No CRs
TEI18_IPv6PD | General Support of IPv6 Prefix Delegation | SP-220797 | No CRs
TEI18_DCAMP_Ph2 | Dynamically Changing AM Policies in the 5GC Phase 2 | SP-230102 | No CRs
eNSAC | Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection | SP-230113 | No CRs
TEI18 mini WIDs

## Slide 20: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 21: SA WG2 progress -Summary
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 06/06/2024 | 100% | SP-231391 | 100% | 
1050112 | (WA) Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 70% | SP-241388 | 100% | 
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 12/12/2024 | 98% | SP-240991 | 99% | 
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 06/06/2024 | 100% | SP-231800 | 100% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | 12/12/2024 | 90% | SP-240969 | 100% | 
1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | 06/06/2025 | 30% | SP-250377 | 90% | 
1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 06/06/2024 | 100% | SP-231199 | 100% | 
1040027 | Integration of satellite components in the 5G architecture Phase III | 5GSAT_Ph3-ARC | 12/12/2024 | 65% | SP-240986 | 100% | 
1010032 | Study on Extended Reality and Media service (XRM) Phase 2 | FS_XRM_Ph2 | 09/09/2024 | 100% | SP-231671 | 100% | 
1040032 | Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | 12/12/2024 | 65% | SP-240990 | 100% | 
1040035 | UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 12/12/2024 | 100% | SP-240995 | 100% | 
1020003 | Study on UPF enhancement for Exposure And SBA Phase 2 | FS_UPEAS_Ph2 | 06/06/2024 | 100% | SP-231795 | 100% | 
1040036 | Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 12/12/2024 | 97% | SP-240996 | 100% | 
1020004 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | FS_eEDGE_5GC_Ph3 | 09/09/2024 | 100% | SP-240962 | 100% | 
Updates in RED

## Slide 22: SA WG2 progress -Summary
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040034 | Multi-Access (ATSSS_Ph4) | MASSS | 12/12/2024 | 100% | SP-240994 | 100% | 
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 09/09/2024 | 100% | SP-240467 | 100% | 
1040026 | System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | 12/12/2024 | 98% | SP-240985 | 99% | 
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 09/09/2024 | 100% | SP-231196 | 100% | 
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 99% | SP-240997 | 100% | 
1020002 | Study on System aspects of 5G NR Femto | FS_5G_Femto | 09/09/2024 | 100% | SP-231797 | 100% | 
1040028 | System aspects of 5G NR Femto | 5G_Femto | 12/12/2024 | 100% | SP-240629 | 100% | 
1020066 | Study on Proximity-based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3 | 09/09/2024 | 100% | SP-231798 | 100% | 
1040030 | Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 12/12/2024 | 100% | SP-240988 | 100% | 
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 09/09/2024 | 100% | SP-240493 | 100% | 
1040031 | Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 12/12/2024 | 100% | SP-240989 | 100% | 
1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | 09/09/2024 | 100% | SP-231804 | 100% | 
1040085 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 12/12/2024 | 90% | SP-240971 | 100% | 
1040029 | (stage 2 of) MPS for IMS Messaging and SMS services | MPS4msg | 12/12/2024 | 100% | SP-240987 | 100% | 
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 06/06/2024 | 100% | SP-231197 | 100% | 
Updates in RED

## Slide 23: SA WG2 progress – (TEI19) (1/2)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1030010 | On-demand broadcast of GNSS assistance data | TEI19_OBGAD | 12/12/2024 | 100% | SP-240487 | 100% | No CRs
1040078 | Stage 2 of Minimize the Number of Policy Associations | TEI19_MINPA | 03/03/2025 | 100% | SP-240118 | 100% | No CRs
1030014 | Spending Limits for UE Policies in Roaming scenario | TEI19_SLUPiR | 06/06/2024 | 100% | SP-240486 | 100% | No CRs
1040079 | Stage 2 of Enhancing Parameter Provisioning with static UE IP address and UP security policy | TEI19_IP_SP_EXP | 12/12/2024 | 100% | SP-240121 | 100% | No CRs
1030017 | Multiple Location Procedure for Emergency LCS Routing | TEI19_MLR4RTR | 12/12/2024 | 100% | SP-240123 | 100% | No CRs
1030018 | Roaming traffic offloading via session breakout in HPLMN | TEI19_HSBO | 12/12/2024 | 100% | SP-240491 | 100% | No CRs
1030019 | Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports | TEI19_DLPMR | 12/12/2024 | 100% | SP-240125 | 100% | No CRs
1030011 | (Stage 2 of) Indirect Network Sharing | TEI19_NetShare | 06/06/2024 | 100% | SP-240488 | 100% | 2 CRs to TS 23.501
1030013 | Architecture support of roaming value-added services | TEI19_RVAS | 06/06/2024 | 100% | SP-240119 | 100% | No CRs
Updates in RED

## Slide 24: SA WG2 progress – (TEI19) (2/2)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1030016 | ProSe support in NPN | TEI19_ProSe_NPN | 06/06/2024 | 100% | SP-240122 | 100% | No CRs
1030020 | QoS monitoring enhancement | TEI19_QME | 06/06/2024 | 100% | SP-240961 | 100% | No CRs
1030021 | Subscription control for reference time distribution in EPS | TEI19_TIME_SUB_EPS | 12/12/2024 | 100% | SP-240127 | 100% | No CRs
1040080 | Stage 2 of Providing per-subscriber VLAN instructions from UDM and DN-AAA | TEI19_VLANSUB | 12/12/2024 | 100% | SP-240128 | 100% | No CRs
1030023 | NF discovery and selection by target PLMN | TEI19_NFsel_by_tPLMN | 06/06/2024 | 100% | SP-240490 | 100% | No CRs
1060030 | Network Controlled Network Slice Selection | TEI19_SliceSel | 12/12/2024 | 100% | SP-241502 | 100% | 2 CRs to TS 23.501, 2 CRs to TS 23.502, 2 CRs to TS 23.503
1060031 | PRU Usage Extension supported by Core Network | TEI19_PRUE | 12/12/2024 | 100% | SP-241504 | 100% | No CRs
1060028 | MSISDN verification operation support to Nnef_UEId Service | TEI19_MVOSNS | 12/12/2024 | 100% | SP-241498 | 100% | No CRs
1060029 | ATSSS Rule Provisioning via 3GPP access connected to EPC | TEI19_ARP3E | 12/12/2024 | 100% | SP-241500 | 100% | No CRs
Updates in RED

## Slide 25: FS_5GSAT_Ph3_ARCH/ 5GSAT_Ph3-ARC
Progress since SA#107
  KI#1 (regenerative payload satellite access): 2 CRs and 1 LS out are approved for maintenance
  KI#2 (S&F): 5 CRs are approved for maintenance
  RAN impacts and dependencies
  Yes, KI#1 depends on RAN3 conclusion, and KI#2 has RAN impact
Contentious issues
  None
Next Steps
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040027 | Integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 14/03/2025 | 100 | SP-240986 | 100 | Completed
1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 21/06/2024 | 100 | SP-231199 | 100 | Completed

## Slide 26: FS_NG_RTC_Ph2/NG_RTC_Ph2
Progress since SA#107
  In SA2 #168 and #169 meetings totally 98 contributions were submitted and 37 contributions were handled with 18 agreed
  Achievements:
    16 CRs were agreed correcting services and procedures related to KI#1, #2, #3 and #6
    4 LSs to SA4, SA3, CT1 and GSMA were sent with related agreed CRs
Impacts and dependencies on other WGs
  None
Controversial issues
  None
Next steps
  Continue the maintenance and alignment with other WGs
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 12/12/2024 | 100% | SP-231196 | 100% | Complete
1040026 | System architecture for next generation real time communication services phase 2 | NG_RTC_Ph2 | 12/12/2024 | 98% | SP-240985 | 99% | Remaining issues in exception list have been resolved

## Slide 27: FS_XRM_Ph2/XRM_Ph2
  Progress since SA#107
  Maintenance work at SA2#168, SA2#169
  SA2#169: 2 LS OUT (Transport level marking on N3/N9, RTP retransmissions) with 1 related CR and 4 more CRs are approved (KI#9: 1 CR, KI#1: 1 CR, Multimodal awareness at RAN: 1 CR, Dynamic detection of L4S traffic: 1 CR)
  SA2#168: 2 LS OUT (MoQ Relay address in UPF profile, Uplink rate control) with 1 related CR and 8 more CRs are approved (KI#9: 4 CRs, KI#1: 4 CRs)
  All KIs completed
  Impacts and dependencies on other WGs
  None
  Controversial issues
    None
Next steps
  Work on postponed LSs (Uplink Rate Control, Unmarked N6 PDUs), continue maintenance work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010032 | Study on Extended Reality and Media Service (XRM) Phase 2 | FS_XRM_Ph2 | 09/09/2024 | 100% | SP-231671 | 100% | 
1040032 | Extended Reality and Media Service (XRM) Phase 2 | XRM_Ph2 | 12/03/2025 | 100% | SP-241385 | 100% | 

## Slide 28: FS_EnergySys/EnergySys
  Progress since SA#107
  Discussion on CRs for maintenance of TS documents was continued
  95 Tdocs were submitted to SA2#168 and #169 (51 CRs and 3 LSs are handled, 33 CRs are agreed)
  Impacts and dependencies on other WGs
  None
  Contentious issues
  None
  Next steps:
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 100% | SP-231192 | 100% | Study has been completed
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 100% | SP-241388 | 100% | Normative work complete

## Slide 29: FS_MPS4msg/MPS4msg
Progress since SA#107:
  No contributions submitted.
  Normative work is 100% complete
Impacts and dependencies on other WGs:
  None
Controversial issues:
  None
Next steps:
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 06/06/2024 | 100% | SP-231197 | 100% | 
1040029 | MPS for IMS Messaging and SMS services | MPS4msg | 12/12/2024 | 100% | SP-240987 | 100% | 

## Slide 30: FS_VMR_Ph2/VMR_Ph2
Progress since SA#107
  8 CRs to TS 23.501 and TS 23.502 were agreed - updates to Principles, Configuration of MWAB-gNB, PWS references and documentation, Additional ULI support.
  2 CRs to TS 23.273 agreed: Updates to: 5GC-MT-LR procedure involving MWAB (figure update), Inter PLMN GMLC communication via NEF removal.
  3 LS replies
    to SA5: Answers on OAM configurations of the MWAB-gNB
    to CT1: Confirmation on PWS description in TS 23.501 and TS 23.502
    to RAN3: Confirmation of support of additional ULI for NTN backhaul
Impacts and dependencies on other WGs
  OAM support is expected to be handled by SA5, and security to be handled by SA3
Next steps
  Alignment based on work progressed in other working groups
  Maintenance work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 09/09/2024 | 100% | SP-240493 | 100% | 
1040031 | Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 12/12/2024 | 100% | SP-240989 | 100% | 

## Slide 31: FS_5G_ProSe_Ph3/5G_ProSe_Ph3
  Progress since SA#107
  10 CRs to TS 23.304 and one CR to TS 23.502 were agreed.
  Additional corrections and clarifications for Layer 3 UE-to-Network and UE-to-UE Relay
  Introduction of Layer 2 UE-to-Network Relay in TS 23.304 based on RAN progress
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
Outstanding issues
  None.
Next steps
  Continue maintenance work.
  Alignment with RAN for Layer 2 UE-to-Network Relay
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 100% | SP-231798 | 100% | 
1040030 | Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 18/12/2024 | 100% | SP-240988 | 100% | 

## Slide 32: FS_UIA_ARC/UIA_ARC
Progress since SA#107
  41 documents were submitted to SA2 #168. 13 were approved, 2 were merged, 2 were noted, 2 were postponed, 22 were not handled.
  At SA2 #169, technical discussion of UIA_ARC was not on the agenda. However, one UIA_ARC CR from SA2 #168 was replaced with a new CR to fix the cover sheet.
  In sumary, 1 LS Out and 12 CAT-F CRs were approved.
    The LS Out (S2-2504337) is a reply LS to CT1 (S2-2502806).
    1 for TS 23.316 CR, 5 for TS 23.501 CRs, 4 for TS 23.502 CRs, and 2 for TS 23.503 CRs.
    3 CRs realted to the CT 1 LS
Impacts and dependencies on other WGs
  None identified
Contentious Issues
  None identified
Next Steps
  Maintenance work and alignments based on feedback from and progress in CT WGs
  2 papers that were postponed at SA2 #168 relate to SMF/PCF selection
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | 09/09/2024 | 100% | SP-231804 | 100% | 
1040085 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 30/12/2024 | 100% | SP-240971 | 100% | 

## Slide 33: FS_eEDGE_5GC_ph3/ eEDGE_5GC_ph3
Progress since SA#107
  23 Tdocs received, 11 CRs were approved
  1 CR to TS 23.501 approved triggered by LS from SA3 on Security related protocol-specific parameters for N6 delay measurement
  Impacts and dependencies on other WGs:
  None
Controversial issues:
  On support of I-SMF reallocation per target DNAI notified by SMF. Potential show of hands needed in August meeting
Next steps:
  Continue maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020004 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | FS_eEDGE_5GC_Ph3 | 09/09/2024 | 100% | SP-240962 | 100% | 
1040036 | Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 12/12/2024 | 100% | SP-240996 | 100% | 

## Slide 34: FS_UAS_Ph3/UAS_Ph3
Progress since SA#107
  4 CRs to TS 23.256 and 1 CR to TS 23.502 were agreed
  Reply LS on UAV regulation was sent to RAN3.
  The issue on Using Nnef_RetrieveInfoUAVFlight_Get in the procedure for USS changeover during a UAV flight which has dependency on CT3 was resolved per LS from CT3 (S2-2502810) and no additional action needed by SA2
  Impacts and dependencies on other WGs
  RAN3: Procedures for altitude reporting for aerial UEs  alignments expected to be progressed during Q3 meeting.
  SA3: check USS list aspect progressed in SA3 and follow-up if necessary
Outstanding issues
  None
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 100% | SP-240997 | 100% | 

## Slide 35: FS_UPEAS_Ph2/UPEAS_Ph2
Progress since SA#107
  Continue maintenance work at SA2#168
  5 CRs are approved at SA2#168
  Not on the SA2#169 agenda
Impacts and dependencies on other WGs
  None
Controversial issues
  None
Next steps
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020003 | Study on UPF enhancement for Exposure And SBA Phase 2 | FS_UPEAS_Ph2 | 06/06/2024 | 100% | SP-231795 | 100% | 
1040035 | UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 12/12/2024 | 100% | SP-240995 | 100% | 

## Slide 36: FS_5G_Femto/5G_Femto
  Progress since SA#107
  1 LS In on “LS on security verification related to NR Femtos” for information.
  4 CRs are approved at SA2#168.
  LS from RAN WG3: Reply LS on NR Femto node shared by PLMN and PNI-NPN
  1 CR is approved in relation to the RAN WG3 LS in SA2#169.
  RAN impacts and dependencies
  Depending on the LS response, there may be dependencies on the RAN
Outstanding issues
  None
Next steps
  Maintenance work and alignment based on work progressed in other working groups
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020002 | Study on System aspects of 5G NR Femto | FS_5G_Femto | 09/09/2024 | 100% | SP-231797 | 100% | 
1040028 | System aspects of 5G NR Femto | 5G_Femto | 12/12/2024 | 100% | SP-241327 | 100% | 

## Slide 37: FS_MASSS/MASSS
  Progress since SA#107
  1 LS from CT4 on the support of MPQUIC-E in interworking and HR scenario was discussed, and the reply LS was approved.
  9 maintenance CRs were approved (TS 23.501/23.502/23.503)
  RAN impacts and dependencies
  None
Contentious issues:
  None
Next steps
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 09/09/2024 | 100% | SP-240467 | 100% | 
1040034 | Multi-Access (ATSSS_Ph4) | MASSS | 12/12/2024 | 100% | SP-240994 | 100% | 

## Slide 38: AmbientIoT-ARC/FS_AmbientIoT
Progress since SA#107
  36 p-CR were approved
  5 LS out were approved, including: D2R message size(RAN2 and RAN3), paging ID length(RAN2, CT4 and SA3), Follow- up questions on Reader selection (RAN3), Check RAN view on removal of service type information (RAN2 and RAN3), AIoT Device ID length (CT4)
  TS 23.369 is 90% complete, and will be sent to SA plenary for approval
  Impacts and dependencies on other WGs
  SA3: AIoT Device security, including AIoT Device ID privacy protection
Outstanding issues
  Alignment and dependency to SA3 on security aspects and RAN2/RAN3 on RAN aspects are required to be addressed.
  Once SA3 has concluded on security aspects, SA2 needs to determine which procedures are mandatory or optional for the Ambient IoT device
Next steps
  Resolve outstanding issues based on SA3 and RAN WGs progress
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | Jun, 2025 | 30% | SP-250377 | 90% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 100% | SP-240969 | 100% | 

## Slide 39: FS_AIML_CN/AIML_CN
General
  176 papers were submitted, 19 agreed, 2 LS out, 1 endorsed, 2 merged, 5 postponed.
  KI#1: 1 LS out, 4 agreed, 1 endorsed, 1 merged, 5 postponed
    LS out to answer SA WG 5, about the mechanisms to collect AI/ML positioning relevant data.
  KI#2: 7 agreed, 1 merged
  KI#3: 1 agreed
  KI#4: 1 LS out, 7 agreed
    LS out to reply CT 4
  Impacts and dependence with other WGs :
  Impact SA3: consent/privacy aspects in coordination with SA3
Controversial issues
  Consent/privacy aspects need to be resolved, in coordination with SA3
Next Steps
  Maintenance
  KI#1 to align with SA3 for user consent and decide on use of privacy profile
  KI#1/3/4 to answer CT3 LS IN
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 06/06/2024 | 100% | SP-231800 | 100% | 
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 12/12/2024 | 98% | SP-240991 | 99% | 

## Slide 40: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 41: FS_5GSAT_Ph4_ARC
Progress since SA2#107
  In SA2#168 meeting, 5 pCRs are approved, including TR skeleton, TR scope, Architectural assumptions (2 pCRs), and a KI for WT-1
  In SA2#169 meeting, 14 pCRs are approved, including:
    11 pCRs for KI#1 (IMS call via NB-IoT NTN GEO satellite connecting to EPC)
    2 pCRs for KI#2 (IMS enhancement for GEO NB-IoT NTN access),
    1 pCR for WT2.2(UE-SAT-UE communication for non-IMS services)
  Impacts and dependencies on other WGs
  KI#1 and KI#3 have RAN impact, KI#2 may have dependency on RAN conclusion.
Contentious issues
  None
Next Step
  Continuing solution discussion.
  Start solution evaluation for KI#1
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070011 | Study on Integration of satellite components in the 5G architecture Phase 4 | FS_5GSAT_Ph4_ARC | 12/12/2025 | 0 | SP-250400 | 30 | In progress

## Slide 42: FS_Sensing_ARC
Progress since SA2#107
  TR skeleton, Terms and definition, architectural assumptions and requirements. All 6 key issues were agreed
  20 new solutions agreed
  Impacts and dependencies on other WGs
  SA3: Privacy protection and other security aspects will be coordinated with SA3
  SA5: Charging and OAM aspects will be coordinated with SA5
  RAN TSG/WG: The scope of the sensing study (incl. TUs) will be further aligned in plenary TSG#108 together with RAN TSG
  Solutions proposing exposure of sensing results to the UE need to be coordinated / checked with SA1 and SA3
Contentious issues
  None
Next Step
  To update the contents in TR 23.700-14 if necessary, based on the study scope alignment at TGS#108
  Continue discussing solutions for all the key issues based on updated SID scope
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 0% | SP-250401 | 35% | NOTE: the exact completion rate will be updated based on the outcome of TSG#108

## Slide 43: FS_AIML_CN_Ph2
Progress since SA2#107
  TR 23.700-04 v.0.2.0 was created based on approved contributions.
  1 LS out for AI/ML UE sided data collection
  TR skeleton, architecture assumptions, solutions for KT#1 and KI#2, use cases for WT#2, key issues and solutions for WT#1
  3 TU used and 2 TU left for the Study Phase
  2 Key Issues agreed for the study
  Impacts and dependencies on other WGs
  RAN impacts or dependencies identified for Key Issue #1.
  Potential user consent and privacy enhancements are under SA3 scope, then SA2 may need to align with SA3. This study considers user consent and privacy as currently defined in SA2 specifications
Contentious issues
  None
Next Step
  Solution updates to resolve ENs (with higher priority) and last chance for new solution(s)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070013 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML)_Ph2 | FS_AIML_CN_Ph2 | 09/12/2025 | 0 | SP-250413 | 50 | 

## Slide 44: FS_EnergySys_Ph2
Progress since SA2#107
  Approved updated TR skeleton
  Approved 5 solution related to KI1
  Approved 6 solutions related to KI2
  Approved 5 solutions related to KI3
  RAN impacts and dependencies
  Dependency on SA5 related to new performance measurements regarding renewable energy.
  Dependency on RAN WGs regarding new performance measurements
Contentious issues
  Improvements of “accuracy“ in terms of energy related measurements for Rel-20 is still open.
  There are at least 2 contradicting solution types on discovery and selection of NFs considering energy metrics.
Next Steps
  Try to agree on the notion of accuracy related to energy related measurements for Rel-20.
  Continue to handle new solutons for KI1, KI 2 and KI 3
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070058 | New SID on Energy Efficiency and Energy Saving Phase 2 | FS_EnergySys_Ph2 | 12/12/2025 | 0% | SP-250417 | 50% | 

## Slide 45: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 46: 2.7) IETF and External SDO Normative Reference Update
None

## Slide 47: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 48: 3) SA2 Work Planning: Rel-20 progress
Summary of status of Rel-20 work and study items (excluding TEI20)
Item | Study Item status | Work Item status | Comment
FS_5GSAT_Ph4_ARC | 30% | N/A | 
FS_Sensing_ARC | 35% | N/A | 
FS_AIML_CN_Ph2 | 50% | N/A | 
FS_EnergySys_Ph2 | 50% | N/A | 

## Slide 49: 3) SA2 Work Planning: Rel-20 5GA
5GA WIDs and SIDs summary – already approved by SA
* Study + Norm = Total
Topic | SID/WID titles | Acronym | TU estimates * | Status
Integration of satellite components in the 5G architecture Phase 4 | Study on Integration of satellite components in the 5G architecture Phase 4 | FS_5GSAT_Ph4_ARC | 8.5 + 8.5 = 17 | Approved in SA#107
AI/ML Enhancements | Study on Core Network Enhanced Support for Artificial Intelligence (AI) / Machine Learning (ML) Phase 2 | FS_AIML_CN_Ph2 | 5 + 2 = 7 (plus WT#1 normative TU’s) | Approved in SA#107
Integrated Sensing and Communication | Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | No consensus | Approved in SA#107
Energy Efficiency Enhancements | Study on Energy Efficiency and Energy Saving Phase2 | FS_EnergySys_Ph2 | 6 + 6 = 12 | Approved in SA#107

## Slide 50: 3) SA2 Work Planning: Rel-20 5GA
5GA WIDs and SIDs summary – approved by SA2 but not yet by SA
* Study + Norm = Total
Topic | SID/WID titles | Acronym | TU estimates * | Status
Ambient IoT | Architecture support of Ambient power-enabled Internet of Things-Phase 2 | FS_AmbientIoT_ARC_Ph2 | 6 + 6 = 12 | Approved in SA2#169
Indirect Network Sharing Phase 2 | Indirect Network Sharing phase2 | NetShare_ph2 | 0 + 2 = 2 | Approved in SA2#169
Mission Critical Services, Multimedia Priority Services | MPS Enhancements for IoT | FS_MPS_IOT | 3 + 3 = 6 | Approved in SA2#169
 | 5G ProSe Phase 4 | ProSe_Ph4-ARC | 0 + 1 = 1 | Approved in SA2#169
NG_RTC continuation | Study on system architecture for next generation real time communication services phase 3 | FS_NG_RTC_Ph3 | 5 + 4 = 9 | Approved in SA2#169
SMS to Emergency Centre | Study on Short Message Service to Emergency Response Centre | FS_SMS2EC_Ph2_ARC | 4 + 3.5 = 7.5 | Approved in SA2#169

## Slide 51: 3) SA2 Work Planning: Rel-20 5GA
5GA WIDs and SIDs summary – not approved by SA2
* Study + Norm = Total
Topic | SID/WID titles | Acronym | TU estimates * | Status
User Identities and Authentication Architecture – Phase 2 | Study on Identifying non-3GPP Devices Connecting behind a UE or 5G-RG Phase 2 | FS_UIA_ARC_Ph2 | 2.5 + 2.5 = 5 | Not approved
 | Study on User Identities and Authentication Architecture Phase 2 | - | 3.5 + 3.5 = 7 | Not approved
Enhancements for ePDG based access to 5GC | Study on Enhancements for ePDG based access to 5GC | FS_ePDG5GC | 1.5 + 1.5 = 3 | Not approved
Industrial network enhancements | Industrial Networks Loop Prevention | Vertical_LAN_Loop_Ph2 | 0 + 1 = 1 | Not approved
XR and Media Services | Study on Extended Reality and Media Service (XRM) Phase 3 | FS_XRM_Ph3 | 3 + 3.5 = 6.5 | Not approved

## Slide 52: 3) SA2 Work Planning: Rel-20 5GA
4 SIDs related to 4 SA-identified topics were approved in SA#107
  3 of these have a total estimate of 36 TU’s
  1 of these (FS_AIML_CN_Ph2) will need updated TU’s for WT#1, depending on RAN decisions
  The FS_Sensing_ARC SID does not yet have TU estimates
6 WIDs and SIDs related to 5 5GA SA-identified topics were approved in SA2#169 with a total estimate of 37.5 TU’s
WIDs and SIDs related to 4 additional SA-identified topics were not approved by SA2 during Q2 2025
The known TU total for SA and SA2 approved items is therefore 36 + 37.5 = 73.5 TU’s
The final estimate of TU’s for FS_Sensing_ARC and FS_AIML_CN_Ph2 WT#1 will need to be added to this

## Slide 53: 3) SA2 Work Planning: Rel-20 6G
The 6G SID was approved in SA2#169
One Work Task was removed from the draft SID and a note added to the Chair’s notes
  The following WT is considered technically correct and could be the basis for a company SID submission to SA
    WT#7: Study whether and how to enhance the IMS architecture (e.g. simplify the IMS architecture, enhance the support of existing services, etc.)
    NOTE n: This study assumes that the UNI signaling and NNI signaling are not modified and IMS architecture remains access agnostic.
    NOTE n: Whether WT#7 is part of this study will be determined at TSG SA#108(Jun)
No TU estimates were included in the SID
The scope of the work tasks and potential key issues derived from the work tasks will be refined during Q3 and Q4 2025
Next slide describes the plan until SA#110 (December 2025)

## Slide 54: 3) SA2 Work Planning: Rel-20 6G planning
A plan for Q3 and Q4 for the 6G study work was endorsed in SA2#169 in S2-2505648
Summarised:
  Input papers are invited to the three meetings to provide justification and clarification of each Work Task scope
  When the scope of each Work Task is clear and documented Key Issues for that Work Task can be discussed and documented
  Input papers on architectural assumptions and principles will also be discussed
  Completion of Key Issues, Arch assumptions and principles is in general targeted for the end of the November meeting unless there are dependencies on other WG’s
  During the November meeting the Work Task descriptions in the SID will be updated with Work Task descriptions agreed during the three meetings and TU estimates and completion dates will be added

## Slide 55: 3) SA2 Work Planning: Rel-20 planning
An SA2 Rel-20 planning conference call is scheduled for 25th June
Agenda
  Discuss 5GA SID TU plan and milestone proposals from rapporteurs
  6G SID
    Discuss milestone proposals from rapporteurs
    Discuss guidance on input papers at least for August
    Discuss planning for how to handle the input papers

## Slide 56: 3) SA2 Work Planning: Other topics
TEI20
  TEI20 proposals were invited (for information only) for SA2#169
    19 proposals were received
  TEI20 proposals are invited for discussion and approval for SA2#170
    To fill a maximum of 8 TU’s
  It is planned to invite further TEI20 proposals for SA2#173
    To fill a maximum of 4 TU’s
SA2 endorsed a new best practice document for SA2 studies
SA2 endorsed a new SA2 TR template in line with this best practice
SA2 endorsed new guidance and template for SI/WI status reports in line with this best practice
The best practice document and TR template are available at ftp://ftp.3gpp.org/tsg_sa/WG2_Arch/SA2_Templates

## Slide 57: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 58: 4) Documents for Information and Approval (1/4)
Revised SID/WID for Approval
TSG SA# | Type | Title | Acronym
SP-250481 | SID REVISED | Revised SID on Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC

## Slide 59: 4) Documents for Information and Approval (2/4)
New SID/WID for Approval
TSG SA# | Type | Title | Acronym
SP-250482 | WID NEW | New WID on Indirect Network Sharing phase2. | NetShare_ph2
SP-250483 | WID NEW | New WID on ProSe Phase 4. | ProSe_Ph4-ARC
SP-250484 | SID NEW | New SID on Short Message Service to Emergency Response Centre. | FS_SMS2EC_Ph2_ARC
SP-250485 | SID NEW | New SID: Study on system architecture for next generation real time communication services phase 3. | FS_NG_RTC_Ph3
SP-250486 | SID NEW | New SID on MPS Enhancements for IoT. | FS_MPS_IOT
SP-250487 | SID NEW | NEW SID on Architecture support of Ambient power-enabled Internet of Things-Phase 2. | FS_AmbientIoT_ARC_Ph2
SP-250488 | SID NEW | Study on Architecture for 6G System. | FS_6G_ARC

## Slide 60: 4) Documents for Information and Approval (3/4)
TSs/TRs for Approval
TSG SA# | Title | Release | TR/TS | WI Acronym
SP-250489 | Cover sheet for presentation of TS 23.369 to TSG SA for Approval | Rel-19 | TS | AmbientIoT-ARC

## Slide 61: 4) Documents for Information and Approval (4/4)
TSs/TRs for Information
TSG SA# | Title | Release | TR/TS | WI Code

## Slide 62: Contents
1) General aspects (events since SA#107, statistics, next meetings)
2) SA Work Report
  2.1) Rel-16 and before Maintenance
  2.2) Rel-17 Work and Maintenance
  2.3) Rel-18 Work and Maintenance
  2.4) Rel-19 Work and Maintenance
  2.5) Rel-20 Work and Maintenance
  2.6) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 63: 5) Collected Items requiring action from SA
Approve TR 23.700-13 and TS 23.369
Approve the Rel-20 new and revised SIDs and WIDs
Determine the TU estimates for FS_Sensing_ARC
  Dependent on the SI scope in SA2 and based on alignment with RAN at TSG#108
Determine the TU estimates for FS_AIML_CN_Ph2 WT#1
  Dependent on RAN’s decision on e.g. which solution(s) are selected
Discuss and decide on the TU split between 5GA and 6G in Rel-20
Determine the package of Rel-20 study and work items

## Slide 64: Thank You !
Andrew Bennett
Chair of 3GPP SA2
a.bennett@Samsung.com
www.3gpp.org