3GPP TSG SA Meeting #108 	SP-250803

10-13 June 2025, Prague, Czech Republic	(rev of SP-250716)

Source:	SA5 Officials & MCC Work Plan Coordinator

Title :	Follow-up of Selecting the Release for Charging/OAM aspects

Agenda item:	5.1

Document for:	Endorsement

Contact:	alain.sultan@etsi.org

Abstract: Follow-up of the discussions on selecting the Release for Charging

1. Introduction

At SA#107, then later by e-mail, the topic of “selecting the right Release for Charging aspects of a Feature” was discussed, on the basis of tdoc SP-250327. The topic was later discussed in SA5#161 as in tdoc S5-252826, and OAM aspects were added. A final round of e-mail exchanges took place between SA5 Chair and MCC Work Plan Coordinator to reach this proposal.

Summary of the problem statement: it was asked if the Charging/OAM aspects of a Feature can be specified in a later Release than the Release in which the other aspects of the Feature (Stages 1 to 3, testing, etc) were specified.

2. Analysis of the problem

At present, the need for defining Charging/OAM aspects is sometimes discovered quite late in the Release, and sometimes even at the end/after the Stage 3 specification. This may lead to having the Feature defined in Rel-n and its corresponding charging/OAM in Rel-[n+1] - which would break the 3GPP "Release" concept (a Release is a self-contained set of Specifications).

SA5#161 concluded on the following (endorsed by SA5):

SA5 kindly asks SA to endorse the following proposals:

- Whether each Feature requires Charging/OAM aspects or not shall be decided as early as possible, and to be revisited on regular basis during the whole release in SA, by:

  - An indication of “require the specification of charging/OAM aspects” to be added in the WID template

  - Maintaining dedicated NWM links to capture the relationship of Charging/OAM support to SA2/RAN features

  - Regular SA5 report to SA with latest status information

- The default completion time for defining the network support Charging/OAM features is 3 months after completion of Stage 3, i.e. same time as ASN.1 freeze.

- For those Features that require Charging/OAM but for which the Charging/OAM could not be completed on time, exceptions sheets can be used, as for other Stages.

SA5 kindly asks SA to provide guidance for the following proposal:

- If, at the Charging/OAM completion time (potentially extended by the exception sheet), the Charging/OAM is (still) not completed, then 2 different handlings are possible. The selection of handling options will be made on case by case basis.

  - Option 1: Keep the Feature in its original Release (Release n) and allow the corresponding Charging/OAM aspects to be in the subsequent Release [n+1].

  - Option 2: Postpone the entire Feature (i.e. all its 3 stages) to the next Release

After SA5#161, the case where the OAM/Charging aspects take long to be defined was further discussed between the authors of this contribution (SA5 Chair & MCC Work Plan Coordinator), and one more option than the two ones pointed out by SA5 was identified:

- Option 3: Keep the Feature in its original Release (Release n) and flag that corresponding Charging/OAM aspects are missing. Here, whenever provided, the Charging/OAM aspects will still belong to Release n, even if they come years after, as done for Testing aspects.

The pros and cons of all options (including options 1 and 2 from SA5) were concluded to be as follows:

Option 1 (current case) breaks the Release concept and leads to authorise incomplete Features in the 3GPP standard.

Option 2 jeopardizes the work done by all the other WGs and would be extremely complex to achieve (i.e. the removal of all Stages 1, 2 and 3 from a complete Release). If Charging/OAM feature is recognized as a must for a certain feature, the interested companies shall actively contribute to the corresponding Charging/OAM solution in time.

Option 3 follows what is being done for decades with success for RAN Testing specifications. It enhances this solution (compared to Testing) by providing a clear information that the missing Charging/OAM aspects still have to be standardized. In practice, this means that category B CRs can be allowed even after the freezing date of Stage 3 for Release n.

With the above analysis, Option 3 is seen as the way forward.

3. Proposal for SA endorsement

Based on the analysis above, the following proposals are for SA endorsement:

- Proposal 1: Whether a Feature requires Charging/OAM aspects or not should be decided as early as possible (preferably at the start of the Feature specification), and be revisited on a regular basis during the whole Release.

  - This should be documented in the WID form as early as possible (ideally from Stage 1/SA1, or Stage2/SA2/RAN), using clause 8 (Aspects that involve other WGs).

  - A dedicated NWM document shall be maintained for each release to capture the relationship of Charging/OAM support to SA1/SA2/RAN features (see https://nwm-trial.etsi.org/#/documents/9187)

  - A regular SA5 report shall be made to SA with latest status information.

- Proposal 2: Companies contributing to a Feature should also contribute to the Charging/OAM aspects.

  - This will ensure completeness of the end-to-end 3GPP standard solution.

- Proposal 3: The default completion time for defining the network support Charging/OAM Stage 3 follows the code freeze date.

  - Exceptions sheets can be used if needed.

- Proposal 4: If, at the Charging/OAM completion time (potentially extended by the exception sheet), there are still Feature(s) missing completion of their Charging/OAM aspects then:

  - The SA5 chair shall report these Feature(s) to SA, which in turn will take the appropriate action(s) (e.g. grant even more time for the completion of the OAM/Charging aspects, or postpone the entire Feature to the next Release, or Operators can accept the Feature to stay in the original Release without charging/OAM, etc.)

  - Features missing Charging/OAM aspects will be flagged as such in the Work Plan and in the Release description document.