## Slide 1
1
Next Generation Architecture for New Radio
Vodafone, Qualcomm
3GPP TSG SA#72
Busan, Korea, 15th – 17th June 2016
SP-160442

## Slide 2: TSG RAN timeline updates
This week’s RAN # 72 is expected to re-discuss the timeline for “New Radio” (c.f. 5G)
That discussion is important to ensure that 3GPP remains relevant to the world and that “5G” can:
  Encourage new industry sectors to adopt 3GPP’s technology; - c.f. Rel 12 features aimed at encouraging the Public Safety community to adopt 3GPP technology
  Generate the economies of scale needed to fund “5G” R&D - c.f. after Rel 8, apparent lack of resources to sustain leading edge developments of both LTE and WiMAX
This document focuses on the relationship of the SA timeline with the RAN timeline.

## Slide 3: Proposals
SA coordinate with RAN and align the schedules such that “Next Gen” and “Standalone New Radio” are a co-ordinated product
SA#72 to task SA2 to develop a plan on how to complete a “NextGen” study by SA#74 to enable delivery of the new core network architecture (including stage 3 specifications) aligned with “Standalone New Radio” Note: SA2 should embark on this plan with the anticipation of its approval by SA#73

## Slide 4: RP-160813’s Proposed re-schedule - milestones & checkpoint
On condition that the5G phase 1 spec to be finished in March June 2018
CHECKPOINT: RAN#75: March 2017:
Initial specification work may start only if TSG RAN agrees that sufficient progress has been made on the key aspects (see next slide) for 5G NR to meet 5G RAN requirements
On condition that the5G phase 1 spec to be finished in March June 2018
Only if CHECKPOINT was passed, Non StandAlone NR spec complete, Targeting RAN#78/Dec’17, at latest RAN#79. Functionally complete
Priority <6GHz and >6GHz licensed bands (unpaired and paired)
eMBB and Low Latency User Plane support
“Non-standalone” 5G NR with LTE as anchor for Control Plane & considering at least LTE EPC connectivity (other CN connectivity pending TSG-SA decision)
StandAlone NR spec complete targeting RAN#81/Sep’18, at latest RAN#82. Functionally complete:
All RAN functionality for standalone,
Core Network [dependent on SA2 (re)plan]
NAS protocol
NSA-NR
SA-NR
RAN#86, Dec 2019 latest: Full NR spec completion for IMT 2020.
Functionally complete, contains e.g. D2D, MBMS..
Full IMT-2020 NR
2017
2018
2019

## Slide 5: Need to align SA & CT timeline to RAN “standalone”
Non-StandAlone 5G expected to launch with largely unmodified EPC connected by S1-MME to LTE eNB, and to use Dual Connectivity concepts for data transfer.
For Next Gen architecture to be relevant, the new “Next Gen” UE <-> Core Network (NAS) protocol needs to be available for launch of the StandAlone system.
Otherwise EPC will be reused and unlikely to ever be removed from use with New Radio

## Slide 6: Architecture developments not linked to RAN developments tend to be less successful
Iu mode GERAN specifications defined new NAS protocol: “chicken and egg” situation, e.g. of: - terminal developers wanting to see wide geographic core network availability; and - core network vendors/operators needing good device penetration before investing
Release 8, 2G/3G “S4 SGSN” - individual new 3G/2G feature did not justify investment/rollout of S4 SGSN, - hence new 3G/2G features also added to legacy Gn/Gp SGSN Result -> Slow/low level of deployment of S4 SGSN
 “UE visible” architectural changes tend to be fundamentally linked to new RAN

## Slide 7: Current SA2 timeline
SA 2 SID is in SP-150853, both it and TR 23.799’s scope say: “The complete or partial conclusions of this study will form the basis for the normative work and/or for any further study.”
TR 23.799 timeline expected to slip by at least 3 months (it is not yet presented for information).
Current focus of TR 23.799 work is on “Key Issues” and candidate “Solutions”, not yet on construction of a complete architecture. Prioritisation of the tasks is essential in order to enable to timely agreement on the architecture vision.
SA2 normative work after targeted study: 9 months to approval
CT(1) normative work 9 months after SA(2) work approval
New specifications [If Study Item, one TR is anticipated] |  |  |  |  |  | 
Spec No. | Title | 1st rsp. WG | 2nd rsp. WG(s) | Presented for information at plenary# | Approved at plenary # | Comments
TR 23.xxx | Study on Architecture for Next Generation System | SA2 |  | TSG SA#72 (June 2016) | TSG SA#73 (September, 2016) | Technical Report

## Slide 8: Proposed SA timeline update to align SA/CT Next Gen with RAN New Radio
SA2 specify
StandAlone NR spec complete targeting RAN#81/Sep’18, at latest RAN#82. Functionally complete:
All RAN functionality for standalone,
Core Network
NAS protocol
CT specify
SA-NR
2017
2018
SA2 focussed
study
2016
SA3 study
SA1 work
SA5 study
SA3 specify
Buffer for slippage
Note probable SA1, 3, 5 timeline changes

## Slide 9: Thank You
9