## Slide 1: SA#85 Agreements on SA R17 Prioritization & Content
Georg Mayer, SA Chairman

## Slide 2: Prioritized R17 List

## Slide 3: R17 Prio: Working Assumptions
The following list is taken as the current working assumption.
Green items are in or in*. Red items are out.
Items which are out shall not be progressed in Rel-17 by SA2.
Items which are in may be worked on in Q4 by SA2.
Items which are in* are conditionally included and shall not be worked on in Q4 by SA2.
Planning will be done based on max 3 TUs per item per SA2 meeting. This doesn’t preclude that SA2 could assign more than 3 TUs at a specific meeting due to available time, starting from SA#85.
in & in* items should be broken down into work tasks by SA2 in Q4. Each work task should be in the form of a headline + an assigned TU estimation.
SA2 will NOT do any down-scoping of any items in Q4.
SA#86 will prioritize the in work tasks until sufficient TUs are freed to cover all in items in R17. When TUs are freed (or more time is available) then SA#86 will select the work tasks of in* items.
SA has the intention to accommodate as many in* items as possible in R17.

## Slide 4: Way Forward for SA Rel-17 Prioritization
SA2 during Q4/2019
SA2 should break down each in & in* item on the R17 items list into self-contained work tasks. Each work task needs to include a TU estimation for both study and work phase. The TU estimation of an item will be the sum of it work task TUs.
SA2 shall identify the work tasks of the in & in* items in Work Task Papers. Those have to be finally agreed by SA2.
The work Task Papers including the TU estimations need to be agreed latest by the end of SA2#136
The Work Task Papers will be the input from SA2 to SA.
Before SA#86
For a better overview, a list of all Work Tasks (sorted by Work Item), listing all assigned TUs will be made available before SA#86 by the SA Chairman.
There will be no collection and consolidation of company prioritized lists before SA#86.

## Slide 5: Way Forward for SA Rel-17 Prioritization
SA#86
SA#86 will start on Tuesday, December 9 at 13:00 and finish on Friday, December 12 at 17:00
Joint Session with RAN will be on Wednesday from 18:00 – 20:30. (to be confirmed with RAN)
SA#86 on Tuesday & Wednesday will focus only on R17 prioritization and R17 timeline discussions.
Work Tasks that are worked on in Q4 by SA2 will not be automatically in, but need through the SA#86 prio process
SA#86 will not change items which were marked in by SA#85 to out.
SA#86 invites presentations from companies on R17 prioritization. The presentation time for each of these items will be a maximum of 3 minutes during the meeting.
Work-Task prioritization at SA#86 will first be done (as far as possible) for work task of items that are in.
If total TUs are freed up then work task prioritization for the in* items will be done.
Expected output from SA#86
  Final list of in items for Rel-17 (from SA perspective)

## Slide 6: Proposal: Moderated Item Discussions
Moderated Item Discussions
A new mailing list 3GPP_TSG_SA_DRAFTS shall be created, which allows for open offline discussions on R17 priorities between SA#85 and SA#86
For every item on the in/in* lists Item Moderator will be named. The moderator needs to be a delegate at SA#85 and SA#86.
Discussions should start after SA2#135 but before SA2#136.
For those Items where SA2 has already (proposed) Work Task Documents available discussions should start amongst the interested parties on the new SA_DRAFTS list. The discussion will be moderated by the Item Moderators.
The discussions should stay within the individual items. The goal is to get better understanding of what is commonly agreeable and what can be (even if painful) maybe left out.
The discussions will be based upon the SA2 decomposition of items into work tasks. These decompostions will NOT be changed. The goal of the discussions should be to find common ground for an initial proposal to SA#86 on the down-sized scope of the item.
The moderators will present the outcome of these discussions at SA#86.
Decisions will ONLY be made by SA#86, i.e. not on the mailing list and not by the moderators.