## Slide 1
Puneet Jain
SA2 Chairman, Intel
Maurice Pope
SA2 Support, MCC
SA2 Status Report to
TSG SA#88-e

## Slide 2: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 3: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 4: 1) General Aspects (1/7)
SA2 meetings held since SA#87-e
  SA2#138E: 20 – 24 April 2020
    Electronic meeting in place of SA2#138 with limited agenda focusing on pre-Rel-17 items
    No Rel-17 items (except for TEI17 proposals) were discussed.
  SA2#139E: 01 – 12 June 2020
    Electronic meeting in place of SA2#139 with limited agenda focusing on Rel-17 items and essential LS/CRs.
Future SA2 meetings
  SA2#140E: 19 Aug – 02 Sep 2020

## Slide 5: 1) General Aspects (2/7)
SA2 WG leadership
  Chairman: Puneet Jain (Intel)
  Vice Chairmen: Tao Sun (CMCC), Andrew Bennett (Samsung)
  Secretary: Maurice Pope (MCC)
Many thanks to Maurice Pope and vice chairs, Andrew Bennett and Tao Sun for their outstanding support!

## Slide 6: 1) General Aspects (3/7)
Statistics at SA WG2 #138-e:
228 delegates ‘attended’ (registered) for SA WG2 #138-e
  ~3700 e-mails were sent to the list during the e-meeting
  806 documents (including revisions), 806 documents handled including:
    658 CRs (including revisions)
    68 Incoming LSs, of which 22 were postponed
    19 Outgoing LSs Approved
  36 documents postponed
Total CRs agreed: 256 (of which, 10 were further revised/agreed at SA WG2#139-e)
Statistics at SA WG2 #139-e:
326 delegates ‘attended’ (registered) for SA WG2 #139-e (Only registered delegates were added to the EMEET List)
  ~7000 e-mails were sent to the list during the e-meeting
  1201 documents (including revisions), 1201 documents handled, including:
    115 CRs (including revisions)
    83 Incoming LSs, of which 21 were postponed
    31 Outgoing LSs Approved
  43 documents postponed
Total CRs agreed: 45
819 people registered on the SA WG2 e-mail reflector on 10 March 2020

## Slide 7: 1) General Aspects (4/7)
Chart: SA WG2 meeting attendance
| 88 | REL-11 FREEZE: 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | REL-12 FREEZE: 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107+E | 108 | REL-13 FREEZE: 109 | 110 | 111 | 112 | 113 | 113AH | 114 | 115 | 116 | REL-14 FREEZE: 116-bis | 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 123 | REL-15 FREEZE: 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | REL-16 FREEZE: 133 | 134 | 135 | 136 | 136AH | 137-e | 138-e | 139-e | 140 | 141 | (Expected Rel-17 FREEZE): 142
 | 157 | 139 | 133 | 162 | 135 | 142 | 139 | 173 | 181 | 165 | 158 | 153 | 189 | 146 | 133 | 145 | 142 | 144 | 195 | 159 | 175 | 182 | 113 | 137 | 200 | 137 | 107 | 157 | 168 | 169 | 143 | 157 | 233 | 182 | 175 | 191 | 188 | 156 | 154 | 156 | 222 | 196 | 174 | 149 | 140 | 152 | 149 | 165 | 191 | 153 | 178 | 279 | 280 | 229 | 189 | 241 | 180 | 124 | 228 | 326

## Slide 8: 1) General Aspects (5/7) Resource usage
SA2 meetings
Number of Sessions
Chart: 
| 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 123 | REL-15 FREEZE: 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | REL-16 FREEZE: 133 | 134 | 135 | 136 | 136AH | 137-e | 138-e | 139-e | 140 | 141 | (Expected Rel-17 FREEZE): 142
maintenance | 5 | 6 | 5 | 6 | 6.7 | 6.5 | 6 | 3.4 | 5 | 3 | 4.5 | 3.8 | 4 | 4 | 1.5 | 1.2 | 3 | 1.5 | 0.9 | 0.9 | 2 | 0.9 | 3.5 | 2.1 | 1.6 | 2 | 2 | 0 | 0
Rel-15 5GS / maintenance | 18 | 23 | 24 | 27 | 31 | 32.5 | 36 | 37 | 24 | 25 | 19 | 19 | 15 | 15 | 13.7 | 11.5 | 9 | 9.3 | 8.2 | 7.2 | 6 | 8.9 | 7.7 | 5 | 6 | 0 | 0
Rel-16 work | 3.7 | 13.5 | 12 | 19.5 | 20 | 26.4 | 28.6 | 31.2 | 34.9 | 34.9 | 34.4 | 35.3 | 37.7 | 33 | 21 | 23.2 | 14.5 | 16 | 0 | 0
Rel-17 work | 10.8 | 11 | 12.5 | 0 | 0 | 0

## Slide 9: 1) General Aspects (6/7) Document Handling / Meeting
Number of Tdocs
Chart: 
| 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | REL-12 FREEZE: 100 | 101 | 101b | 102 | 103 | 104 | 105 | 106 | 107+E | 108 | REL-13 FREEZE: 109 | 110 | 110AH | 111 | 112 | 113 | 113AH | 114 | 115 | 116 | REL-14 FREEZE: 116-bis | 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 122e | 123 | REL-15 FREEZE: 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | REL-16 FREEZE: 133 | 134 | 135 | 136 | 136AH | 137-e | 138-e | 139-e | 140 | 141 | (Expected Rel-17 FREEZE): 142
#approved/endorsed/merged (total) | 108 | 117 | 115 | 134 | 147 | 170 | 168 | 165 | 134 | 123 | 56 | 145 | 150 | 130 | 212 | 198 | 162 | 162 | 168 | 161 | 61 | 151 | 175 | 180 | 87 | 86 | 224 | 278 | 317 | 158 | 210 | 151 | 224 | 269 | 264 | 311 | 368 | 67 | 414 | 467 | 399 | 516 | 483 | 434 | 364 | 423 | 427 | 503 | 407 | 432 | 417 | 561 | 446 | 508 | 480 | 406 | 237 | 318 | 529
#not handled, postponed | 77 | 149 | 91 | 138 | 144 | 124 | 101 | 131 | 117 | 23 | 3 | 49 | 63 | 72 | 70 | 66 | 73 | 74 | 65 | 27 | 34 | 145 | 112 | 120 | 35 | 120 | 90 | 53 | 52 | 166 | 108 | 122 | 178 | 254 | 254 | 188 | 200 | 2 | 148 | 85 | 176 | 154 | 186 | 189 | 170 | 185 | 188 | 160 | 133 | 193 | 274 | 154 | 265 | 473 | 351 | 249 | 71 | 33 | 43
#noted | 120 | 139 | 155 | 131 | 123 | 121 | 110 | 165 | 172 | 141 | 62 | 95 | 137 | 143 | 143 | 143 | 141 | 120 | 77 | 65 | 38 | 103 | 78 | 124 | 43 | 112 | 137 | 119 | 131 | 70 | 97 | 95 | 101 | 138 | 142 | 119 | 109 | 7 | 163 | 137 | 142 | 137 | 132 | 183 | 113 | 90 | 132 | 158 | 124 | 138 | 216 | 198 | 181 | 177 | 187 | 169 | 202 | 196 | 202

## Slide 10: 1) General Aspects (7/7) SA2 Agreed CRs by Release / Meeting
Number of CRs
Chart: 
| 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | REL-12 FREEZE: 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107+E | 108 | REL-13 FREEZE: 109 | 110 | 110AH | 111 | 112 | 113 | 113AH | 114 | 115 | 116 | REL-14 FREEZE: 116-bis | 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 122e | 123 | REL-15 FREEZE: 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | REL-16 FREEZE: 133 | 134 | 135 | 136 | 136AH | 137-e | 138-e | 139-e | 140 | 141 | (Expected Rel-17 FREEZE): 142
Rel-12 CR | 2 | 2 | 4 | 11 | 8 | 19 | 21 | 35 | 50 | 38 | 64 | 55 | 39 | 35 | 34 | 21 | 11 | 10 | 9 | 1 | 9 | 3 | 3 | 3 | 1
Rel-13 CR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10 | 19 | 13 | 14 | 6 | 9 | 56 | 25 | 58 | 73 | 41 | 11 | 35 | 29 | 25 | 25 | 9 | 11 | 2 | 5 | 2 | 4 | 2 | 5 | 3 | 1 | 1 | 1 | 1 | 0 | 1
Rel-14 CR | 4 | 21 | 69 | 81 | 33 | 56 | 23 | 13 | 17 | 18 | 20 | 10 | 8 | 10 | 8 | 1 | 7 | 2 | 1 | 2 | 5 | 1 | 1 | 1
Rel-15 PCR/draftCR | 63 | 126 | 117 | 121 | 171 | 214 | 62 | 287 | 328 | 182 | 4 | 0 | 0
Rel-15 CR | 19 | 19 | 27 | 27 | 12 | 351 | 201 | 213 | 119 | 159 | 100 | 102 | 78 | 74 | 50 | 40 | 17 | 6 | 10 | 3 | 4 | 6 | 2
Rel-16 PCR/draftCR | 43 | 80 | 170 | 147 | 181 | 171 | 207 | 250 | 88 | 87 | 71 | 103 | 26 | 39 | 30 | 21 | 0 | 0 | 0
Rel-16 CR | 2 | 3 | 66 | 133 | 117 | 233 | 279 | 205 | 260 | 174 | 197 | 248 | 31
Rel-17 PCR/draftCR | 48 | 55 | 91 | 0 | 0 | 348

## Slide 11: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 12: 2.1) Rel-14 and before Maintenance (1/1)
Work Progress on Corrections (Category A CRs are not counted)
  R12: none
  R13: none
  R14: none

## Slide 13: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2 Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 14: 2.2) Rel-15 Work and Maintenance (1/2)
Work Progress on Corrections (Category A CRs are not counted)
  R15: 1 CR for TS 23.401 (CIoT_Ext, System support
                for wake up signal)

## Slide 15: 2.2) Rel-15 Work and Maintenance (2/2)
Progress since SA#87-e:
  Rel-15 CRs agreed for TS 23.501 (3 CRs), TS 23.502 (3 CRs) + Rel-16 Mirrors (6 CRs).
  TEI16 5GS_Ph1 CRs agreed for TS 23.501 (8 CRs), TS 23.502 (19 CRs), TS 23.503 (9 CRs)
Next steps:
  FASMO corrections
  Further aligning with the work from other WGs
WI Code | Work Item Title | WP | Target Date | WID#
5GS_Ph1 | 5G System – Phase 1 | 100% | Dec, 17 | SP-160958

## Slide 16: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 17: 2.3) Rel-16 Work and Maintenance (1/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_PARLOS_SA2 | Study on System enhancements for Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | 100 -> 100% | Sep, 18 | SP-180501
PARLOS | System enhancements for Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | 100 -> 100% | Mar, 19 | SP-180738
Progress since SA#87-e:
  No new CRs agreed.
  RAN impacts or dependencies:
  None identified
Next steps:
  Maintenance

## Slide 18: 2.3) Rel-16 Work and Maintenance (2/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5WWC | Study on the Wireless and Wireline Convergence for the 5G system architecture | 100 -> 100% | Dec, 18 | SP-170380
5WWC | Wireless and Wireline Convergence for the 5G system architecture | 100 -> 100% | Jun, 19 | SP-181117
Progress since SA#87-e:
  Maintenance work ongoing, 15 CRs (7 CRs to TS 23.316, 3 CRs to TS 23.501, 4 CRs to TS 23.502, 1 CRs to TS 23.503) were agreed.
  RAN impacts or dependencies:
  None Identified
Next steps:
  Maintenance

## Slide 19: 2.3) Rel-16 Work and Maintenance (3/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ATSSS | Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture | 100 -> 100% | Dec, 18 | SP-180732
ATSSS | Access Traffic Steering, Switch and Splitting support in the 5G system architecture | 100 -> 100% | Jun,19 | SP-181124
Progress since SA#87-e:
  Maintenance on going - 7 CRs to TS 23.501, 7CRs to TS 23.502, 4 CRs to 23,503 approved.
  Open Issue - Non-homogeneous support for ATSSS was resolved
  RAN impacts and dependencies:
  None identified
Next steps:
  Maintenance

## Slide 20: 2.3) Rel-16 Work and Maintenance (4/17)
Progress since SA#87-e:
  Maintenance work ongoing, and alignments with the work from other WGs.
  1 CR to TS 23.285 and 21 CRs to TS 23.287 were agreed.
  2 CRs to TS 23.501, 1 CR to TS 23.502 and 3 CRs to TS 23.503 agreed regarding Uu QoS.
RAN impacts or dependencies:
  Nothing new identified.
Next steps:
  Maintenance and aligning with the work from other WGs.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eV2XARC | Study on architecture enhancements for 3GPP support of advanced V2X services (FS_eV2XARC) | 100 -> 100% | Dec, 18 | SP-180733
eV2XARC | Architecture enhancements for 3GPP support of advanced V2X services (eV2XARC) | 100 -> 100% | Jun, 19 | SP-181121

## Slide 21: 2.3) Rel-16 Work and Maintenance (5/17)
Progress since SA#87-e:
  Maintenance work ongoing, 32 CRs (24 CRs to 23.288, 8 CRs to TS 23.502, 1 CR to TS 23.503) were agreed.
  Open issue about whether/how to support abnormal UE behaviour for any UE is resolved
RAN impacts or dependences:
  None identified
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA | Study of enablers for Network Automation for 5G | 100 -> 100% | Dec, 18 | SP-180792
eNA | Enablers for Network Automation for 5G | 100 -> 100% | Jun, 19 | SP-181123

## Slide 22: 2.3) Rel-16 Work and Maintenance (6/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_CIoT_5G | Study on Cellular IoT support and evolution for the 5G System | 100 -> 100% | Dec, 18 | SP-180614
5G_CIoT | Cellular IoT support and evolution for the 5G System | 100 -> 100% | Jun, 19 | SP-181118
Progress since SA#87-e:
  Maintenance work ongoing, 19 CRs (1 CR to TS 23.273, 6 CRs to TS 23.501, 11 CRs to TS 23.502, 1 CR to TS 23.503) were agreed.
  RAN impacts or dependencies:
  None identified
Next steps:
  Maintenance

## Slide 23: 2.3) Rel-16 Work and Maintenance (7/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ETSUN | Study on Enhancing Topology of SMF and UPF in 5G Networks | 100 -> 100% | Dec, 18 | SP-180731
ETSUN | Enhancing Topology of SMF and UPF in 5G Networks | 100 -> 100% | Jun, 19 | SP-181116
Progress since SA#87-e:
  Maintenance work ongoing, 12 CRs (5 CRs to TS 23.501, 7 CRs to TS 23.502) were agreed.
  Decision taken on the issue of interworking between ETSUN and each of non 3GPP access, ATSSS, TSC, NPN, URLLC
  RAN impacts and dependencies:
  None identified
Next steps:
  Maintenance

## Slide 24: 2.3) Rel-16 Work and Maintenance (8/17)
Progress since SA#87-e:
  Maintenance work ongoing, 11 CRs (10 CRs to 23.273, 1 CR to TS 23.502) were agreed.
RAN impacts or dependencies:
  None identified.
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_eLCS | Study on Enhancement to Service Based Architecture for Location Services | 100 -> 100% | Mar, 19 | SP-180734
5G_eLCS | Enhancement to Service Based Architecture for Location Services | 100 -> 100% | Jun, 19 | SP-181119

## Slide 25: 2.3) Rel-16 Work and Maintenance (9/17)
Progress since SA#87-e:
  Maintenance work ongoing, 12 CRs (4 CRs to TS 23.401, 4 CRs to TS 23.501, 3 CRs to TS 23.502, 1 CR to TS 23.682) were agreed.
RAN impacts or dependencies:
  None Identified.
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_RACS | Study on optimisations on UE radio capability signalling | 100 -> 100% | Dec, 18 | SP-180599
RACS | Optimisations on UE radio capability signalling | 100 -> 100% | Jun, 19 | SP-190180

## Slide 26: 2.3) Rel-16 Work and Maintenance (10/17)
Progress since SA#87-e:
  5G-LAN, NPN and TSN: Maintenance work ongoing, 46 CRs (5G_LAN - 4 CRs; TSN - 34; NPN - 8) were agreed.
  Open Issues - NPN: NID for NSSF services, TSN: co-existence of plain ETH and IEEE TSN sessions to be clarified.
RAN impacts or dependencies:
  None
Next steps:
  Maintenance.
WI Code | Work Item Title | WP | Target Date | WID#
FS_Vertical_LAN | Study on 5GS Enhanced support of Vertical and LAN Services | 100 -> 100% | Dec, 18 | SP-180507
Vertical_LAN | 5GS Enhanced support of Vertical and LAN Services | 100 -> 100% | Jun, 19 | SP-181120

## Slide 27: 2.3) Rel-16 Work and Maintenance (11/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_URLLC | Study on enhancement of URLLC supporting in 5GC | 100 -> 100% | Jun, 19 | SP-180118
5G_URLLC | Enhancement of URLLC supporting in 5GC | 100 -> 100% | Jun, 19 | SP-181122
Progress since SA#87-e:
  Maintenance work ongoing, 4 CRs (2 CRs to TS 23.501, 2 CRs to TS 23.502) were agreed.
RAN impacts and dependencies:
  Identified issue on QoS monitoring is resolved by above CRs. LS from RAN WG3 is replied.
Next steps:
  Maintenance

## Slide 28: 2.3) Rel-16 Work and Maintenance (12/17)
Progress since SA#87-e:
  Maintenance work ongoing, 9 CRs (4 CRs to TS 23.501, 4 CRs to TS 23.502, 1 CR to TS 23.503) were agreed.
RAN impacts or dependencies:
  None identified
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_eSBA | Study on Enhancements to the Service-Based 5G System Architecture | 100 -> 100% | Dec, 18 | SP-180231
5G_eSBA | Enhancements to the Service-Based 5G System Architecture | 100 -> 100% | Jun, 19 | SP-181125

## Slide 29: 2.3) Rel-16 Work and Maintenance (13/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNS | Study on Enhancement of Network Slicing | 100 > 100% | Dec. 18 | SP-180503
eNS | Enhancement of Network Slicing | 100 > 100% | Jun. 19 | SP-181232
Progress since SA#87-e:
  Maintenance work ongoing, 12 CRs (5 CRs to TS 23.501, 7 CRs to TS 23.502) were agreed.
  Open Issue whether AUSF to host NSSAA services was resolved and new NF, NSSAAF (Network Slicing Specific Authentication & Authorization Function) was introduced to support NSSAA instead of AUSF
  RAN impacts and dependencies:
  None
Next steps:
  Maintenance

## Slide 30: 2.3) Rel-16 Work and Maintenance (14/17)
Progress since SA#87-e:
  Maintenance work ongoing, 3 CRs (1 CR to TS 23.501, 2 CRs to TS 23.502) were agreed.
RAN impacts or dependencies:
  None identified
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_UDICoM | Study on User data interworking, Coexistence and Migration | 100 > 100% | Jun, 19 | SP-190148
UDICoM | User data interworking, Coexistence and Migration | 100 > 100% | Jun, 19 | SP-190182

## Slide 31: 2.3) Rel-16 Work and Maintenance (15/17)
Progress since SA#87-e:
  Maintenance work ongoing, 3 CRs (2 CRs to TS 23.502, 1 CR to TS 23.503) were agreed.
RAN impacts or dependencies:
  None identified
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
xBDT | 5GS Transfer of Policies for Background Data Transfer | 100 -> 100% | Dec, 19 | SP-180509

## Slide 32: 2.3) Rel-16 Work and Maintenance (16/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eIMS5G | Study on Enhanced IMS to 5GC Integration | 100 ->100% | Jun, 19 | SP-180736
eIMS5G_SBA | SBA aspects of enhanced IMS to 5GC integration | 100 -> 100% | Jun, 19 | SP-190181
Progress since SA#87-e:
  Maintenance work ongoing, 1 CRs (1 CR to TS 23.501) was agreed.
  RAN impacts and dependencies:
  None
Next steps:
  Maintenance

## Slide 33: 2.3) Rel-16 Work and Maintenance (17/17)
WI Code | Work Item Title | WP | Target Date | WID#
IABARC | Architecture enhancements for the support of Integrated access and backhaul (IAB) | 100 -> 100% | Dec, 19 | SP-190627
Progress since SA#87-e:
  1 CR (TS 23.501, CR2382: IAB support in NPN deployment) conditionally approved
  1 LS response to RAN2, RAN3, SA, (cc CT1), on the approval of the above CR
  RAN impacts and dependencies:
  Formal approval of SP-200435 depends on approval of RAN2 CRs: R2-2004280/R2-2004281
Next steps:
  Maintenance based on inputs from other working groups.

## Slide 34: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 35: 2.4) Rel-17 Study/Work (1/12)
Progress since SA#87-e:
  Remaining Key Issues (such as Mobility for Large coverage areas or with moving tracking areas, or , Regulatory services with super-national satellite ground station) were evaluated (based on feedback from RAN2/RAN3/CT1 and SA3-LI) and corresponding conclusions have been finalized.
RAN impacts or dependencies:
  SA2 sent LS to RAN2, RAN3 and CT1 informing them that SA2 has finalised the study for the two remaining open key issues and ask two questions related to solution#1 implementation.
Next steps:
  Move to normative phase.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSAT_ARCH | Study on architecture aspects for using satellite access in 5G | 85% -> 100% | Dec, 19 -> June, 20 | SP-181253

## Slide 36
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 40% -> 60% | Jun, 20 -> Sep, 20 | SP-200093
Progress since SA#87-e:
  43 new Solutions has been agreed to address various KIs.
  7 existing solutions are updated to address Editor’s Notes.
RAN impacts and dependencies:
  None identified
Next steps:
  Resolve Editor’s Notes of existing solutions.
  Solution evaluation towards conclusion.
  Target Completion: 50 solutions in the TR. There is risk that several Key Issues may not conclude by Sep, 20. Original TU estimates were severely under-estimated.
2.4) Rel-17 Study/Work (2/12)

## Slide 37: 2.4) Rel-17 Study/Work (3/12)
Progress since SA#87-e:
  Agreed new solutions for all Key Issues.
  Progressed some existing solutions with resolution for editor’s notes, open items.
RAN impacts or dependencies:
  Coordination with RAN is needed on “survival time”.
  Coordination needed on other KIs depend on solutions concluded
Next steps:
  Progress solutions by resolving ENs.
  Work towards identification of commonalities, differences and way forward towards conclusion.
  Target Completion: Some key Issue may not conclude by Sep, 20 due to RAN dependency.
WI Code | Work Item Title | WP | Target Date | WID#
FS_IIoT | Study on enhanced support of Industrial IoT - TSC/URLLC enhancements | 40% -> 55% | Jun, 20 -> Sep, 20 | SP-200096

## Slide 38: 2.4) Rel-17 Study/Work (4/12)
Progress since SA#87-e:
  Revised SID (SP-200444) submitted for Approval, aligning scope to agreed Rel-17 prioritization at TSG#86.
  2 KIs have been revised and 1 KI (KI#6: Path Switching) has been removed as a result of downscoping exercise.
  16 new solutions and 21 solutions update agreed for inclusion in TR 23.752, there are now 38 solutions in TR 23.752 on all the 7 prioritized key issues.
  Solutions for KI#1 (Direct Discovery), #2 (Direct Communication), #7 (PC5 Charging) and #8 (Service Authorization) are considered stable and ready for evaluation and conclusion.
RAN impacts or dependencies:
  Solutions for KI#1, #2, #5 and #8 has minimal RAN impact.
  Solutions for KI#3 (UE-to-Network Relay) and #4 (UE-to-UE Relay) have dependencies on RAN and SA3. RAN/SA3 plan to start corresponding study work in August, this makes final conclusions on these two KIs in August meeting at high risk.
Next steps:
  Complete and consolidate the solutions. Communicate with RAN WGs on the TR contents and finalize/complete ENs.
  Start solution evaluation and interim conclusion(s).
  Target Completion: Some key Issue may not conclude by Sep, 20 due to RAN dependency.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% -> 65% | Jun, 20 -> Sep, 20 | SP-190443

## Slide 39: 2.4) Rel-17 Study/Work (5/12)
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 29% -> 60% | Jun, 20 -> Sep, 20 | SP-200091
Progress since SA#87-e:
  14 new solutions agreed for inclusion in TR 23.761
  There are now 22 solutions in TR 23.761 on all the three prioritized key issues.
  RAN impacts and dependencies:
  All three key issues may potentially lead to solutions with RAN impact and may require RAN coordination
  Whether normative phase can be completed in Q4 depends on the interactions with RAN in Q4
Next steps:
  Complete description of existing solutions and add any new solutions
  Solution evaluation and conclusion
  Target Completion: There is risk that study item may not conclude by Sep, 20 as all of the KI have RAN dependencies.

## Slide 40: 2.4) Rel-17 Study/Work (6/12)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 35% -> 50% | Jun, 20 -> Sep, 20 | SP-200092
Progress since SA#87-e:
  Definition clarifications and KI#7 terminology alignment.
  Agreed not to address KI#8 in Rel-17 time frame.
  Updated the two architectural baselines in Annex A.
  Added 24 new solutions: now 31 solutions are described in the TR, most of which focusing on session handling (KI#1) and on switch between multicast and unicast (KI#7).
  RAN impacts and dependencies:
  Most of the key issues may lead to RAN impact.
Next steps:
  Continue with solution discussions with focus on KI#1, KI#7 and architecture baseline.
  Start solution and architecture baseline evaluation and conclusion(s).
  List identified RAN dependencies and send liaisons to relevant RAN WGs.
  Target Completion: There is risk that study item may not conclude by Sep, 20 as all of the KI have RAN dependencies, and TU requirements were under-estimated.

## Slide 41: 2.4) Rel-17 Study/Work (7/12)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNS_Ph2 | Study on Enhancement of Network Slicing Phase 2 | 35% -> 55% | Jun, 20 -> Sep, 20 | SP-190628
Progress since SA#87-e:
  3 KIs have been revised and 1 KI has been obsoleted based on the feedback from GSMA on the GST parameters. 7 KIs are now remained in total.
  20 new solutions have been added. Total 31 solutions in TR to address various KIs.
  RAN impacts and dependencies:
  KI#s 3, 5 and 7 could have dependency on RAN.
Next steps:
  Resolve disagreement on the interpretation of frequency bands configuration within & among the TAs for a given Allowed NSSAI.
  Complete solution, evaluation and conclusion(s) for each Key Issue.
  Target Completion: There is risk that study item will not conclude by Sep, 20.

## Slide 42: 2.4) Rel-17 Study/Work (8/12)
Progress since SA#87-e:
  52 new solutions have been agreed
  4 pCRs to update the existing solutions and 1 PCR to update the existing key issue.
RAN impacts or dependencies:
  Regarding KI#8: UE data as an input for analytics generation, the method of collection of RAN impacting parameters from the UE will be investigated after the MDT work of TSG RAN is completed
Next steps:
  Complete solution, evaluation and conclusion(s) for each Key Issue.
  Target Completion: SID has 18 KI and 53 solutions in the TR. There is risk that several Key Issues will not conclude by Sep, 20. Original TU estimates were severely under-estimated.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA_Ph2 | Study on Enablers for Network Automation for 5G - phase 2 | 32% -> 55% | June, 20 -> Sep, 20 | SP-200098

## Slide 43: 2.4) Rel-17 Study/Work (9/12)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 35% -> 55% | Jun, 20 -> Sep, 20 | SP-200094
Progress since SA#87-e:
  Clarified KI#4
  Existing solutions updated and 33 new solutions added. TR 23.700-07 now includes 40 solutions and there are solutions for all Key Issues agreed to be prioritized for Rel-17 at SA#86
  SA1 clarified in LS reply (cc: SA, CT1, SA3, CT6) the scope of provisioning of UE credentials, related to KI#4
  Dependencies to SA3 identified by Editor’s notes and LS sent to SA3 for one of the aspects
  Dependencies to SA1 and CT1 identified by Editor’s notes regarding network selection and roaming/service continuity
  RAN impacts and dependencies:
  RAN impact depends on the conclusions of the KIs (e.g. KI#1, KI#2, KI#4).
Next steps:
  Complete description of existing solutions, and add any new solutions
  Evaluation and agree on conclusions
  Target Completion: There is risk that several Key Issues will not conclude by Sep, 20 due to RAN/SA3 dependencies, and due to TU under-estimation.

## Slide 44: 2.4) Rel-17 Study/Work (10/12)
Progress since SA#87-e:
  Update to architectural assumptions based on moderated email discussion, 20 solutions added addressing all key issues.
  RAN impacts and dependencies:
  One solution proposes porting to NR the LTE aerial features.
Next steps:
  Complete solutions and solve pending open questions.
  Moderated email discussion to address key building blocks of overall solution, to aim at conclusions.
  Focus on evaluation and conclusions.
  Target Completion: Study is on target to be completed by Sep, 20.
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 25% -> 50% | Jun, 20 -> Sep, 20 | SP-200097

## Slide 45: 2.4) Rel-17 Study/Work (11/12)
Progress since SA#87-e:
  TR 23.776 skeleton and scope agreed.
  1 key isue and 1 solution covering Support of QoS aware NR PC5 power efficiency for pedestrian UEs were captured in TR 23.776.
RAN impacts or dependencies:
  Sidelink DRX related operation
Next steps:
  Continue the study.
  Target Completion: There is risk that study item will not conclude by Sep, 20 due to RAN dependencies.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eV2XARC_Ph2 | Study on architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 0% -> 25% | Jun, 20 -> Sep, 20 | SP-190631

## Slide 46: 2.4) Rel-17 Study/Work (12/12)
Progress since SA#87-e:
  3 KIs have been introduced.
  8 new solutions have been proposed to address various KIs.
  Strong dependency on IETF progress on QUIC/MP-QUIC development for some proposed solutions. These solutions require tighter collaboration between 3GPP and IETF to address SA2 requirements in a timely manner
RAN impacts or dependencies:
    None identified.
Next steps:
  Complete solution, evaluation and conclusion(s) for each Key Issue.
  Target Completion: There is risk that study item will not conclude by Sep, 20 due to IETF dependency dependencies.
WI Code | Work Item Title | WP | Target Date | WID#
FS_ATSSS_Ph2 | Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture Phase 2 | 0% -> 35% | Jun, 20 -> Sep, 20 | SP-200095

## Slide 47: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF and External SDO Normative Reference Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 48: 2.5) IETF and External SDO Normative Reference Update (1/1)
None identified

## Slide 49: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 50: 3) SA2 Work Planning
Due to COVID-19, most of 2020 F2F meetings have been cancelled and converted into e-meeting.
SA2 managed to have fairly decent progress during e-meetings but it comes at price of longer duration of e-meetings and with reduced agenda. It is not feasible to plan 2 e-meetings in Q4, 20 with full meeting agenda.
SA2 has agreed 9 new TEI17 WIDs during Q1 and Q2 (see slide# 52).
Several Rel-17 study items may not conclude at Sep, 20 due to RAN dependencies, and/or under-estimation of required effort for the completion of the SID. As a result, Rel-17 normative work completion by stage-2 freeze deadline of Dec, 20 is at high risk.
Action to SA#88-e:
  TSG SA to request RAN WGs (especially RAN2/3) to allocate time during their Q3 and Q4, 2020 e-meetings to respond to LSs from SA2 on Rel-17 topics.
  SA2 request TSG SA to evaluate feasibility of shifting Rel-17 stage-2 freeze dates to March 2021.

## Slide 51: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 52: 4) Documents for Information and Approval (1/2)
TEI17 WID(s) for Approval
SA-TD | Type | WI Code | Title | TUs Requested
SP-200452 | WID NEW | TEI17_IMSGID | IMS Optimization for HSS Group ID in an SBA environment | 0.5
SP-200453 | WID NEW | TEI17_SAPES | Support for Signed Attestation for Priority and Emergency Sessions | 0.5
SP-200446 | WID NEW | TEI17_DCAMP | Dynamically Changing AM Policies in the 5GC | 1.0
SP-200454 | WID NEW | TEI17_IPU | IP address pool information from UDM | 0.5
SP-200455 | WID NEW | TEI17_GroupEventMont | Dynamic management of group-based event monitoring | 0.5
SP-200456 | WID NEW | TEI17_N3SLICE | Support of different slices over different Non 3GPP access | 0.5
SP-200457 | WID NEW | TEI17_NIESGU | N7/N40 Interfaces Enhancements to Support GERAN and UTRAN | 0.5
SP-200447 | WID NEW | TEI17_SPSFAS | New WID on same PCF selection for AMF and SMF. | 0.5
SP-200448 | WID NEW | TEI17_SE_RPS | New WID: System enhancement for Redundant PDU Session. | 0.5

## Slide 53: 4) Documents for Information and Approval (2/2)
Rel-17 SID(s)/WID(s) for Approval
SA-TD | Type | WI Code | Title
SP-200444 | SID REVISED | FS_5G_ProSe | Revised SID: Study on System enhancement for Proximity based Services in 5GS
SP-200445 | WID REVISED | 5GSAT_ARCH | Change of rapporteur on WID 'Integration of satellite systems in the 5G architecture'

## Slide 54: Contents
1) General aspects (events since SA#87-e, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 55: 5) Collected Items requiring action from SA
1) Approval of new/revised SID(s)/WIDs (Please see slide# 52 & 53)
2) TSG SA to request RAN WGs (especially RAN2/3) to allocate time during their Q3 and Q4, 2020 e-meetings to respond to LSs from SA2 on Rel-17 topics. (Please see slide# 50)
3) SA2 request TSG SA to evaluate feasibility of shifting Rel-17 stage-2 freeze dates to March 2021. (Please see slide# 50)

## Slide 56
Thank You!