Title

Advanced Addressing

Intended Output

Technical Report

Impact on Other Technical Specifications and Technical Reports

This report will be based on the ETSI specification UMTS 22.75. ( Advanced Addressing ).  Any other agreed requirements defined by the other partners or individual members will be captured in this report.

Technical Scope

UMTS is a telecommunications system which allows person to person and machine to machine interactions. Addressing schemes allow users (people or machines) to indicate to the system the target of a particular communications session. Traditionally, this has involved a user dialling a telephone number to indicate the destination of a telephone call.

This report describes the desirable features of the UMTS advanced addressing scheme requirements for numbering and addressing for UMTS , and example directory, application and translation mechanisms which could be used to enhance the service to the customer.

A key requirement is the need for UMTS users to be able to interwork with users on  legacy schemes. These would encompass telephony, data and multimedia.

The requirements developed in this report are to be used within 3GPP  to develop a  proposal for numbering and addressing applying existing schemes or developing new ones.

.

Impact on Other 3GPP Work Items

This report may be converted into a technical report at a later date.

Schedule of Tasks to be Performed.

| Task | Planned Start | Planned Finish |
| --- | --- | --- |
| Work Item Creation | 15/2/99 | 23/2/99 |
| Work item Approval by TSG SA | 1/3/99 | 5/3/99 |
| Review of requirements from other partners input papers | 22/2/99 | 6/7/99 |
| Members and partners input and e-mail discussion | 22/2/99 | 6/7/99 |
| Review and resolution of issues at WG1 meeting | 6/7/99 | 9/7/99 |
| Presentation to other groups for comments | 12/7/99* | 30/9/99 |
| Ad hoc meeting to resolve any final problems | 30/4/99* | 1/11/99 |
| Submission to TSG SA for approval | 1/11/99* | 1/11/99 |

Note:	* These dates are a guess at present

Supporting Individual Members

All WG1 members

Rapporteur

Stephan Klier ( Mannesmann )

Tel:	+49 211 533 3807

FAX:	+49 211 533 2804

E-mail	stephan.klier@2privat.de