| 3GPP TSG-SA-WG1, Meeting #7 Sophia Antipolice Feb 9 – Feb 11, 2000 | Tdoc S1-00 0061 |
| --- | --- |

Agenda Item:

Source:	NTT DoCoMo

Title:	Approval procedure of Multicall

Effected Specifications / Releases: Release '99

Document for:	Approval

## I. Introduction

Since SA agreed that Multicall was R99 item.  However it comes up against interruption of working progress at CN.    As a result, it was recognized that more clarification is necessary on Multicall Stage1 (22.135).

It was agreed that Multicall Joint Ad Hoc, which was introduced as TSG SA#6(99)625 at SA #6 Nice(See below), shall be held on 17-18, Feb.  The purpose of the Joint Ad Hoc is to complete all necessary CRs and documentation related to CN WGs. It might affect to Stage1.

# II. Proposal

Due to be in time of Mutlicall for R99, we suggest to agree email approval procedure to be able to approve CR by Multicall Joint Ad Hoc after Ad Hoc  in case of S1 needs.

Time-Plan for CR approval of Mutlicall

| Date | Meeting | Action |
| --- | --- | --- |
| 7-11 Feb 2000 | TSG-SA WG1, Meeting #7 | S1 agrees on clarifications to the stage 1 |
| 14-16 Feb 2000 | TSG-CN WG2B | N2B discusses and conditionally agrees on additional CRs to MAP and Basic Call Handling. |
| 17-18 Feb 2000 | TSG-CN Joint Multicall Ad Hoc | The draft stage 2 and stage 3 documents. |
| 2weeks Approval | S1 E-mail Approval | Mailing Approval of CR which influences to Stage1 is performed. |
| 13-17 Mar 2000 | TSG Plenary, Meeting#7, | TSG-CN/SA approves stage 1, stage2, stage 3, and all changes on Multicall for release '99. |

Technical Specification Group Services and System Aspects	TSGS#6(99)625

Meeting #6, Nice, France, 15-17 December 1999

Source:	NTT DoCoMo

Title:	Milestone for Multicall

Document for:	Information

Agenda Item:	    6.1.3

Multicall AdHoc Working Plan and the Milestone

1: In Offline Meeting

An offline meeting for Multicall issue was held in Dec 16, the major objective of the meeting was clarifying MC related issues (such as Stage 2 level descriptions for MC) that were raised in CN#6 and find a working plan to solve the concerns and complete the MC-WI in R99 time schedule. This minutes recorded the outcome of the meeting.

2: Basic Agreements and High level understandings

  - Recognize Multicall as a R99 WI. Therefore this meeting was held to realize the completion of the topic in the expected time schedule.

  - It is planned to have a NSS-Joint AdHoc on Multicall during February 17-18 2000 at Milan, Italy, following N2B meeting. The meeting invites those who has interesting on Multicall, especially N1, N2, NSS and S1 delegates. This will be informed to each WG members from the chairperson.

3: Objective of the NSS-Joint AdHoc on Multicall:

The meeting is NOT a place to start discussions, but it was agreed that the purpose of the meeting is to solve all issues, which means complete all CRs with all necessary documentation on Multicall.

4: Milestone (work plan) toward the NSS-Joint AdHoc

This work plan was built to smoothly complete all Multicall issues at the AdHoc meeting. The following time schedule (steps) was recognized.

Note; Toward NSS-Joint AdHoc meeting, e-mail discussion starts by following steps. For the e-mail discussion NSS mailing list will be used. All of those who want to participate this discussion should subscribe NSS-ML. ( 3GPP_TSG_CN_SS_ADHOC@LIST.ETSI.FR)

Step-1) Our working assumption is separate stage2 for MC, does anybody has objection to this direction? If so, state them.

By 04 Jan 2000 via e-mail.

Background : In CN#6, the necessity of Multicall stage2 was proposed. Originally, such as in N2, the stage 2 description was included in 23.018, basic call procedure. But in the above offline meeting on Dec 16, in order to more clearly describe the relation of SS and MC, the formulation of independent stage 2 description was recognized.

Step-2) Merge comments raised at CN#6 + High level MC documents (N2 used to have such documents) => we will express this document as “Stage 1.5 for MC”.

By Jan 10 2000, by Japanese interesting companies.

Background : At CN#6, NSS chairman stated that it is necessary to prepare such document that describe High level functional procedure for MC(Stage 1.5 for MC), In order to clearly understand the relationship between MC and SS.

CN2 used to have a high level MC documentation to proceed MC discussion, a technical summary on multicall. The document includes some of the MC and SS relationships and information flows. It should be brushed up to reflect current status. Additionally, previous MC offline meeting raised some comments. These also to be included to updated, High level MC document.

(If the necessity of independent stage-2 document is agreed, this (Stage 1.5 for MC) draft document could be a bases of MC stage 2 document. ).  Japanese interesting companies will provide the draft document by the stated due date.

Step-3) Identification of Open issues after reviewing the documents (Stage 1.5 for MC).

By Jan 21 via e-mail.

Identify those open issues after reviewing the revised MC high level document, if any. The due date should critically be kept. All of the concerns have to be informed by the due date to be registered as open issues.

Step-4) Propose solutions

By Feb 04 2000 (fry)

Propose solutions to the risen open issues.

Step-5) Does it contentious, identify them

# By Feb 8 2000.

This step just identify those are contentious or not. Those are not contentious, prepare CRs.

Step-6) Draft CRs on non contentious issues.

Due for the CRs toward the meeting is Feb 14.

Step-7) Face to face meeting, NSS-Joint AdHoc on Multicall, 17-18 February 2000.

# At Milan, Italy following the N2B meeting.