## Slide 1: FS_eULRS Status Update Study on Enhancements to User Location Reporting Support
Zhuoyun Zhang
China Unicom
FS_eULRS Rapporteur
3GPP TSG-SA WG1 Meeting #68
San Francisco, USA, 17-21 November 2014
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_eULRS Status
Is this a new WI? <n>
This WI has been approved at SP#64
  Approved WID is in tdoc SP-140402
Notes: 1

## Slide 3: FS_eULRS Progress
Progress made at this meeting
  One new use case has been agreed: Use case on focus area based location reporting
  One use case has been updated: Update of use case on pre-configured location reporting time
  Two considerations have been agreed: considerations on charging, considerations on security and privacy
  Impact of use case 5.2 has been agreed
Study Item Completion: 70%
Draft TR 22.899 Completion: 70%
Controversial issues: None.
Notes: 1

## Slide 4: FS_eULRS Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 2
Number of slots requested for next meeting
  sum of plenary and drafting slots: 2
Notes: 1

## Slide 5: FS_eULRS Completion Date
Target completion date in WID: <06/2015> SP#68
Is current completion date the same as above? Y
Will target completion date be met? Y
Expected date to send TR to SA plenary:
  For information: SA1#69 (02/2015)
  For approval: SA1#70 (04/2015)
Notes: 1

## Slide 6: FS_eULRS Planning/Progress
Topics to focus on at SA1#69 (Feb 2015):
  Potential requirements
  Clean-ups
Planning for subsequent meetings
  SA1#70 (Apr 2015)
    Overview
    Conclusions
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Socialize requirements
  Tentative start date: <01/12/2014>
Notes: 1

## Slide 8: FS_eULRS Progress Estimate
Estimated percentage completion:
  SA1#69 (Feb 2015): 80%
  SA1#70 (Apr 2015): 100%
Notes: 1

## Slide 9: FS_eULRS Agreed documents
List of agreed documents at this meeting:
S1-144616 | one2many | Impact of Use Case 5.2
S1-144613 | China Unicom, CATR, ZTE | Use case on focus area based location reporting
S1-144544 | China Unicom | Update of use case on pre-configured location reporting time
S1-144545 | China Unicom | Considerations on Security and Privacy for eULRS
S1-144520 | China Unicom, Intel, ZTE | Considerations on Charging for eULRS
Notes: 1