## Slide 1: MCCoRe Status Update Mission Critical Servies Common Requirements
Andrew Thiessen
U.S. Dept. of Commerce
MCCoRe Rapporteur
3GPP TSG-SA WG1 Meeting #72
Anaheim, CA, USA, 16-20 November 2015
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: MCCoRe Status
Is this a new WI? Yes
This WI has not been approved by SP
  The following slides assume approval at SP#70
Notes: 1

## Slide 3: MCCoRe Progress
Progress made at this meeting
  Work Item proposal agreed
  Method for identification of requirements as common between MCPTT, MCVideo, and MCData agreed
    New TS to house such requirements
Work Item Completion: 0%
Draft TS 22.xxx Completion: 0%
Controversial issues
  None
S1-154595
Notes: 1

## Slide 4: MCCoRe Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 2
Number of slots requested for next meeting
  sum of plenary and drafting slots: 12
Number of Drafting session participants: 15
S1-154595
Notes: 1

## Slide 5: MCCoRe Completion Date
Target completion date in WID: 03/2016> SP#71
Is current completion date the same as above? Yes
Will target completion date be met? Yes
Expected date to send TS to SA plenary:
  For information: SA1#73 (02/2016)
  For approval: SA1#73 (02/2016)
S1-154595
Notes: 1

## Slide 6: MCCoRe Planning/Progress
Topics to focus on at next SA1 meeting:
  Structure of TS
  Identification and re-wording of MCPTT, MCVideo, and MCData common requirements for placement in MCCoRe
  Enumeration of MCCoRe requirements applicable to each MC service (MCPTT, MCVideo, and MCData)
S1-154595
Notes: 1

## Slide 7: Work plan between meetings
Email planning
  Email sent on 20/11/2015 laying out plan for project
  Common requirements analysis spreadsheet to be sent to SA1 reflector on 23/11/2015
  First pass of common requirements analysis to be completed on 11/12/2015 and submitted to rapporteur
Email discussion & conference call
  Identification of common requirements
    Focus on disagreements
    Determine grouping for TS structure
    Develop common re-phrasing method
  Planning for Okinawa meeting
  Tentative start date: 14/12/2015
S1-154595
Notes: 1

## Slide 8: MCCoRe Progress Estimate
Estimated percentage completion:
  now: 0%
  Next meeting: 100%
S1-154595
Notes: 1

## Slide 9: MCCoRe Agreed documents
List of agreed documents at this meeting:
S1-154395 | U.S. Dept. of Commerce, TTA | Mission Critical Service Common Requirements
S1-154570 | U.S. Dept. of Commerce, TTA | TS Skeleton for Mission Critical Services Common Requirements
S1-154595
Notes: 1