## Slide 1: USOS Status Update Unlicensed spectrum offloading system enhancements
Eddy Hall
Qualcomm Incorporated
USOS Rapporteur
3GPP TSG-SA WG1 Meeting #73
Okinawa, Japan, 1-5 February 2016
Notes: 1

## Slide 2: USOS Status
Is this a new WI? Y
This WI has not been approved by SP
  The following slides assume approval at SP#71
Notes: 1

## Slide 3: USOS Progress
Progress made at this meeting
  Agreed WID
  Agreed 2 CRs to introduce requirements to document data on unlicensed access, and that such data needs to be sufficiently detailed
Work/Study Item Completion: 100%
Controversial issues
  None
Notes: 1

## Slide 4: USOS Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 1/2
Notes: 1

## Slide 5: USOS Completion Date
Target completion date in WID: 03/2016, SP#71
Is current completion date the same as above? Y
Will target completion date be met? Y
Notes: 1

## Slide 6: USOS Agreed documents
List of agreed documents at this meeting:
S1-160541 | Qualcomm Incorporated, NTT DOCOMO | CR22.101v14.1.0: Accounting for usage when using unlicensed access networks
S1-160542 | Qualcomm Incorporated, NTT DOCOMO | CR22.115: Accounting for usage when using unlicensed access networks
Notes: 1