## Slide 1: FS_ePWS Status Update Enhancements of Public Warning System
Hyounhee Koo
SyncTechno Inc.
ePWS Rapporteur
3GPP TSG-SA WG1 Meeting #76
Tenerife, Spain, 7-11 November 2016
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_ePWS Status
Is this a new WI? No
Notes: 1

## Slide 3: FS_ePWS Progress
Progress made at this meeting
  Addition of TR scope agreed
Work/Study Item Completion: 5%
Draft TR 22.969 Completion: 5%
Controversial issues
  None
Notes: 1

## Slide 4: FS_ePWS Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 1
Number of slots requested for next meeting
  sum of plenary and drafting slots: 1
Notes: 1

## Slide 5: FS_ePWS Completion Date
Current expected dates to send TR to SA plenary:
  For information: SA#76 (06/2017)
  For approval: SA#77 (09/2017)
Have these dates been changed at this meeting? No
Notes: 1

## Slide 6: FS_ePWS Planning/Progress
Topics to focus on at next SA1 meeting:
  Introduction of new use cases
Planning for subsequent meetings
  SA1#78 (May 2017)
    Use cases
    Consolidation of requirements
    TR submission for the information
Notes: 1

## Slide 7: FS_ePWS Progress Estimate
Estimated percentage completion:
  now: 5%
  Next meeting: 20%
  In two meetings: 75%
Notes: 1

## Slide 8: FS_ePWS Agreed documents
List of agreed documents at this meeting:
S1-163394 | SyncTechno Inc. | Proposed scope for FS_ePWS TR 22.969
Notes: 1