## Slide 1: FS_PARLOS Status Update Feasibility Study on Provision of Access to Restricted Local Operator Access Services by Unauthenticated UEs
Betsy Covell
Nokia
FS_PARLOS Rapporteur
3GPP TSG-SA WG1 Meeting #76
Tenerife, Spain, 7-11 November 2016
Notes: 1

## Slide 2: FS_PARLOS Status
Is this a new WI? y
This WI has not been approved by SP
  The following slides assume approval at SP#74
Notes: 1

## Slide 3: FS_PARLOS Progress
Progress made at this meeting
  TR skeleton, Scope, and Overview
  4 use cases illustrating
    3 ways of making the local service addresses known to the user, including by operator website, by provisioning in the UE, and by captive portal,
    Requirements for the system to broadcast support of local service access, to identify a set of addresss for local service access, and to recognize a local service access attempt and allow it to succeed
  1 use case illustrating there is no impact to systems where the operator chooses not to provide the local service access
  Considerations on security and charging
  Consolidated potential requirements
Work/Study Item Completion: 75%
Draft TR 22.xxx Completion: 75%
Controversial issues
  none
Notes: 1

## Slide 4: FS_PARLOS Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 1
Number of slots requested for next meeting
  sum of plenary and drafting slots: 1
Notes: 1

## Slide 5: FS_PARLOS Completion Date
Current expected dates to send TR to SA plenary:
  For information: SA#74 (Dec/2016)
  For approval: SA#75 (Mar/2017)
Have these dates been changed at this meeting? n
Notes: 1

## Slide 6: FS_PARLOS Planning/Progress
Topics to focus on at next SA1 meeting:
  Definitions
  Review of security and charging considerations
  Conclusion
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  As needed
Notes: 1

## Slide 8: FS_PARLOS Progress Estimate
Estimated percentage completion:
  now: 75%
  Next meeting: 100%
Notes: 1

## Slide 9: FS_PARLOS Agreed documents
List of agreed documents at this meeting:
S1-163078 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe skeleton
S1-163244 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe - Scope
S1-163433 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe - Overview
S1-163247 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe – access to local service for roaming
S1-163248 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe – access to customer care using captive portal
S1-163086 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe – access to local service for service establishment
S1-163384 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe – local service addresses stored on UE
S1-163435 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe – failed access to local service
S1-163387 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe – Considerations
S1-163388 | Nokia, Alcatel-Lucent Shanghai Bell, Verizon, Qualcomm, Sprint | FS_PLeaSe – Potential requirements
Notes: 1