## Slide 1: FS_5G_HYPOS Status Update Study on positioning use cases
Lionel Ries
ESA (European Space Agency)
FS_5G_HYPOS Rapporteur
3GPP TSG-SA WG1 Meeting #83
West Palm Beach, Florida, USA, 20 - 24 August 2018
Notes: 1

## Slide 2: FS_5G_HYPOS Progress
Progress made at this meeting
  Some cleaning CRs (annex A, multiple – including conservative and ambitious scenario for accuracy levels in use case categories, updated figure)
  New use case on container management (no impact on KPI agreed in normative work in SA1#83, but impacts functional requirements to be processed in SA1#84)
Study Item Completion: 100 %
Controversial issues
  none
Notes: 1

## Slide 3: FS_5G_HYPOS Completion Date
Current expected dates to send TR to SA plenary:
  TS already approved in SA#80 (06/2018)
Have these dates been changed at this meeting? No
Estimated percentage completion: SA#81: 100 %
Notes: 1

## Slide 4: FS_5G_HYPOS Planning/Progress
Topics to focus on at next SA1 meeting:
Planning for subsequent meetings
Notes: 1

## Slide 5: Work plan between meetings
Email discussion
  NA
Telephone conference
  NA
Notes: 1

## Slide 6: FS_5G_HYPOS Essential Info
This WI has been approved at SP#76
  Approved WID is in tdoc SP-170589
Notes: 1