## Slide 1: FS_AIML_MT_Ph2 Status Update Study on AI/ML Model Transfer Phase 2 in 5GS
Yang Xu
OPPO
FS_AIML_MT_Ph2 Rapporteur
3GPP TSG-SA WG1 Meeting #98-e
Electronic Meeting, 9 – 19 May 2021
Notes: 1

## Slide 2: FS_AIML_MT_Phase2 Progress
Progress made at this meeting
  SID update to use SA1 terminology in justification and objective, change the Acronym to “FS_AIML_MT_Ph2”
  A TR skeleton was agreed for phase 2 work
  2 use cases were submitted but due to procedural issue, they were noted and will be brought back in next meeting:
    Use Case of AI model transfer management through direct device connection
    Use Case of direct device connection assisted Federated Learning
Work/Study Item Completion: 5%
Controversial issues
  None
Notes: 1

## Slide 3: FS_AMMT Planning
Planning for subsequent meetings
  SA1#99 (Aug 2022): 45%
    Scope, Introduction, New use cases and potential requirements
  SA1#100 (Nov 2022): 85%
    New/Updated use cases and potential requirements
    Start consolidation
  SA1#101 (Feb 2023): 100%
    Updated use cases and potential requirements
    Complete consolidation and conclusions
    Final TR clean-up
Notes: 1

## Slide 4: Work plan between meetings
Email discussion
  Will be arranged if necessary.
Telephone conference
  1 CC (~1.5h) is recommended be held to discuss introduction, scope, and use cases for distributed AIML.
Notes: 1

## Slide 5: FS_AIML_MT_Ph2 Completion Date
Current expected completion dates:
  For information: SA#98 (12/2022)
  For approval: SA#99 (03/2022)
Have these dates been changed at this meeting? No
Notes: 1

## Slide 6: FS_AIML_MT_Ph2 History
This Study Item was agreed at SA1#97e
  Approved WID is in tdoc SP-220083
  SA1#96e – SID in tdoc S1-214039 was noted
  SA1#97e – SID in tdoc S1-220039 was agreed
  SA1#98e – SID were updated and TR were agreed
Notes: 1