## Slide 1: IMS_WebRTC Status Update
Lu Lu
China Mobile
IMS_WebRTC Rapporteur
3GPP TSG-SA WG1 Meeting #60
Edinburgh, UK, 12th – 16th November 2012
Notes: 1

## Slide 2: IMS_WebRTC Status
Is this a new WI? Yes
This WI has not been approved by SA
  Agreed at SA1 #60 in tdoc S1-124511
  The following slides assume approval at SA #59
Notes: 1

## Slide 3: IMS_WebRTC Progress
Progress made at this meeting
  WID agreed
Work/Study Item Completion: 0%
Controversial issues
  none
Notes: 1

## Slide 4: IMS_WebRTC Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: < 1
Number of slots requested for next meeting
  sum of plenary and drafting slots: 2
    anticipate 2 slots for IMS_WebRTC CRs
Notes: 1

## Slide 5: IMS_WebRTC Completion Date
Target completion date defined in WID:
  <03/2013> SA#59
Current target completion date:
  <03/2013> SA#59
Will target completion date be met? Yes
Notes: 1

## Slide 6: IMS_WebRTC Planning
Topics to focus on for the next meeting:
  Based on the clear understanding on Use cases, add normative requirements in TS 22.101 and TS 22.228
Planning for subsequent meetings
  n/a
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Review Use cases
  Review draft CR(s)
Notes: 1

## Slide 8: Progress Estimate
Estimated percentage completion:
  SA1#61 (Jan 2013): 100%
Notes: 1