## Slide 1: FS_V2XLTE Status Update Study on LTE support for V2X services
Ki-Dong Lee
LG Electronics Inc.
FS_V2XLTE Rapporteur
3GPP TSG-SA WG1 Meeting #70
Los Cabos, Mexico, 13-17 April 2015
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_V2XLTE Status
Is this a new WI? <y/n> N
  Guide: remove one of the following bullets as appropriate:
This WI has been approved at SP#67
  Approved WID is in tdoc SP-150051
  Guide: indicate the SA tdoc number for the most recent version of the approved WID
Notes: 1

## Slide 3: FS_V2XLTE Progress
Progress made at this meeting
  Editorial clean-up, Scope,
  Terminology (e.g. RSU/UE for V2X)
  Numerology for V2X, security
  Addition/clarification of V2V/V2I/V2P Use cases: e.g. V2V pre-crash; V2I road safety, curve speeding; V2P pedestrian safety;
  Reply LS to RAN; Reply LS to ETSI ITS;
Work/Study Item Completion: 55%
Draft <TS/TR> 22.885 Completion: 55%
Controversial issues
  Terminology
  Numerology
S1-151439
Notes: 1

## Slide 4: FS_V2XLTE Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 9
Number of slots requested for next meeting
  sum of plenary and drafting slots: 10
  Guide: remove bullet above if WID is 100% complete
Number of Drafting session participants: 49
  Guide: remove bullet above if no Drafting sessions held
S1-151439
Notes: 1

## Slide 5: FS_V2XLTE Completion Date
Target completion date in WID: <12/2015> SP#70
    Guide: SA plenary meeting number and date (not SA1)
Is current completion date the same as above? <y>
Will target completion date be met? <y>
Expected date to send <TR/TS> to SA plenary:
  For information: SA1#71 (08/2015)
  For approval: SA1#72 (11/2015)
S1-151439
Notes: 1

## Slide 6: FS_V2XLTE Planning/Progress
Topics to focus on at SA1#71 (Aug 2015):
  Spectrum
  Use cases
  Consolidation of V2X potential requirements
    Possible completion of Consolidation of V2V PRs
  Clean-up
Planning for subsequent meetings
  SA1#72 (Nov 2015)
    Clean-up and completion
  SA1#73 (Feb 2016)
    <Short list of topics>
  <Until close of WI as defined in WID>
S1-151439
Notes: 1

## Slide 7: Work plan between meetings
  Guide: if WID is 100% complete or if SA1 agreed to stop the work, delete this slide
Email discussion
  Possible preparation for WID proposal
  <other topics/items to be covered>
  <e.g. introduction of new topics>
  <e.g. review of incoming LS>
  <e.g. planning next meeting>
  Tentative start date: <dd/mm/yyyy>
S1-151439
Notes: 1

## Slide 8: FS_V2XLTE Progress Estimate
Estimated percentage completion:
  SA1#71 (Aug 2015): <90%>
  SA1#72 (Nov 2015): <100%>
  <Until expected Completion Date>
S1-151439
Notes: 1

## Slide 9: FS_V2XLTE Agreed documents
List of agreed documents at this meeting:
S1-151439
S1-151331 | Rapporteur | Proposed editorial changes for Technical Report of FS_V2XLTE
S1-151332 | LG Electronics France | Scope section for Technical Report of FS_V2XLTE
S1-151585 | HUAWEI TECHNOLOGIES Co. Ltd. | V2V terminology update on V2X enabled, vehicular UE, device on vehicle
S1-151574 | HUAWEI TECHNOLOGIES Co. Ltd., Hisilicon | V2V value for High Speed Requirement instead of [TBD]
S1-151578 | HUAWEI TECHNOLOGIES Co. Ltd. | V2V clarification that communication range is distance between UEs
S1-151338 | HUAWEI TECHNOLOGIES Co. Ltd., Hisilicon | V2V loss requirement clarification
S1-151614 | HUAWEI TECHNOLOGIES Co. Ltd., Hisilicon | V2V service requirement values to replace the [TBD]
S1-151576 | Qualcomm Incorporated | Parameterisation for Forward Collision Warning
S1-151616 | Qualcomm Incorporated | Parameterisation for Control Loss Warning
S1-151617 | Qualcomm Incorporated | Parameterisation for CACC
S1-151580 | HUAWEI TECHNOLOGIES Co. Ltd., Ericsson | V2V: MNO role for in coverage V2V message transfer
S1-151594 | Ericsson LM | New use case for High-speed pre-crash warning
S1-151615 | LG Electronics, Inc. | V2X in areas outside network coverage
S1-151586 | Qualcomm Incorporated | Considerations on Security
S1-151587 | HUAWEI TECHNOLOGIES Co. Ltd. | V2V: MNO role for Security Operation of V2V Service
S1-151347 | LG Electronics, Inc. | V2X Road safety service by infrastructure
S1-151618 | HUAWEI TECHNOLOGIES Co. Ltd. | Clarification of V2I Service requirements
S1-151590 | Nokia Networks | V2I Traffic Flow Optimisation Use Case
S1-151591 | ETRI | V2I use case for curve speed warning
S1-151596 | LG Electronics France | V2P Use Case: Part 2 – Warning to pedestrian for Pedestrian Safety
S1-151608 | Qualcomm Incorporated | V2X Use Case: Vulnerable Road User (VRU) Safety
Notes: 1