## Slide 1: FS_MMTELin5G Status Update Study on evolution of IMS multimedia telephony service
Yan Di
China Mobile
FS_MMTELin5G Rapporteur
3GPP TSG-SA WG1 Meeting #91e
Electronic Meeting, 24 August - 2 September 2020
Notes: 1

## Slide 2: FS_MMTELin5G Progress
Progress made at this meeting
  Scope and one use case is agreed.
Work/Study Item Completion: 15%
Controversial issues
  Discussions on what is the suitable level of requirements.
Notes: 1

## Slide 3: FS_MMTELin5G Planning
Planning for subsequent meetings
  SA1#92e (11/2020): <40%>
    Definition of use cases and potential service requirements
  SA1#92ebis (01/2021): <70%>
    Additional use cases
    Gap analysis of existing reqs and potential reqs
  SA1#93e (03/2021): <100%>
    Consolidated requirements & add conclusion
Notes: 1

## Slide 4: Work plan between meetings
Email discussion
  Overview
  New use cases and enhancements to existing use cases.
  potential service requirements
  Oct 2020
Telephone conference
  Oct 2020 if needed
Notes: 1

## Slide 5: FS_MMTELin5G Completion Date
Current expected completion dates:
  For information: SA#91 (03/2021)
  For approval: SA#91 (03/2021)
Have these dates been changed at this meeting? y
  previous target completion dates:
    For information: SA#89 (09/2020)
    For approval: SA#90 (12/2020)
Notes: 1

## Slide 6: FS_MMTELin5G History
This WI has been approved at SA1#87
  Approved SID is in tdoc S1-192827
History of completion rates
  SA1#88-1 (11/2019): 10%
  SA1#91e-3 (09/2020): 15%
Notes: 1