## Slide 1: FS_VMR Status Update Study on vehicle-mounted relays
Francesco Pica
Qualcomm
FS_VMR Rapporteur
3GPP TSG-SA WG1 Meeting #94e
Electronic Meeting, 10 – 20 May 2021
Notes: 1

## Slide 2: FS_VMR Progress
Progress made at this meeting
  Agreed 6 new use cases, and (5) updates to existing sections
  Started discussion on consolidated requirements
Work/Study Item Completion: 85%
Controversial issues
  none
Notes: 1

## Slide 3: FS_VMR Planning
Planning for subsequent meetings
  SA1#95e (Aug 2021): 100%
    Update/finalize use cases and potential requirements
    Complete consolidation and conclusions
    TR clean-ups
Notes: 1

## Slide 4: Work plan between meetings
Email/Conference calls coordination
  Coordination among interested/contributing companies, about
    consolidated requirements
    planned inputs and clean-ups for next meeting
  To be moderated by the rapporteur
Notes: 1

## Slide 5: FS_VMR Completion Date
Current expected completion dates:
  For information: SA#92 (06/2021)
  For approval: SA#93 (09/2021)
Have these dates been changed at this meeting? n
Notes: 1

## Slide 6: FS_VMR History
This WI has been approved at SA#89e
  Approved SID is in tdoc SP-200798
History of completion rates
  S1-93e (Feb 2021): 60%
  S1-92e (Nov 2020): 35%
Notes: 1