## Slide 1: FS_DualSteer Status Update Study on Upper layer traffic steering, switching and split over dual 3GPP access
Francesco Pica
Qualcomm
FS_DualSteer Rapporteur
3GPP TSG-SA WG1 Meeting #98e
Electronic Meeting, May 9-19, 2022
Notes: 1

## Slide 2: FS_ DualSteer Progress
Progress made at this meeting
  Agreed SID
Study Item Completion: 0%
Controversial issues
  None
Notes: 1

## Slide 3: FS_ DualSteer Planning
Planning for subsequent meetings
  SA1#99e (Aug 2022): 30%
    Agree TR skeleton & scope
    Agree initial Use cases and potential requirements
  SA1#100e (Nov 2022): 60%
    Updated/Additional Use cases and potential requirements
  SA1#101e (Feb 2023): 85%
    Consolidation
    Send TR to SA for infomation
  SA1#102e (May 2023): 100%
    Conclusions, TR corrections/clean-up
    Send TR to SA for Approval
Notes: 1

## Slide 4: Work plan between meetings
Email coordination
  Coordination among interested/contributing companies, about planned inputs, use cases, etc.
  Before each SA1 meeting
  To be moderated by the rapporteur
Conference calls
  TBD (upon need)
Notes: 1

## Slide 5: FS_ DualSteer Completion Date
Current expected completion dates:
  For information: SA#99 (03/2023)
  For approval: SA#100 (06/2023)
Have these dates been changed at this meeting? n
  If yes, previous target completion dates:
    N/A
Notes: 1

## Slide 6: FS_ DualSteer History
This SI has been agreed at SA1#98e
  Agreed SID is in Tdoc S1-221231
History of completion rates
  N.A.
Notes: 1