## Slide 1: FS_EnergieServ Status Update Study on Energy Efficiency as service criteria
Xiaonan Shi
China Mobile
FS_EnergieServ Rapporteur
3GPP TSG-SA WG1 Meeting SA1#99-e
Electronic Meeting, 22 August – 1 September 2022
Notes: 1

## Slide 2: FS_EnergieServ Progress
Progress made at this meeting
  Agreed on skeleton, scope, overview, state of art (annex)
  Agreed on one use case
Work/Study Item Completion: 10%
Controversial issues
  Exact scope of use cases
Notes: 1

## Slide 3: FS_EnergieServ Planning
Planning for subsequent meetings
  SA1#100e (11/2022): 50%
    new use cases and potential requirements
    Consolidation and conclusions
  SA1#100_adhoc (01/2023): 80%
    new use cases and potential requirements
    Consolidation and conclusions
  SA1#101 (02/2023): 100%
    Consolidation and conclusions
    Final TR cleanup.
Notes: 1

## Slide 4: Work plan between meetings
Email discussion and pre-conf call
  New use cases
  Before next meeting, probably 10/2022
Notes: 1

## Slide 5: FS_TACMM Completion Date
Current expected completion dates:
  For approval: SA#99 (03/2023)
Have these dates been changed at this meeting? N
Notes: 1

## Slide 6: FS_TACMM History
This WI has been <agreed/approved/revised> at <SA1#98 >
  Agreed WID is in tdoc < S1-221232>
History of completion rates
  SA1#98e (05/2022): 0%
  SA1#99e (08/2022): 10%
Notes: 1