## Sheet1
| SA WG2 Meeting #114 | [12 empty] | S2-161728
23 – 26 Feb 2016, Sophia Antipolis, FR
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Discussion
Agenda Item: 7.2
Work Item / Release: All / Rel-13 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[8 empty] | Oct 15 |  | Nov 15 |  | Jan 16 |  | Feb 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Aug 16 |  | Oct 16 |  | Nov 16
| status (%) |  |  | Target |  | planned | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#113AH |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#116bis |  | SA2#117 |  | SA2#118 |  |  | percentage of planned resources
Work Item | 4/15 | 1/16 | 2/16 | date |  | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | 113AH | 114 | 115 | 116 | 116bis | 117 | 118
FS_AE_CIoT | 95 | 100 |  | Dec 15 |  | 5 | 5 | 4 | 4 | 1 | 1 | [16 empty] | 113AH: 100; percentage of planned resources 114: 100
CIOT_stage2 |  | 95 |  |  |  | 11 | 15 |  |  | 3 | 3 | 3 | 3 | 5 | 9 | [12 empty] | 113AH: 100; percentage of planned resources 114: 100
FS_eDECOR | 70 | 80 |  | Mar 16 |  | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | [11 empty] | 113AH: 75; percentage of planned resources 114: 100
FS_CUPS | 20 | 40 |  | Jun 16 |  | 9.3 | 6 | 1 | 2 | 2 | 2 | 2 | 2 |  |  | 2.3 |  | 2 | [9 empty] | 113AH: 53.7634; percentage of planned resources 114: 78.4946
FS_NextGen | 5 | 15 |  | Sep 16 | many | 55 | 15 |  |  | 1 | 2 | 4 | 4 | 9 | 9 | 6 |  | 6 |  | 6 |  | 9 |  | 6 |  | 8 |  | 113AH: 25.4545; percentage of planned resources 114: 36.3636
FS_V2XARC | 10 | 22 |  | Jun 16 | O9 V18 | 7.7 | 3 |  |  | 1 | 1 | 2 | 2 |  |  | 2.7 |  | 2 | [9 empty] | 113AH: 38.961; percentage of planned resources 114: 74.026
FS_GENCEF |  | 10 |  | Jun 16 | O3 V7 | 2.7 | 0.5 |  |  |  |  | 1 | 0.5 |  |  | 0.7 |  | 1 | [9 empty] | 113AH: 37.037; percentage of planned resources 114: 62.963
FS_IOPS_LB |  |  |  |  | O7 V5 | 5 | 0 | [8 empty] | 1 |  | 2 |  | 2 | [7 empty] | 113AH: 0; percentage of planned resources 114: 20
FS_AE_enTV |  |  |  |  | O4 V5 | 5 | 0 | [8 empty] | 1 |  | 2 |  | 2 | [7 empty] | 113AH: 0; percentage of planned resources 114: 20
NonIP_GPRS |  |  |  |  | O1 V8 | 0.3 | 0 | [8 empty] | 0.3 | [11 empty] | 113AH: 0; percentage of planned resources 114: 100
FS_V8 | 70 | 80 |  | Mar 16 |  | 7.3 | 6 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 1.3 | [11 empty] | 113AH: 82.1918; percentage of planned resources 114: 100
FS_SEW2 | 60 | 75 |  | Jun 16 |  | 9 | 4 | 2 | 1.5 | 2 | 1 | 1 | 1.5 |  |  | 2 |  | 2 | [9 empty] | 113AH: 55.5556; percentage of planned resources 114: 77.7778
FS_AULC | 40 | 70 |  | Jun 16 |  | 5.3 | 2.5 | 1 | 1 | 1 | 1 | 1 | 0.5 |  |  | 1.3 |  | 1 | [9 empty] | 113AH: 56.6038; percentage of planned resources 114: 81.1321
FS_SeDoC |  | 30 |  | Jun 16 | O5 V3 | 4 | 1 |  |  | 1 |  | 1 | 1 |  |  | 1 |  | 1 | [9 empty] | 113AH: 50; percentage of planned resources 114: 75
FS_SDCI | 10 | 40 |  | Jun 16 | O6 V7 | 4.3 | 2.5 |  |  | 1 | 1 | 1 | 1.5 |  |  | 1.3 |  | 1 | [9 empty] | 113AH: 46.5116; percentage of planned resources 114: 76.7442
EIEI |  | 20 |  | Jun 16 |  | 3 | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1 | [9 empty] | 113AH: 33.3333; percentage of planned resources 114: 66.6667
EWE | 45 | 60 |  | Jun 16 |  | 2.8 | 0.75 |  |  | 1 | 0.5 | 1 | 0.25 |  |  | 0.3 |  | 0.5 | [9 empty] | 113AH: 71.4286; percentage of planned resources 114: 82.1429
FS_RobVoLTE |  | 20 |  | Jun 16 | O6 V8 | 3 | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1 | [9 empty] | 113AH: 33.3333; percentage of planned resources 114: 66.6667
Maint 5.1 | [6 empty] | 9 | 2 | 3 | 2 | 3 | 3 | 3 |  |  | 4.7 |  | 4 |  | 3
Maint 5.2 | [6 empty] | 1 |  |  |  |  | 1 | 1 |  |  | 1.3 |  | 1 |  | 1
Maint 5.3 | [6 empty] | 9.5 | 2 | 3.5 | 2 | 3.5 | 3 | 2.5 |  |  | 2.7 |  | 2 |  | 2
Maint 5.4 | [6 empty] | 2 | 1 | 0.5 | 1 | 1 | 1 | 0.5 |  |  | 1 |  | 0.5 |  | 0.5
TEI14 3GPP acc | [6 empty] | 1 | 1 | 1 | [8 empty] | 1
TEI14 PCC/QoS | [6 empty] | 0.5 | 0.5 | 0.5
TEI14 IMS/rel. | [6 empty] | 0 | 0.5 | [9 empty] | 1
sum | [7 empty] | 18 | 22 | 22 | 23 | 30 | 28.25 | 14 | 18 | 33.9 | 0 | 32 | 0 | 16.5 | 0 | 9 | 0 | 0 | 0 | 8 | 0