## Sheet1
| SA WG2 Meeting #136 | [13 empty] | S2-1912486
Nov 18 - 22, 2019, Reno, NV, USA
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Endorsement
Agenda Item: 9.2
Work Item / Release: All / Rel-15 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[6 empty] | Target | Total TU | Total TU | Oct, 19 | Oct, 19 | Nov, 19 | Nov, 19 | Jan, 20 | Feb, 20 | Apr, 20 | May, 20 | Aug, 20
[6 empty] | Completion | requested | updated | #135 | #135 | #136 | #136 | #136AH | #137 | #138 | #139 | #140
|  | Title | Rapporteur | WID | Work Tasks | date for Study | SA2#134 | SA2#135/136 | Plan | Actual | Plan | Actual | Plan | Plan | Plan | Plan | Plan
Rel-15/Rel-16 maintenance
| Maint 5.1 | [7 empty] | 1 | 1.8 | 1 | 1.3 | 1 | 1 | 1 | 1 | 1
| Maint 5.2 | [7 empty] | 1 | 0 | 1 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Maint 5.3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Maint 5.4 | [7 empty] | 1 | 0.3 | 1 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Maint 5GS_ph1 | [7 empty] | 5 | 8.9 | 5 | 7.7 | 5 | 5 | 3 | 3 | 2
| Maint other (5G_URLLC, eNS, RACS, eIMS5G, UDICoM, ETSUN, 5G_SRVCC) | [7 empty] | 3 | 4.8 | 3 | 5.5 | 3 | 3 | 3 | 2 | 2
| Sum | [7 empty] | 11 | 15.8 | 11 | 14.8 | 10 | 10 | 8 | 7 | 6
Rel-16 maintenance
| eV2XARC | [7 empty] | 2 | 2 | 2 | 3 | 2 | 2
| ATSSS | [7 empty] | 1.5 | 2.3 | 1.5 | 2.3 | 2 | 2
| 5WWC | [7 empty] | 1.5 | 2 | 1.5 | 1 | 1 | 1
| 5G_CIoT | [7 empty] | 2 | 1.8 | 2 | 1.8 | 1.5 | 1
| Vertical_LAN | [7 empty] | 2 | 2.6 | 2 | 3.6 | 2 | 2
| eNA | [7 empty] | 2 | 2 | 1.5 | 2.5 | 1.5 | 1.5
| eLCS | [7 empty] | 1 | 1 | 1 | 1 | 0.5 | 0.5
| eSBA | [7 empty] | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.5
| Rel-16 Maint (combined) | [13 empty] | 8 | 6 | 4
| Sum | [7 empty] | 13.5 | 15.2 | 13 | 16.7 | 11.5 | 10.5 | 8 | 6 | 4
Rel-16 Alignment
| IAB | [7 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
| MT EDT | [7 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
| Sum | [7 empty] | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Total (Maintenance) | [8 empty] | 25.5 | 32 | 25 | 32.5 | 21.5 | 20.5 | 16 | 13 | 10
Buffer (TEI17, overflow, other)
| Buffer | [7 empty] | 3 | 0 | 3 | 0 | 3 | 3 | 3 | 3 | 3
Total (Maintenance + Buffer) | [8 empty] | 28.5 | 32 | 28 | 32.5 | 24.5 | 23.5 | 19 | 16 | 13
Rel- 17 Study/Work items ("In" items, See SP-190949)
| FS_5GSAT_ARCH | Study on architecture aspects for using satellite access in 5G | Cyril Michel (Thales) | SP-181253 | S2-1912780 | 2019-12-01 | 2 + 2 | 2 + 4 | 1 | 1.5 | 1 | 1.7
| FS_eNA_ph2 | Study on Enablers for Network Automation for 5G - phase 2 | Xiaobo Wu (Huawei), Aihua Li (China Mobile) | SP-190557 | S2-1910845 | 2020-03-01 | 14 + 9 | 15.2 + 9.3 | 1 | 1 | 1 | 1
| FS_eNPN | Study on enhanced support of Non-Public Networks | Peter Hedman (Ericsson) | SP-191100 | S2-1912752 | 2020-06-01 | 7 + 3.5 | 13 + 6 | 1 | 1 | 1 | 1
| FS_MUSIM | Study on system enablers for multi-USIM devices | Sašo Stojanovski (Intel) | SP-190248 | S2-1912751 | 2020-03-01 | 5 + 2 | 7 + 2 | 1 | 1 | 1 | 1
| FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | Hui Ni (Huawei), Changhong Shan (Intel) | SP-190185 | S2-1910846 | 2020-03-01 | 10 + 9 | 10 + 7 | 1 | 1 | 1 | 1
| FS_5G_ProSe | Study on system enhancement for Proximity based Services in 5GS | Qiang Deng (CATT), Jianhua Liu (OPPO) | SP-191096 | S2-1910835 | 2020-06-01 | 20 + 12 | 17 + 8.5 | 2 | 2 | 1 | 2
| FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | Dario Serafino Tonesi (Huawei) | SP-190442 | S2-1910844 | 2020-06-01 | 16 + 10 | 20 + 12 | 1 | 1.3 | 1 | 1.3
| FS_eNS_ph2 | Study on Enhancement of Network Slicing Phase 2 | Tricci So (ZTE) | SP-190931 | S2-1910831 | 2020-03-01 | 6 + 3 | 6 + 3 | 1 | 1 | 1 | 1
| FS_eV2XARC_ph2 | Study on architecture enhancements for 3GPP support of advanced V2X services - Phase 2 | LaeYoung Kim (LG Electronics) | SP-190631 | S2-1910833 | 2020-06-01 | 4 + 2 | 4 + 2 | 0 | 0 | 0 | 0
| FS_IIoT | Study on enhanced support of Industrial IoT - TSC/URLLC enhancements | Devaki Chandramouli (Nokia) | SP-191098 | S2-1912750 | 2020-03-01 | 6 + 3 | 8 + 5.5 | 1 | 1 | 1 | 1
| 5G_AIS | 5G System Enhancement for Advanced Interactive Services | Lei Yixue (Tencent) | SP-190564 | S2-1910832 | 2020-03-01 | 2 | 2 | 0 | 0 | 0 | 0
| Sum | [7 empty] | 10 | 10.8 | 9 | 11
Rel- 17 Study/Work items ("In*" items, See SP-190949)
| FS_5GLAN enh | Study on enhancement of support for 5G LAN-type service | Runze Zhou (Huawei) | SP-191097 | S2-1912482 | 2020-03-01 | 7 + 7 | 8.5 + 6.5 | 0 |  | 0
| FS_eATSSS | Study Extended Access Traffic Steering, Switch and Splitting support in the 5G system architecture | Tricci So (ZTE) | SP-190558 | S2-1910841 | 2020-06-01 | 9 + 6 | 12.5 + 6 | 0 |  | 0
| FS_eLCS_ph2 | Study on Enhancement to the 5GC LoCation Services - Phase 2 | Ming Ai (CATT) | SP-190452 | S2-1910834 | 2020-03-01 | 8 + 6 | 7.5 + 4.5 | 0 |  | 0
| FS_5WWC_enh | Study on enhancement of support for 5WWC | Huan Li (Huawei) | SP-190562 | S2-1910842 | 2020-06-01 | 10 + 8 | 10 + 7 | 0 |  | 0
| FS_ID_UAS-SA2 | Study on supporting UAS Connectivity, Identification, and Tracking | Stefano Faccin (Qualcomm) | SP-181114 | S2-1910540 | 2020-03-01 | 8 + 6 | 6 + 4.5 | 0 |  | 0
| FS_UPCAS | Study on UPF enhancement for control and SBA | Dan Wang (China Mobile) | SP-190187 | S2-1910838 | 2020-03-01 | 10 + 7 | 9 + 5 | 0 |  | 0
| FS_MPS | Study on Multimedia Priority Service (MPS) Phase 2, Stage 2 | Don Lukacs (Perspecta Labs) | SP-190629 | S2-1910840 | 2020-06-01 | 4 + 2 | 2 + 1 | 0 |  | 0
| Sum | [7 empty] | 0 |  | 0
NOTE1: Planning Is based on max 38 TUs (including 3TU as buffer) per meeting
NOTE2: On Rel-17 Study/Work items tables above, black numbers denotes TU estimates for the study phase while red numbers denotes TU estimates for the normative work.
Note on E58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New WID approved in S2-1912749
Note on I58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WT shows 3.3 + 4 TUs. 3.3 TUs take into consideration 2 + additional TUs allocated during SA2#135 and SA2#136 meetings.
Note on E60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: revised WID in S2-1912754/SP-191100 for Approval at SA#86
Note on G61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mar-2020 completion is not feasible
Note on G62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mar-2020 completion is not feasible
Note on E63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: revised WID in S2-1912753/SP-191096 for Approval at SA#86
Note on E67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: revised WID in S2-1912756/SP-191098 for Approval at SA#86
Note on G67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mar-2020 completion is not feasible
Note on E72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: revised WID in S2-1910755/SP-191097 for Approval at SA#86