## Slide 1: FS_eNA_ph2 Status Report
Xiaobo Wu (Huawei), Aihua Li (China Mobile)

## Slide 2: FS_eNA_ph2 status at SA#90-e
Progress since SA#89E:
  Agreed normative WID
  TR 23.700-91 submitted to SA#90E for approval
  It is 97% complete and the remaining 3% are to take into account feedback from other WGs.
  43 (SA2#141E) / 31 (SA2#142E) contributions agreed to update current solutions; 29 (SA2#141E)/30(SA2#142E) contributions are agreed to evaluate or conclude the Key Issues.
  18 KIs potential for R17 (21 KIs in total captured in TR with 3 KIs not to be progressed in R17)
    Evaluation agreed for 18 KIs;
    Conclusion agreed for 17 KIs.
RAN impacts or dependencies:
  None
Next steps:
  Start normative work as per agreed WID.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA_Ph2 | Study on Enablers for Network Automation for 5G - phase 2 | 70 > 97% | TBD | SP-200098

## Slide 3: FS_eNA_ph2 status after SA2#142E (1/5)
  General
  FS_eNA_ph2 TR 23.700-91 is available here.
  18 KIs potential for R17 (21 KIs in total captured in TR with 3 KIs not to be progressed in R17) and 77 solutions in the TR.
  Key Issue #1: Logical decomposition of NWDAF and possible interactions between logical functions
  9 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.
  Key Issue #2: Multiple NWDAF instances
  27 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.
  Key Issue #3: Mapping of NWDAF use cases to NFs and identify actions that could be taken based on NWDAF analytics and predictions (NOT to be progressed in R17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA_Ph2 | Study on Enablers for Network Automation for 5G - phase 2 | 70 > 97% | TBD | SP-200098

## Slide 4: FS_eNA_ph2 status after SA2#142E (2/5)
  Key Issue #4: Remaining aspects on how to ensure that slice SLA is guaranteed
  1 solution is documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work. Alignment with SA5, an LS was sent to SA5 in SA2#141e.
  Key Issue #5: New types of outputs provided by NWDAF (NOT to be progressed in R17)
  Key Issue #6: Study possible mechanisms for improved correctness of NWDAF analytics (NOT to be progressed in R17)
  Key Issue #7: Adding Application attributes and KPIs as the Input data in some services described in TS 23.288 [5]
  1 solution is documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.
  Key Issue #8: UE data as an input for analytics generation
  7 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work. Alignment with SA4 and SA3, an LS was sent to SA4 and SA3 in SA2#140e.
  Key Issue #9: Dispersion analytic output provided by NWDAF
  2 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.
  Key Issue #10: NWDAF Assisted UP Optimization
  3 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.

## Slide 5: FS_eNA_ph2 status after SA2#142E (3/5)
  Key Issue #11: Increasing efficiency of data collection
  19 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work. Alignment with SA3, an LS was sent to SA3 in SA2#141e.
  Key issue #12: NWDAF-assisted RFSP policy
  5 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work. Alignment with SA5 and, an LS sent to SA5 in SA2#142e.
  Key Issue #13: Triggering conditions for analytics
  6 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.
  Key Issue #14: NWDAF-assisted application detection
  1 solution is documented for this key issue.
  Next steps: No normative work in R17
  Key Issue #15: User consent for UE data collection/analysis
  2 existing solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work. Alignment with SA3, an LS was sent to SA3 on user consent in SA2#139e and SA2#142e.
  Key Issue #16: UP optimization for edge computing
  6 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.
  Key Issue #17: Definition of accuracy levels
  1 solution is documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.

## Slide 6: FS_eNA_ph2 status after SA2#142E (4/5)
  Key Issue #18: Enhancement for real-time communication with NWDAF
  3 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.
  Key Issue #19: Trained data model sharing between multiple NWDAF instances
  3 solutions are documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: Normative work.
  Key Issue #20: NWDAF assisting in detecting anomaly events for the user plane
  No solutions are captured for this key issue and it is concluded that no normative work has been identified for Rel-17.
  Next steps: None.
  Key Issue #21: NWDAF assisting in user plane performance
  1 solution is documented for this key issue. Final evaluation and conclusion agreed.
  Next steps: None as no normative work is intended in R17.

## Slide 7: FS_eNA_ph2 status after SA2#142E (5/5)
  RAN impacts and dependencies:
  None identified so far.
Contentious Issue:
  None.
Dependencies with other WGs:
  KI#15 LS send to SA3 to request feedback on solutions.
  KI#8 requires work in SA4 for the end to end solution, but there is no need to wait for the SA4 work before it starts the normative work for KI#8.
  KI#4 requires SA5 to define some new procedures for OAM to provide slice information, but there is no need to wait for the SA5 work before it starts the normative work for KI#4.
Focus for the Next Meeting:
  SA#90E: Submit TR 23.700-91 to SA#90 plenary for approval and agree a WID.
  SA2#143E: Start normative work.
    Risk:
  None.

## Slide 8: backup