## Slide 1: eEdge_5GC Status Report
Hui Ni
Huawei

## Slide 2: eEdge_5GC status after SA2#147e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | 95%-> 96% | Sep, 2021 | SP-201134
General
  6 CRs for TS 23.548 and 10 CRs for TS 23.501/23.502/23.503 are approved.
  3 CRs for TS 23.548 are endorsed as baseline for further discussion.
Topic 1: (Re-)Discovery of Edge Application Server
  The contentious issue is discussed, and a CR is endorsed as baseline for further revision to resolve the issue.
  The following solutions are updated:
    For Session breakout case: Support of node level EAS deployment info, corrections on EASDF based EAS discovery procedure.
    For Distributed anchor case: Dynamic PSA Distribution.
    AF guidance to URSP: Correction of UE Policies delivery notification.
Topic 2: Edge Relocation
  The following solutions are updated:
    Support of transferring AF Coordination Information between SMFs.
    Topic 3: Network Exposure to Edge Application Server
  Clarify the local AF subscription for the QoS Monitoring during UE mobility.
Topic 4: Support of 3GPP Application Layer Architecture
  Corrections on provisioning of ECS Address Configuration .
Topic 5: DNAI based (I-)SMF selection
  Corrections on DNAI based I-SMF selection.

## Slide 3: eEdge_5GC status after SA2#147e (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  How to guarantee that the UE uses the DNS setting provided by operator for the subsequent DNS Query.
Focus for the Next Meeting (SA2#148e):
  TS Maintenance.
  Resolve the contentious issue by taking S2-2108177 as baseline.
Overall Plan:
  TS Maintenance.
  Resolve the contentious issue by taking S2-2108177 as baseline.

## Slide 4: backup

## Slide 5: eEdge_5GC status after SA2#143e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | 0%-> 35% | Jun, 2021 | SP-201107
General
  First meeting for eEdge_5GC WI. TS 23.548 v0.1.0 is available at link.
  15 pCRs for TS 23.548 (incl. TS skeleton) and 13 CRs for TS 23.501/23.502/23.503 are approved. Most of concluded solutions in study phase are agreed with identified FFS.
  2 LS replies are sent out to GSMA and SA6.
Topic 1: (Re-)Discovery of Edge Application Server
  The following solutions are approved:
    EAS discovery procedures for Distributed Anchor and Session breakout; EAS re-discovery for Session Breakout; UE Considerations for EAS rediscovery; Application layer based EAS (re-)direction; EAS discovery using 3rd party mechanisms
Topic 2: Edge Relocation
  The following solutions are approved:
    Target PSA buffering; Edge Relocation considering User Plane latency; EAS IP replacement.
Topic 3: Network Exposure to Edge Application Server
  The following solutions are approved:
    Network exposure via local NEF; Parameter for local NEF selection;
Topic 4: Support of 3GPP Application Layer Architecture
  pCR/CRs for ECS Address Provisioning are approved.
Topic 5: DNAI based SMF/I-SMF selection
  CRs for SMF/I-SMF selections are approved.

## Slide 6: eEdge_5GC status after SA2#143e (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  Whether/how to address the issue on “cooperation among the applications, the 5GC and the UE to ensure no conflict on selecting the appropriate DNS server”.
Focus for the Next Meeting (SA2#144e):
  Continue to discuss the postponed solutions.
  Resolve the open issues.
Overall Plan:
  Achieve 60% completion after SA2#144e.

## Slide 7: eEdge_5GC status after SA2#144e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | 35%-> 60% | Jun, 2021 | SP-201107
General
  TS 23.548 v0.2.0 is available at link.
  26 pCRs for TS 23.548 and 14 CRs for TS 23.501/23.502/23.503 are approved.
  General aspects for EC in both 23.501 and 23.548 are updated/addressed.
Topic 1: (Re-)Discovery of Edge Application Server
  pCRs/CRs for the following solutions are approved:
    New: EASDF discovery and selection, EASDF functional description, EASDF services, EAS deployment information from AF; EAS Re-discovery Procedure at Edge Relocation, EAS Discovery with dynamic PSA Distribution(sol#12).
    Update: EAS discovery procedure for session breakout, EAS rediscovery for session breakout, UE Considerations for EAS (re)Discovery, AF guidance to PCF determination of proper URSP rules.
Topic 2: Edge Relocation
  pCRs/CRs for the following solutions are approved:
    New: General part for Edge relocation, Edge Relocation with Multiple AFs, EAS Relocation on Simultaneous connectivity over source and target PSA .
    Update: Target PSA buffering, Edge Relocation considering User Plane latency, EAS IP replacement.
    Topic 3: Network Exposure to Edge Application Server
  pCRs/CRs for the following solutions are approved:
    Update: Network exposure via local NEF, local NEF selection.
Topic 4: Support of 3GPP Application Layer Architecture
  pCR/CRs for updating ECS Address Provisioning are approved.

## Slide 8: eEdge_5GC status after SA2#144e (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  Issues related to “whether/how to guarantee that the UE uses the EASDF's IP address”.
  Issue related to “whether specify Local UPF-Local NEF interface”.
Focus for the Next Meeting (SA2#145e):
  Continue to discuss the postponed solutions.
  Resolve the open issues.
Overall Plan:
  Achieve 80% completion after SA2 #145e.
  Send TS 23.548 to SA#92-e for information/approval after SA2 #145e.
Risk:
  Depending on the progress on contentious issues, there may be a risk that the TS cannot be ready for approval before SA #92-e.

## Slide 9
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 100% -> 100% | Dec, 20 | SP-200093
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | 35%-> 75% | Sep, 2021 | SP-201134
Progress since SA#91-e:
  TS 23.548 v0.3.0 is sent to SA #92-e for information.
  64 pCRs for TS 23.548 and 33 CRs for TS 23.501/23.502/23.503 were approved. All solutions concluded in study phase were addressed in the TS.
  1 LS response was sent to SA.
RAN impacts and dependencies:
  None identified
Next steps:
  Finalize normative work if WI exception is approved.
2.4) Rel-17 Study/Work (2/16)

## Slide 10: eEdge_5GC status after SA2#145e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | 60%-> 75% | Sep, 2021 | SP-201134
General
  TS 23.548 v0.3.0 (available at link) is sent to SA #92E for information.
  38 pCRs for TS 23.548 and 29 CRs for TS 23.501/23.502/23.503 are approved.
  LS reply to SA on GSMA 3GPP Edge Computing coordination is sent out.
Topic 1: (Re-)Discovery of Edge Application Server
  The following solutions are updated:
    For Session breakout case: EAS discovery procedure, EAS Re-discovery Procedure at Edge Relocation, EPS Interworking Considerations.
    For Distributed anchor case: EAS Re-discovery Procedure at Edge Relocation, EAS Discovery with Dynamic PSA Distribution.
    AF guidance to URSP: Support for Service Specific Authorization, Notification to AF on the outcome.
    Added considerations for split-UE case.
Topic 2: Edge Relocation
  The following solutions are updated:
    Target PSA buffering, Edge Relocation considering User Plane latency, EAS IP replacement, AF relocation.
    Topic 3: Network Exposure to Edge Application Server
  UPF service is added. Local NEF selection is updated.
Topic 4: Support of 3GPP Application Layer Architecture
  Procedure for ECS Address Provisioning is updated. Interworking scenario is addressed.
Topic 5: DNAI based (I-)SMF selection
  SMF/I-SMF selection procedures are updated.

## Slide 11: eEdge_5GC status after SA2#145e (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  How to handle DNS messages in case UE does not use the network DNS resolver sent by the SMF in EASDF based EAS discovery procedure.
Focus for the Next Meeting (SA2#146e):
  Resolve the open issues listed in WI exception.
Overall Plan:
  Finalize normative work after SA2 #146E.
  Send TS 23.548 to SA#93-e for approval.

## Slide 12
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 100% -> 100% | Dec, 20 | SP-200093
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | 75%-> 95% | Sep, 2021 | SP-201134
Progress since SA#92-e:
  TS 23.548 v1.1.0 is sent to SA #93-e for approval.
  28 pCRs for TS 23.548 and 21 CRs for TS 23.501/23.502/23.503 were approved.
  All exceptions were resolved except for a contentious issue listed in the TS cover page.
RAN impacts and dependencies:
  None identified
Next steps:
  TS Maintenance.
  Resolve the contentious issue based on SA plenary outputs.
2.4) Rel-17 Study/Work (2/16)

## Slide 13: eEdge_5GC status after SA2#146e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | 75%-> 95% | Sep, 2021 | SP-201134
General
  TS 23.548 v1.1.0 (available at link) is sent to SA #93E for approval.
  28 pCRs for TS 23.548 and 21 CRs for TS 23.501/23.502/23.503 are approved.
  Supporting for SNPN is clarified.
Topic 1: (Re-)Discovery of Edge Application Server
  The following solutions are updated:
    For Session breakout case: Support of node level EAS deployment info, EASDF registration, Multiple candidate DNAI issues, EAS (Re-)discovery.
    For Distributed anchor case: EAS Re-discovery, Dynamic PSA distribution.
    AF guidance to URSP: Support of group of UE, Service specific authorization.
Topic 2: Edge Relocation
  The following solutions are updated:
    Simultaneous connectivity at Edge relocation, Edge relocation considering User Plane latency, AF triggered EAS relocation, Edge relocation Involving AF change
    Topic 3: Network Exposure to Edge Application Server
  NEF related services and registration are updated.
Topic 4: Support of 3GPP Application Layer Architecture
  Several Editor’s notes for support ECS address provisioning are resolved.
Topic 5: DNAI based (I-)SMF selection
  I-SMF removal procedure is added.

## Slide 14: eEdge_5GC status after SA2#146e (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  How to guarantee that the UE uses the DNS setting provided by operator for the subsequent DNS Query.
Focus for the Next Meeting (SA2#146e):
  TS Maintenance.
  Resolve the contentious issue based on SA plenary outputs.
Overall Plan:
  TS Maintenance.
  Resolve the contentious issue based on SA plenary outputs.