## Slide 1: FS_eUEPO Status Report
Intel (Rapporteur)

## Slide 2: FS_eUEPO status after SA#96
WI Code | Work Item Title | WP | Target Date | WID#
FS_eUEPO | Study on enhancement of 5G UE Policy | 70% -> 80% | Dec. 2022 | SP-211649
General
  The latest TR 23.700-85 v0.4.0 generated based on agreed contributions and sent to SA for information.
  WID on eUEPO is approved by SA2. Objectives for KI#3 and #4 are included.
  46 papers were submitted including one LS OUT, 19 papers were approved, 9 papers was merged, 3 paper was noted, 0 paper was postponed, 15 papers were not handled.
  LS OUT to SA3 is approved in S2-2207501.
  Contentious Issue:
    KI #1 conclusion on whether and how to provide VPLMN ID to UE by H-PCF.
    KI #2 conclusion.
RAN impacts and dependencies:
  No.
Next steps:
  Resolve open issues in the conclusion for KI#1 and #3, reach conclusion for KI #2.

## Slide 3: FS_eUEPO status at SA2#152E
WI Code | Work Item Title | WP | Target Date | WID#
FS_eUEPO | Study on enhancement of 5G UE Policy | 70% -> 80% | Dec. 2022 | SP-211649
General
  The latest TR 23.700-85 is available here and sent to TSG SA for Information.
  Total TUs requested for Study Phase is 4.25 TUs, and 0.75 TUs are left.
  Latest SID is in S2-2207682, latest WID is in S2-2207881.
  46 papers were submitted including one LS OUT, 19 papers were approved, 9 papers was merged, 3 paper was noted, 0 paper was postponed, 15 papers were not handled.
KI#1(URSP in VPLMN):
  3 existing solutions were updated, one evaluation and conclusion paper was approved in S2-2207500.
KI#2(5GC awareness of URSP enforcement):
  6 existing solutions were updated, no conclusion paper was approved.
KI#3(Provision consistent URSP to UE across 5GS and EPS):
  3 existing solutions were updated, one evaluation and conclusion paper was approved in S2-2207883.
KI#4(Support standardized and operator-specific traffic categories in URSP):
  Key Issue is updated with including standardized Traffic Categories based on GSMA requirements.
  3 existing solutions were updated, one evaluation and conclusion paper was approved in S2-2207504.

## Slide 4: FS_eUEPO status at SA2#152E (2/2)
Contentious Issue:
  KI #1 conclusion on whether and how to provide VPLMN ID to UE by H-PCF.
  KI #2 conclusion.
Focus for the Next Meeting (SA2#153E):
  Resolve open issues in the conclusion for KI#1 and #3, reach conclusion for KI #2.
  Approve LS OUT to GSMA on KI #4.
  TR approval
  NOTE: No new solution will be handled at next meeting.

## Slide 5: Rel-18 FS_eUEPO Overall Work Plan
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
  Overall Work Plan
  SA2#149e, 0.5 TU assigned, 15 documents in maximum:
    TR Skeleton, TR Scope, Architectural Assumption, Key Issues.
  SA2#150e, 1 TU assigned, 30 documents in maximum:
    Key issue update and new solutions. Last e-meeting for new Key Issue.
  SA2#151e, 1 TU assigned, 30 documents in maximum:
    Stabilize solution. Last e-meeting for new solution. Potential TR for information.
  SA2#152(e), 1 TU assigned, 30 documents in maximum:
    Stabilize solution and conclusion, TR for information and potential TR for approval, potential WID discussion and approval.
  SA2#153(e), 0.75 TU assigned, 23 documents in maximum:
    Potential update on solution and conclusions, WID approval and update.
*The Work Plan will be updated and reflected in status report after each meeting.
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0.5 | 0.5 | 0.5 | 5.75