## Slide 1: FS_5GSATB Status Report
CATT

## Slide 2: FS_5GSATB status after SA2#151E (1/2)
General
  TR 23.700-27 v.0.4.0 is created based on approved contributions.
  10 contributions agreed (including 7 solution updates and 3 evaluation plus conclusion).
  2.5TU used and 1.0 TU left for the Study Phase.
KI#1: PCC/QoS control enhancement considering dynamic satellite backhaul
  4 solution updates are approved
  1 evaluation plus conclusion is approved
  Next steps: Continue to evaluate solutions, complete the final conclusion and start the normative work per conclusion. .
  KI#2: Support of Satellite Edge Computing via UPF on board
  2 solution updates are approved
  1 evaluation plus conclusion is approved
  Next steps: Complete the final conclusion and start the normative work per conclusion.
  KI#3: Support of Local Data Switching via UPF on-board
  1 solution updates are approved
  1 evaluation plus conclusion is approved
  Next steps: Complete the final conclusion and start the normative work per conclusion.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSATB | Study on Support of Satellite Backhauling in 5GS | 60% > 80% | October, 22 | SP-211639

## Slide 3
  RAN impacts and dependencies:
  None
Focus for the Next Meeting (SA2#152):
  Continue the solution evaluation
  Complete the final conclusion
  Update the WID based on further conclusion
FS_5GSATB status after SA2#151E (2/2)

## Slide 4: FS_5GSATB status at SA#97
  Progress since SA#96-e
  TR 23.700-27 v.0.4.0 is created.
  7 solution updates and 3 per KI evaluation and conclusion are agreed.
  TR was sent for information.
  2.5TU used and 1.0 TU left for the Study Phase.
  RAN impacts and dependencies:
  None.
Next steps:
  Complete the final conclusion and start the normative work per conclusion.
  Send TR for Approval.
  Approval of 5GSATB WID.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSATB | Study on Support of Satellite Backhauling in 5GS | 60% > 80% | October, 22 | SP-211639

## Slide 5
Overall Plan:
  SA2#149: discuss TR skeleton, TR scope, assumptions and Key Issues, start the solution discussion.
  SA2#150: last meeting for Key Issues, continue the solution discussions .
  SA2#151: continue the solution discussions.
  SA2#152: last meeting for solutions, start the solution evaluation, and send the TR for information. Draft the WID (for concluded KIs)
  SA2#153: complete the evaluation and conclusion. Revise and Approve the WID.
  SA2#154 and #154AH: normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Norm TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 5
Work Plan