## Slide 1: FS_5MBS_Ph2 status report
Li, Meng
Huawei

## Slide 2: FS_5MBS_Ph2 status after SA2#151E (1/2)
General
  TR 23.700-47 v0.4.0 is available.
  Total TUs requested for Study phase in 2022 is 7.5, 6 TU used until SA2#152E and 1.5 TUs remaining.
  16 solution updates and 5 new solutions agreed for the existing KIs.
  One LS has been sent to RAN WG to seek their feedback for completing the final conclusion.
  TR was sent for information.
Key Issue 1 (RRC Inactive for Multicast)
  2 new solutions were included in the TR and 7 solutions were updated.
  Evaluation was added, and partial conclusion was agreed.
  Next step: Wait the RAN feedback to complete the final conclusion, and start the normative work per conclusion.
Key Issue 2 (MOCN for broadcast)
  1 new solutions was captured and 5 updates were agreed.
  Evaluation was added, Partial conclusion was agreed.
  Next step: Wait the RAN feedback to complete the final conclusion, and start the normative work per conclusion.
Key Issues 3 (AF triggered MBS session management)
  1 new solution was agreed.
  Evaluation was added and the initial concolusoin has been proposed.
  Next step : Complete the final conclusion and start the normative work per conclusion.
Key Issue 4 (Group message delivery)
  2 solutions were updated.
  Evaluation was added, Partial conclusion was agreed.
  Next step : Complete the final conclusion and start the normative work per conclusion.
Key Issues 5 (Power Saving mechanisms)
  1 solution update was agreed.
  Evaluation was added.
  Next step : Complete the final conclusion and start the normative work per conclusion.
Key Issues 6 (Public safety)
  1 new solution was captured and 1 solution was udpated.
  Evaluation was added.
  Next step : Complete the final conclusion and start the normative work per conclusion.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 55% → 75% | Dec 2022 | SP-220072

## Slide 3: FS_5MBS_Ph2 status after SA2#152E (2/2)
  RAN impacts and dependencies:
  3 KIs (KI#1, KI#2 and KI#6) have RAN WGs coordination requirement as per agreed pCR. The on time RAN feedback is necessary for completing final conclusion.
  It is requested related RAN WG prioritize the related LS handling.
Other WG dependencies
  KIs have potential SA6/SA4/SA3 coordination requirements accordingly as per agreed pCR.
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#153E):
  Resolve the ENs of the solutions.
  Complete the evaluation and final conclusion for the KIs with no RAN dependency, .
  TR to be sent for approval.
  Approval of MBS_Ph2 WID
Overall Plan: (study phase)
  SA2#149e, Feb (1TU): Focus on KIs, solutions are allowed. Agree the skeleton/scope/architectural assumption.
  SA2#150e, Apr (1TU): Focus on Solutions and complete all KIs. Potential updates/new KIs. Last meeting for KI proposal/modification.
  SA2#151e, May (2TUs): Solutions
  SA2#152, Aug (2TUs): Solutions, evaluations, conclusions
  SA2#153, Oct (1TU): Solution updates (No new Solutions), evaluations, conclusions: Approval of MBS_Ph2 WID.
  SA2#154, Nov (0.5 TU): final conclusions: Adjustment/issues depends on RAN progress
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 12

## Slide 4: FS_5MBS_Ph2 Status at SA#97e
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 55% → 75% | Dec 2022 | SP-220072
  Progress since SA#96-e:
  Total TUs requested for Study phase in 2022 is 7.5, 6 TU used until SA2#152E and 1.5 TUs remaining.
  1 LS was sent to RAN WGs to seek RAN WG feedback.
  5 new solutions were approved since SA#96e, and totally 31 solutions have been approved for all KIs.
  Evaluation of all the KIs were added, and 3 KIs have received partial conclusions.
  TR was sent for information.
  RAN impacts and dependencies:
  3 KIs (KI#1, KI#2 and KI#6) have RAN WGs coordination requirement as per agreed pCR. The on time RAN feedback is necessary for completing final conclusion.
  It is requested related RAN WG prioritize the related LS handling.
Other WG dependencies
  KIs have potential SA6 (KI#6)/SA4 (KI#3-5)/SA3 (KI#2) coordination requirements accordingly as per agreed pCR.
Contentious Issue:
  None.
Next steps:
  Resolve the ENs of the solutions.
  Complete the evaluation and final conclusion for the KIs.
  TR to be sent for approval.
  Approval of MBS_Ph2 WID