## Slide 1: SA2 Work Planning
Andy Bennett
SA2 Chair
SA WG2 Meeting #158 S2-2309206
August 21 – 25, 2023

## Slide 2: Contents
Release timeline
Meeting dates – summary
SA2#159 Meeting dates and agenda
SA2#160 Meeting dates and agenda
Overall planning for Rel-19
TEI-19 planning

## Slide 3: Rel-19 timelines
TSG#101
Note: All starting dates are indicative
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2026
RAN Rel-19 workshop
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…)
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
SA Rel-19
Workshop
TSG#100
June
2023
100%
SA1 Stage 1 80%
SP-230390 - 3GPP TSG#99, 20 -24 March 2023, Rotterdam, The Netherlands

## Slide 4: SA2 meeting dates for 2023 & 2024
SA2#158 | Monday, August 21, 2023 | Friday, August 25, 2023 | Goteborg, SE
SA2#159 | Monday, October 9, 2023 | Friday, October 13, 2023 | Xiamen, CN
SA2#160 | Monday, November 13, 2023 | Friday, November 17, 2023 | Chicago, US
SA2-Ad Hoc | Monday, January 22, 2024 | Friday, January 26, 2024 | TBD
SA2#161 | Monday, February 26, 2024 | Friday, March 1, 2024 | EU, EU
SA2#162 | Monday, April 15, 2024 | Friday, April 19, 2024 | CN (TBC)
SA2#163 | Monday, May 27, 2024 | Friday, May 31, 2024 | Korea, KR
SA2#164 | Monday, August 19, 2024 | Friday, August 23, 2024 | EU, EU
SA2#165 | Monday, October 14, 2024 | Friday, October 18, 2024 | India, IN
SA2#166 | Monday, November 18, 2024 | Friday, November 22, 2024 | US (TBC)

## Slide 5
SA2#159 Dates/Agenda
SA2#159 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X
  AI 8.X: Rel-17 Maintenance
  AI 9.X: Rel-18 Maintenance
  AI 19.X: Rel-19 approved study/work items
  AI 30.X: Rel-19 WID/SID proposals
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting.
Doc request deadline | Friday 29 September 2023 |  | 2359 UTC
Doc submission deadline | Friday 29 September 2023 |  | 2359 UTC
Registration | Monday 2 October 2023 |  | 0800 UTC
Start of meeting | Monday 9 October 2023 | 0900 Local time | 0100 UTC
Close of meeting | Friday 13 October 2023 | 1600 Local time (or earlier) | 0800 UTC
Upload approved documents | Friday 13 October 2023 | 1700 Local time | 0900 UTC

## Slide 6
SA2#160 Dates/Agenda
SA2#160 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X
  AI 8.X: Rel-17 Maintenance
  AI 9.X: Rel-18 Maintenance
  AI 19.X: Rel-19 approved study/work items
  AI 30.X: Rel-19 WID/SID proposals
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting.
Doc request deadline | Friday 3 November 2023 |  | 2359 UTC
Doc submission deadline | Friday 3 November 2023 |  | 2359 UTC
Registration | Monday 6 November 2023 |  | 0800 UTC
Start of meeting | Monday 13 November 2023 | 0900 Local time | 1500 UTC
Close of meeting | Friday 17 November 2023 | 1600 Local time (or earlier) | 2200 UTC
Upload approved documents | Friday 17 November 2023 | 1700 Local time | 2300 UTC

## Slide 7: Rel-19 planning for SA2
Final package for SA2 planned to be approved in December (SA#102)
The Rel-19 studies should complete no later than SA2#163 (May 2024)
  In general it is not expected that study work on any KI’s will continue beyond this date
  WIDs based on the outcomes of the studies to be agreed by SA2 in SA2#163 and submitted to SA#104 (June 2024)
Normative work on these studies can start in SA2#164 (August 2024)
Normative work shall complete no later than SA2#166 (November 2024)
Discussion of TEI-19 items can start from January 2024
  Submission and discussion/endorsement of candidates in the January Ad Hoc
  Submission and discussion/agreement of candidates in SA2#161 (February 2024)
    Candidates will only be agreed in the second meeting
  Decision on which TEI-19 items will be agreed will be in SA2#161 (February 2024)
  The total TU budget available for TEI-19 will be 8 TU’s
  Work can start on TEI-19 items in SA2#162 (April 2024)

## Slide 8: TEI-19 planning
Sources of TEI-19 items
  TEI-19 items arising from NWM discussions in Q3 2023
  TEI-19 items arising from NWM discussions in Q4 2023
  TEI-19 items proposed when submissions are invited
TEI-19 proposals should avoid WTs that were decided not to be included in Rel-19 SIDs/WIDs unless they were identified as TEI-19 candidates during moderated discussions
As usual, TEI-19 proposals need to finish within 1 plenary cycle