## Slide 1: Status report template and guidance
Andy Bennett
SA2 Chair
SA WG2 Meeting #169 Fukuoka
May 19 – May 23, 2025

## Slide 2: Status report template and guidance
There are two audiences for the status reports
  Directly - the officials and delegates of SA2
  Indirectly – the officials and delegates of TSG SA
The SA2 audience needs the information after each meeting
The TSG SA audience needs the information once a quarter
  The information is provided to TSG SA in the SA2 report to TSG SA
  Each Study + Work Item in the current release has one slide (taken from the rapporteur status reports) and is also included in summary slides based on the information in that slide
  Consistency of format and content is important – and should fit on one slide

## Slide 3: Status report template and guidance
So there needs to be a slide in the format below in the status report for the meeting prior to the Plenary
If the target dates have changed then this should be shown on this slide

## Slide 4: Status report template and guidance
After each SA2 meeting the status report should include a slide summarizing the status and progress in that meeting
  The format should be the same as shown in the previous slide
  The status report from the meeting prior to the Plenary should contain a status slide from each meeting in that quarter, and a slide summarizing the progress in that quarter
It should also contain a slide showing the work plan (see right)
It would also be helpful to include as backup slides the status reports from at least 2 previous meetings

## Slide 5: Status report template and guidance
After each SA2 meeting the status report should also include slides listing the issues
As endorsed in the Best Practice for SA2 studies document (S2-2504416):
    Substantial issues identified during the work should be included in the report, and any resolutions documented. The record of these issues shall remain in future reports.
Tables of these issues are suggested to be used
Issue # | Description | Identified in | Resolution | Resolved in
1 | [Description of the issue] | Eg SA2#169 | [Describe how the issue was resolved] | Eg SA2#170