## Slide 1: SA2 Work Planning
Andy Bennett
SA2 Chair
SA WG2 Meeting #169 Fukuoka
May 19 – May 23, 2025

## Slide 2: SA2 and SA meeting dates for 2025
Q1 | SA2-Ad Hoc | Monday, January 20, 2025 | Friday, January 24, 2025 | Electronic
 | SA2#167 | Monday, February 17, 2025 | Friday, February 21, 2025 | Athens, Greece
 | SA#107 | Wednesday, March 12, 2025 | Friday, March 14, 2025 | Incheon, Korea
Q2 | SA2#168 | Monday, April 07, 2025 | Friday, April 11, 2025 | Goteborg, Sweden
 | SA2#169 | Monday, May 19, 2025 | Friday, May 23, 2025 | Fukuoka, Japan
 | SA#108 | Tuesday, June 10, 2025 | Friday, June 13, 2025 | Prague, Czech Republic
Q3 | SA2#170 | Monday, August 25, 2025 | Friday, August 29, 2025 | Goteborg, Sweden
 | SA#109 | Tuesday, September 16, 2025 | Friday, September 19, 2025 | Beijing, China
Q4 | SA2#171 | Monday, October 13, 2025 | Friday, October 17, 2025 | Wuhan, China
 | SA2#172 | Monday, November 17, 2025 | Friday, November 21, 2025 | Dallas, USA
 | SA#110 | Tuesday, December 09, 2025 | Friday, December 12, 2025 | Baltimore, USA

## Slide 3: Rel-19 planning for SA2 - General
AmbientIoT-ARC
  The WID was approved in SA#107 and normative work will need to conclude in this meeting
Maintenance work is well under way on the other Work Items
But the planning for Rel-20 anticipates a rapid reduction in time dedicated to Rel-19 maintenance over the next few meetings
Per-company quota of 4 per AI will be applied in August (excluding AmbientIoT-ARC) – excluding LS responses, discussion documents
 |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026
 |  | Apr #168 Goteborg | May #169 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Aug #176 EU | Oct #177 EU | Nov #178 US
Rel-19 |  |  |  |  |  |  |  |  |  |  |  | 
19.x | Original planned total TU's | 11 | 11 | 9 | 6 | 6 | 4 | 4 | 4 | 3 | 3 | 3

## Slide 4: Rel-20 planning
(See SP-240458 endorsed in SA#103 Maastricht)
Studies for 6G in 3GPP are expected to start from Release 20
  First TSG-wide 6G workshop held in March 2025
  SA1 SID was approved in Sept 2024
  SA2 SID is expected to be approved in June 2025
  SA2 6G SI completion: No later than Mar 2027 (see SP-250416 endorsed in SA#107)
    SA will have check point in Dec 2025 to further review SA2 6G SI completion date and make final decision on whether it is Dec 2026 or Mar 2027
For 5G-Advanced
  Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
  100% means no exceptions in September

## Slide 5: Rel-20 planning – TEI20
12 TU’s are proposed for handling TEI20 items
TEI20 proposals were invited to be submitted for information to SA2#170 Fukuoka
We can try to identify all TEI20 items in August but it could make sense to have two opportunities for TEI20 proposals
In the plan below items filling up to 8 TU’s will be discussed in August 2025
Items filling up to 4 TU’s will be discussed in February 2026
Items noted in August 2025 are not encouraged to be re-submitted in February 2026
Proposed meeting by meeting plan
2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
May #169 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Aug #176 EU
 |  |  |  |  |  | Stage 2 80% | Stage 2 100%
Proposals for information | Proposals for SA2 approval |  | Proposals for information | Proposals for SA2 approval |  |  | 
 |  | Approved items on agenda | Approved items on agenda | Approved items on agenda | Approved items on agenda | Approved items on agenda | Approved items on agenda

## Slide 6: Rel-20 planning – 5GA item planning
Planning of 5GA study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
 | Apr #168 Goteborg | May #169 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Aug #176 EU
 |  |  |  |  | Study deadline A | Study deadline B |  | Stage 2 80% | Stage 2 100%
Items starting in April | Meeting #1 | Meeting #2 | Meeting #3 | Meeting #4 | Meeting #5 | Meeting #6 | Meeting #7 | Meeting #8 | Meeting #9
Priority | KI’s | Solutions | Solutions | Solution updates, conclusions | Solution updates, conclusions | Normative | Normative | Normative | Normative
Items starting in August |  |  | Meeting #1 | Meeting #2 | Meeting #3 | Meeting #4 | Meeting #5 | Meeting #6 | Meeting #7
Priority |  |  | KI’s | Solutions | Solutions, conclusions | Solution updates, conclusions | Normative | Normative | Normative

## Slide 7: Upcoming meetings in Q3 2025

## Slide 8
SA2#170 (Goteborg) Dates/Agenda
SA2#170 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Quota limited: 2 per company per AI
  AI 19.X: Rel-19 maintenance
    Quota limited: 4 per company per AI (excluding AmbientIoT-ARC)
  AI 20.X: Approved SIDs
  AI 30.X: TEI20 proposals for approval
Doc request deadline | Friday 15 August 2025 |  | 2359 UTC
Doc submission deadline | Friday 15 August 2025 |  | 2359 UTC
Registration | Monday 18 August 2025 |  | 0800 UTC
Start of meeting | Monday 25 August 2025 | 0900 Local time | 0700 UTC
Close of meeting | Friday 29 August 2025 | 1630 Local time (or earlier) | 1430 UTC
Upload approved documents | Friday 29 August 2025 | 1730 Local time | 1530 UTC
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting