## Slide 1: Status report for EnergySys Phase 2
Konstantinos Samdanis (Lenovo)
Zhuoyi Chen (China Telecom)

## Slide 2: FS_EnergySys_Ph2 Status at SA2#170
  Progress – 7 pCRs Agreed
  Approved 4 solutions related to KI2
  Approved 3 solutions related to KI3
Submit cover sheet to plenary for information
  Impacts and dependencies on other WGs
  Dependency on SA5 related to renewable energy.
  Contentious issues
  How to enhance the accuracy of energy-related metric calculations, i.e., exclude calculation of energy consumption when an NF does not handle any traffic, and if this information is useful for policy selection.
  Support the exposure of information related to renewable energy usage and if SA2 shall create the means of exposing this information before SA5 agree on how to calculate it.
  Select the parameters that can be considered for NF selection based on energy criteria.
  Next steps:
  Try to capture principles and conclusions.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070058 | New SID on Energy Efficiency and Energy Saving Phase 2 | FS_EnergySys_Ph2 | 12/12/2025 | 50% | SP-250417 | 85% | 

## Slide 3: FS_EnergySys_Ph2 Work Plan
Meeting | Date | Planned TUs | Actual Used TUs | Action plan
SA2#168 | Apr. 2025 | 1 | 1 | TR skeleton, scope, Terms, Architectural assumptions & Requirements Key Issues for all WTs.
SA2#169 | May 2025 | 2 | 2 | Key Issue updates (if necessary), New solutions for approved Key Issues.
SA2#170 | Aug. 2025 | 1 | 1 | New solutions and solution updates. Last meeting for new solutions.
SA#109 | Sep. 2025 | - | - | For information
SA2#171 | Oct. 2025 | 1 |  | Solution updates. Evaluation and conclusion.
SA2#172 | Nov.2025 | 1 |  | Conclusion.
SA#110 | Dec 2025 | - | - | For Approval
 | Total | 6 | 4 |