## Slide 1: SA2 Work Planning
Andy Bennett
SA2 Chair
SA WG2 Meeting #171 Wuhan
October 13 – October 17, 2025

## Slide 2: SA2 and SA meeting dates for 2025
Q1 | SA2-Ad Hoc | Monday, January 20, 2025 | Friday, January 24, 2025 | Electronic
 | SA2#167 | Monday, February 17, 2025 | Friday, February 21, 2025 | Athens, Greece
 | SA#107 | Wednesday, March 12, 2025 | Friday, March 14, 2025 | Incheon, Korea
Q2 | SA2#168 | Monday, April 07, 2025 | Friday, April 11, 2025 | Goteborg, Sweden
 | SA2#170 | Monday, May 19, 2025 | Friday, May 23, 2025 | Fukuoka, Japan
 | SA#108 | Tuesday, June 10, 2025 | Friday, June 13, 2025 | Prague, Czech Republic
Q3 | SA2#170 | Monday, August 25, 2025 | Friday, August 29, 2025 | Goteborg, Sweden
 | SA#109 | Tuesday, September 16, 2025 | Friday, September 19, 2025 | Beijing, China
Q4 | SA2#171 | Monday, October 13, 2025 | Friday, October 17, 2025 | Wuhan, China
 | SA2#172 | Monday, November 17, 2025 | Friday, November 21, 2025 | Dallas, USA
 | SA#110 | Tuesday, December 09, 2025 | Friday, December 12, 2025 | Baltimore, USA

## Slide 3: Rel-20 planning – 5G Advanced
Stage-2 freeze
  Jun 2026 (>=80%)
  Sep 2026 (100%)
Study Item deadlines
Study deadline A applies to FS_5GSAT_Ph4_ARC, FS_Sensing_ARC, FS_AIML_CN_Ph2 and FS_EnergySys_Ph2
Study deadline B applies to FS_AmbientIoT_Ph2_ARC, FS_NG_RTC_Ph3_ARC and FS_SMS2EC_ARC
No exceptions are expected to the Stage 2 100% freeze as Stage 3 group require sufficient time for their work
This means it is essential that normative work starts promptly after the respective study deadlines
 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
 | Apr #168 Goteborg | May #170 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Aug #176 EU
 |  |  |  |  | Study deadline A | Study deadline B |  | Stage 2 80% | Stage 2 100%

## Slide 4: Rel-20 planning – 6G
Previously endorsed high level plan
  SA2#170 August 2025
    Input papers to provide justification and clarification of Work Task scope
    During the meeting assess for each WT whether Key Issue submission can start in the next meeting
      (Drafting of Key Issues during the meeting is not precluded)
    Document agreed Work Task scope updates in an annex of the TR
    Input papers on architectural assumptions and principles, with a focus on WT’s in August
  SA2#171 October 2025
    Start Key Issue discussions for Work Tasks identified in previous meeting
    For the Work Tasks not identified in previous meeting as ready for Key Issues, continue 1. 2. and 3. above
    Input papers on architectural assumptions and principles
  SA2#172 November 2025
    Continue as in SA2#171 for Work Tasks and Key Issues
    Completion of Key Issues, Arch assumptions and principles is in general targeted for the end of this meeting unless there are dependencies on other WG’s
    Update Study Item Description with updated Work Task descriptions from the TR annex
    Add TU estimates and completion date to the SID
    Input papers on architectural assumptions and principles

## Slide 5: Rel-20 planning – 6G
The plan is for the 6G SID to be updated in November and submitted to the December SA Plenary

## Slide 6: Rel-20 planning – TEI20
12 TU’s are proposed for handling TEI20 items
Items filling 7.5 TU’s have already been approved by SA Plenary
Items filling up to 4.5 TU’s will be discussed in February 2026
Items noted in August 2025 are not encouraged to be re-submitted in February 2026
Meeting by meeting plan:
2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
May #170 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Aug #176 EU
 |  |  |  |  |  | Stage 2 80% | Stage 2 100%
Proposals for information | Proposals for SA2 approval |  | Proposals for information | Proposals for SA2 approval |  |  | 
 |  | Approved items on agenda | Approved items on agenda | Approved items on agenda | Approved items on agenda | Approved items on agenda | Approved items on agenda

## Slide 7: Upcoming meetings

## Slide 8
SA2#172 (Dallas) Dates/Agenda
SA2#172 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Handling Incoming LS only
  AI 19.X: Rel-19 maintenance
    Subset only:
      5GSAT_Ph3-ARC
      NG_RTC_Ph2
      XRM_Ph2
      EnergySys
      AmbientIoT-ARC
      AIML_CN
    But LS’s in the other topics can be handled
    Quota limited: 4 per company per AI
  AI 20.X: Approved WIDs and SIDs (including TEI20)
  TEI20 proposals for information
Doc request deadline | Friday 07 November 2025 |  | 2359 UTC
Doc submission deadline | Friday 07 November 2025 |  | 2359 UTC
Registration | Monday 10 November 2025 |  | 0800 UTC
Start of meeting | Monday 17 November 2025 | 0900 Local time | 1500 UTC
Close of meeting | Friday 21 November 2025 | 1630 Local time (or earlier) | 2230 UTC
Upload approved documents | Friday 21 November 2025 | 1730 Local time | 2330 UTC
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting

## Slide 9
SA2#173 (India) Dates/Agenda
SA2#173 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Quota limited: 2 per company per AI
  AI 19.X: Rel-19 maintenance
    Quota limited: 4 per company per AI
  AI 20.X: Approved WIDs and SIDs (including TEI20)
  TEI20 proposals for approval
Doc request deadline | Friday 30 January 2026 |  | 2359 UTC
Doc submission deadline | Friday 30 January 2026 |  | 2359 UTC
Registration | Monday 02 February 2026 |  | 0800 UTC
Start of meeting | Monday 09 February 2026 | 0900 Local time | 0430 UTC
Close of meeting | Friday 13 February 2026 | 1630 Local time (or earlier) | 1200 UTC
Upload approved documents | Friday 13 February 2026 | 1730 Local time | 1300 UTC
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting